## MASTER SHEET -MARATHA SITE
S No | Description | TW1 | W1 | TW2 | W2 | TW | W |  | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
C | Statutory Approvals | 0.999% | 0.999% | 0.999% | 0.999% | 0% | 0% | Statutory Approvals | 2024-03-01: 0.357%; 2024-07-01: 0.214%; 2024-08-01: 0.143%; 2024-09-01: 0.071%; 2025-05-01: 0.071%; 2025-08-01: 0.143%; 2025-12-01: 0%
C | Pre Project Activity | 1% | 1% | 1% | 1% | 0% | 0% | Pre Project Activity | 2024-03-01: 0.6%; 2024-04-01: 0.2%; 2024-05-01: 0.2%; 2025-12-01: 0%
C | Tendering and Contracting | 9.999% | 3% | 9.999% | 3% | 0% | 0% | Contractor Finalization | 0% | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.5% | 0.5% | 0.5% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Tendering and Contracting |  | 4.999% |  | 4.999% |  | 0% | Mechanical Packages | 0% | 0% | 0.9458% | 0.608% | 1.081% | 0.8782% | 0.6755% | 0.5404% | 0% | 0.06755% | 0.1351% | 0.06755% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Tendering and Contracting |  | 1.5% |  | 1.5% |  | 0% | E & I Packages | 0% | 0% | 0.05357% | 0.1071% | 0.2143% | 0.3214% | 0.2143% | 0.2679% | 0.2143% | 0.05357% | 0.05357% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Tendering and Contracting |  | 0.5% |  | 0.5% |  | 0% | Process Packages | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.35% | 0.15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering | 15% | 3.5% | 15% | 3.5% | 0% | 0% | Mechanical and Process | 0% | 0.07523% | 0.6706% | 0.2486% | 0.6902% | 0.35% | 0.01963% | 0.1014% | 0.006542% | 0.9911% | 0.2944% | 0.05234% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering |  | 0.999% |  | 0.999% |  | 0% | Plate Fabrication Drawings | 0% | 0% | 0% | 0% | 0% | 0% | 0.1064% | 0.2642% | 0.5604% | 0.03116% | 0.01409% | 0.01348% | 0.009235% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering |  | 3.001% |  | 3.001% |  | 0% | Civil Engineering | 0% | 0% | 0% | 0% | 0.4301% | 0.4347% | 0.2812% | 0.1047% | 0.3808% | 0.4134% | 0.4113% | 0.2628% | 0.1523% | 0.1296% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering |  | 3% |  | 3% |  | 0% | Structural Engineering - GA | 0% | 0% | 0% | 0% | 0% | 0.0221% | 0.3549% | 0.5613% | 0.2516% | 0.637% | 0.6395% | 0.5337% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering |  | 1.501% |  | 1.501% |  | 0% | Structural Engineering - Tekla | 0% | 0% | 0% | 0% | 0% | 0.01167% | 0.07679% | 0.4098% | 0.007905% | 0.05326% | 0.6029% | 0.3386% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Engineering |  | 3.002% |  | 3.002% |  | 0% | E&I Engg. | 0% | 0% | 0% | 0% | 0.01468% | 0.1321% | 0.2569% | 0.2569% | 0.4771% | 0.4771% | 0.4771% | 0.4404% | 0.323% | 0.1468% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery | 25% | 1% | 25% | 1% | 0% | 0% | Fabricated Items - Structural (MANUF) | 0% | 0% | 0% | 0% | 0% | 0.001913% | 0.003827% | 0.07218% | 0.06429% | 0.01641% | 0.03325% | 0.06611% | 0.1115% | 0.1745% | 0.2316% | 0.1436% | 0.08089% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 1% |  | 1% |  | 0% | Fabricated Items - Structural (INSPE) | 0% | 0% | 0% | 0% | 0% | 0.001913% | 0.003827% | 0.07218% | 0.06429% | 0.01641% | 0.03325% | 0.06611% | 0.1115% | 0.1745% | 0.2316% | 0.1436% | 0.08089% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 2% |  | 2% |  | 0% | Fabricated Items - Structural (DILEVERY) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.003827% | 0.007654% | 0.1444% | 0.1286% | 0.03282% | 0.06649% | 0.1322% | 0.223% | 0.3489% | 0.4632% | 0.2871% | 0.1618% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 6% |  | 6% |  | 0% | Equipment's (M) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.8333% | 1.083% | 1.25% | 0.8333% | 0.8333% | 0.4167% | 0.08333% | 0.08333% | 0.08333% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 2% |  | 2% |  | 0% | Equipment's (IN) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1667% | 0.2778% | 0.3611% | 0.4167% | 0.2778% | 0.2778% | 0.1389% | 0.02778% | 0.02778% | 0.02778% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 5.5% |  | 5.5% |  | 0% | Equipment's (DEL) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0549% | 0.1098% | 0.3297% | 0.55% | 1.045% | 1.155% | 0.715% | 0.55% | 0.4398% | 0.3297% | 0.2216% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 3% |  | 3% |  | 0% | Electrical Items (M) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2778% | 0.3889% | 0.4444% | 0.6111% | 0.5% | 0.3333% | 0.2222% | 0.1667% | 0.05556% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 1.001% |  | 1.001% |  | 0% | Electrical Items (IN) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.09269% | 0.1298% | 0.1483% | 0.2039% | 0.1668% | 0.1112% | 0.07415% | 0.05561% | 0.01854% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 1.999% |  | 1.999% |  | 0% | Electrical Items (DEL) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.07404% | 0.03702% | 0.2591% | 0.3332% | 0.3702% | 0.2961% | 0.2961% | 0.2221% | 0.1111% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 1.001% |  | 1.001% |  | 0% | TOR/Structural Steel | 0% | 0% | 0% | 0% | 0.03131% | 0.02885% | 0.02955% | 0.05711% | 0.08391% | 0.1084% | 0.1432% | 0.1254% | 0.1013% | 0.08232% | 0.06268% | 0.05951% | 0.06344% | 0.02398% | 0% | 0% | 0% | 0% | 0% | 0%
C | Delivery |  | 0.5% |  | 0.5% |  | 0% | Refractory | 2025-03-01: 0.1%; 2025-04-01: 0.1%; 2025-05-01: 0.1%; 2025-06-01: 0.1%; 2025-07-01: 0.1%; 2025-12-01: 0%
C | Construction | 41.17% | 2% | 43% | 2% | -1.832% | 0% | Excavation | 0% | 0% | 0.1295% | 0.1924% | 0.07113% | 0.02634% | 0.02054% | 0.06474% | 0.1318% | 0.1062% | 0.219% | 0.1318% | 0.2934% | 0.4664% | 0.1467% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Construction |  | 14.78% |  | 15% |  | -0.2242% | RCC | 0% | 0% | 0% | 0% | 0% | 0.1233% | 0.5746% | 0.6424% | 0.6584% | 0.6266% | 0.7185% | 0.7969% | 1.486% | 1.489% | 1.639% | 1.578% | 1.396% | 1.325% | 0.9268% | 0.4859% | 0.3102% | 0.2242% | 0% | 0%
C | Construction |  | 4% |  | 4% |  | 0% | Plate Fabrication | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1539% | 0.1924% | 0.3979% | 0.5642% | 0.6299% | 0.556% | 0.5402% | 0.4685% | 0.257% | 0.24% | 0% | 0% | 0% | 0% | 0%
C | Construction |  | 6.727% |  | 7.001% |  | -0.2743% | Structure Erection | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1216% | 0.3346% | 0.3573% | 0.851% | 1.123% | 1.17% | 1.321% | 0.999% | 0.4484% | 0.2743% | 0% | 0%
C | Construction |  | 9.226% |  | 10% |  | -0.7748% | Mechnaical Erection (P + E) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03116% | 0.1758% | 0.4213% | 0.6599% | 0.8734% | 1.05% | 1.532% | 1.757% | 1.59% | 1.136% | 0.7232% | 0.05162% | 0%
C | Construction |  | 3.618% |  | 4% |  | -0.3815% | Electrical & Instrument | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3485% | 0.6461% | 0.8998% | 0.981% | 0.7429% | 0.2974% | 0.08416% | 0%
C | Construction |  | 0.8225% |  | 1% |  | -0.1775% | Refractory & Insulation | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0554% | 0.103% | 0.1426% | 0.1743% | 0.1524% | 0.1949% | 0.1613% | 0.01623% | 0%
C | Construction |  | 0% |  | 0% |  | 0% | Electrical & Instrument | bar: 2024-01-01 to 2025-12-01
C | Construction |  | 0% |  | 0% |  | 0% | Electrical & Instrument | bar: 2024-01-01 to 2025-12-01
C | Construction |  | 0% |  | 0% |  | 0% | Refractory | bar: 2024-01-01 to 2025-12-01
C | Commissioning | 0% | 0% | 5% | 2% | -5% | -5% | No Load Trials | 2025-10-01: 1.2%; 2025-11-01: 0.8%; 2025-12-01: 0%
C | Commissioning |  | 0% |  | 1% |  | 0% | Group Trials | 2025-10-01: 0.6%; 2025-11-01: 0.4%; 2025-12-01: 0%
C | Commissioning |  | 0% |  | 1% |  | 0% | Kiln Light Up | bar: 2024-01-01 to 2025-12-01
C | Commissioning |  | 0% |  | 1% |  | 0% | Commissioning with WT | bar: 2024-01-01 to 2025-12-01
1 | Month Plan | [7 empty] | 0% | 0.07523% | 2.832% | 1.356% | 2.733% | 2.333% | 3.332% | 4.729% | 5.366% | 6.619% | 6.759% | 6.87% | 6.599% | 6.67% | 5.7% | 5.873% | 6.269% | 6.036% | 5.914% | 4.351% | 2.832% | 3.48% | 3.352% | -100.1%
2 | Cumulative Plan | [7 empty] | 0% | 0.07523% | 2.907% | 4.263% | 6.996% | 9.328% | 12.66% | 17.39% | 22.76% | 29.37% | 36.13% | 43% | 49.6% | 56.27% | 61.97% | 67.85% | 74.11% | 80.15% | 86.06% | 90.42% | 93.25% | 96.73% | 100.1% | -1041%
C | Statutory Approvals | 0.57% | 0.57% | 0.999% | 0.999% | -0.429% | -0.429% | Statutory Approvals | 2024-03-01: 0.36%; 2024-05-01: 0.07%; 2024-09-01: 0.07%; 2025-01-01: 0.07%; 2025-12-01: 0.429%
C | Pre Project Activity | 1% | 1% | 1% | 1% | 0% | 0% | Pre Project Activity | 2024-03-01: 0.6%; 2024-04-01: 0.2%; 2024-05-01: 0.2%; 2025-12-01: 0%
C | Tendering and Contracting | 7.57% | 2% | 9.999% | 3% | -2.429% | -1% | Contractor Finalization | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.5% | 0% | 0.5% | 0% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1%
C | Tendering and Contracting |  | 4.594% |  | 4.999% |  | -0.4053% | Mechanical Packages | 0% | 0% | 0.4729% | 1.419% | 0.608% | 0.4053% | 0.8106% | 0.3378% | 0.1351% | 0.06755% | 0.2027% | 0% | 0.06755% | 0% | 0.06755% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4053%
C | Tendering and Contracting |  | 0.7768% |  | 1.5% |  | -0.7232% | E & I Packages | 0% | 0% | 0.02679% | 0.02679% | 0.05357% | 0% | 0.05357% | 0.08036% | 0.1339% | 0.1071% | 0.02679% | 0.05357% | 0.05357% | 0.08036% | 0.08036% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7232%
C | Tendering and Contracting |  | 0.2% |  | 0.5% |  | -0.3% | Process Packages | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.15% | 0% | 0.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3%
C | Engineering | 14.08% | 3.382% | 15% | 3.5% | -0.9211% | -0.1178% | Mechanical and Process | 0% | 0% | 0.664% | 0.2879% | 0.2126% | 0.35% | 0.2388% | 0.3206% | 0.2453% | 0.2453% | 0.3762% | 0.1047% | 0.2093% | 0.06869% | 0.03598% | 0.0229% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1178%
C | Engineering |  | 0.8835% |  | 0.999% |  | -0.1155% | Plate Fabrication Drawings | 0% | 0% | 0% | 0% | 0% | 0% | 0.3877% | 0% | 0.06793% | 0% | 0.2335% | 0.1697% | 0.01674% | 0% | 0% | 0.007876% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1155%
C | Engineering |  | 2.998% |  | 3.001% |  | -0.003445% | Civil Engineering | 0% | 0% | 0.2223% | 0.1459% | 0.2417% | 0.2453% | 0.2254% | 0.1304% | 0.7153% | 0.2213% | 0.2322% | 0.3364% | 0.2432% | 0.01723% | 0% | 0.02088% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.003445%
C | Engineering |  | 2.953% |  | 3% |  | -0.04678% | Structural Engineering - GA | 0% | 0% | 0% | 0% | 0% | 0% | 0.9423% | 0.1564% | 0.1937% | 0.1722% | 0.1636% | 0.1392% | 0.5697% | 0.6161% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04678%
C | Engineering |  | 1.333% |  | 1.501% |  | -0.1679% | Structural Engineering - Tekla | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1026% | 0.09627% | 0.1129% | 0.1073% | 0.09382% | 0.1388% | 0.2458% | 0.4356% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1679%
C | Engineering |  | 2.532% |  | 3.002% |  | -0.4698% | E&I Engg. | 0% | 0% | 0% | 0% | 0.01468% | 0.1908% | 0% | 0.0367% | 0.1468% | 0.1468% | 0.0734% | 1.13% | 0.00734% | 0.0734% | 0% | 0.712% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4698%
C | Delivery | 11.37% | 0.5968% | 25% | 1% | -13.63% | -0.4032% | Fabricated Items - Structural (MANUF) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02186% | 0.02971% | 0.05425% | 0.07127% | 0.1424% | 0.2773% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4032%
C | Delivery |  | 0.5968% |  | 1% |  | -0.4032% | Fabricated Items - Structural (INSPE) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02186% | 0.02971% | 0.05425% | 0.07127% | 0.1424% | 0.2773% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4032%
C | Delivery |  | 0.594% |  | 2% |  | -1.406% | Fabricated Items - Structural (DILEVERY) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04372% | 0.05941% | 0.1085% | 0.1425% | 0.0487% | 0.1912% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.406%
C | Delivery |  | 4% |  | 6% |  | -2% | Equipment's (M) | 0% | 0% | 0% | 0% | 0% | 0% | 0.08333% | 0.08333% | 1.5% | 0.8333% | 0.5% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2%
C | Delivery |  | 1.333% |  | 2% |  | -0.6667% | Equipment's (IN) | 0% | 0% | 0% | 0% | 0% | 0% | 0.02778% | 0.02778% | 0.5% | 0.2778% | 0.1667% | 0% | 0% | 0.3333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6667%
C | Delivery |  | 2.497% |  | 5.5% |  | -3.003% | Equipment's (DEL) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1406% | 0.3762% | 0.5573% | 0.2949% | 0.2226% | 0.9055% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.003%
C | Delivery |  | 0.7222% |  | 3% |  | -2.278% | Electrical Items (M) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1111% | 0% | 0.1667% | 0% | 0% | 0.3333% | 0% | 0.1111% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.278%
C | Delivery |  | 0.241% |  | 1.001% |  | -0.76% | Electrical Items (IN) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03707% | 0% | 0.05561% | 0% | 0% | 0.1112% | 0% | 0.03707% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.76%
C | Delivery |  | 0.1481% |  | 1.999% |  | -1.851% | Electrical Items (DEL) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03702% | 0.03702% | 0% | 0% | 0% | 0.03702% | 0.03702% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.851%
C | Delivery |  | 0.6405% |  | 1.001% |  | -0.3605% | TOR/Structural Steel | 0% | 0% | 0% | 0.003987% | 0.01372% | 0.01231% | 0.0618% | 0.03594% | 0.02187% | 0.0747% | 0.07112% | 0.02422% | 0.05154% | 0.07622% | 0.1665% | 0.02656% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3605%
C | Delivery |  | 0% |  | 0.5% |  | -0.5% | Process Packages | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5%
C | Construction | 9.832% | 2% | 43% | 2% | -33.17% | 3.118e-06% | Excavation | 2024-01-01: 0%; 2024-02-01: 0%; 2024-03-01: 0.1581%; 2024-04-01: 0.387%; 2024-05-01: 0.2673%; 2024-06-01: 0.08053%; 2024-07-01: 0.02039%; 2024-08-01: 0.00768%; 2024-09-01: 0.03502%; 2024-10-01: 0.0651%; 2024-11-01: 0.178%; 2024-12-01: 0.1959%; 2025-01-01: 0.3459%; 2025-02-01: 0.1345%; 2025-03-01: 0.1246%; 2025-12-01: -3.118e-06%
C | Construction |  | 6.062% |  | 15% |  | -8.939% | RCC | 0% | 0% | 0% | 0% | 0.05511% | 0.1242% | 0.5401% | 0.6384% | 0.6112% | 0.6725% | 0.5492% | 0.5578% | 0.7327% | 0.5673% | 0.5014% | 0.4735% | 0.03875% | 0% | 0% | 0% | 0% | 0% | 0% | 8.939%
C | Construction |  | 0.6985% |  | 4% |  | -3.301% | Plate Fabrication | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02759% | 0.04336% | 0.05913% | 0.1506% | 0.1861% | 0.08751% | 0.1443% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.301%
C | Construction |  | 0.2076% |  | 7.001% |  | -6.793% | Structure Erection | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.001005% | 0% | 0.1165% | 0.06196% | 0.02813% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.793%
C | Construction |  | 0.8631% |  | 10% |  | -9.138% | Mechnaical Erection (P + E) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1265% | 0.2535% | 0.2116% | 0.02976% | 0.2418% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.138%
C | Construction |  | 0% |  | 4% |  | -4% | Electrical & Instrument | bar: 2024-01-01 to 2025-12-01
C | Construction |  | 0% |  | 1% |  | -1% | Refractory & Insulation | bar: 2024-01-01 to 2025-12-01
C | Construction |  | 0% |  | 0% |  | 0% | Electrical & Instrument | bar: 2024-01-01 to 2025-11-01
C | Construction |  | 0% |  | 0% |  | 0% | Electrical & Instrument | bar: 2024-01-01 to 2025-11-01
C | Construction |  | 0% |  | 0% |  | 0% | Refractory | bar: 2024-01-01 to 2025-11-01
C | Commissioning | 0% | 0% | 5% | 2% | -5% | -5% | No Load Trials | bar: 2024-01-01 to 2025-11-01
C | Commissioning |  | 0% |  | 1% |  | 0% | Group Trials | bar: 2024-01-01 to 2025-11-01
C | Commissioning |  | 0% |  | 1% |  | 0% | Kiln Light Up | bar: 2024-01-01 to 2025-11-01
C | Commissioning |  | 0% |  | 1% |  | 0% | Commissioning with WT | bar: 2024-01-01 to 2025-11-01
3 | Month Actual | [7 empty] | 0% | 0% | 2.504% | 2.47% | 1.737% | 1.908% | 3.892% | 2.108% | 5.121% | 3.111% | 3.911% | 3.487% | 3.685% | 4.752% | 2.184% | 3.514% | 0.03875% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Cumulative Actual | [7 empty] | 0% | 0% | 2.504% | 4.974% | 6.711% | 8.619% | 12.51% | 14.62% | 19.74% | 22.85% | 26.76% | 30.25% | 33.93% | 38.69% | 40.87% | 44.38% | 44.42% | 44.42% | 44.42% | 44.42% | 44.42% | 44.42% | 44.42%
5 | Month Forecast | bar: 2025-04-01 to 2025-11-01
6 | Cumulative Forecast | bar: 2025-04-01 to 2025-11-01
Plan Till Date
[24 empty] | 66.6667 | 71.4286 | 76.1905 | 80.9524 | 85.7143 | 90.4762 | 95.2381 | 100
[24 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[8 empty] | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
[8 empty] | Month Plan | 0% | 0.07523% | 2.832% | 1.356% | 2.733% | 2.333% | 3.332% | 4.729% | 5.366% | 6.619% | 6.759% | 6.87% | 6.599% | 6.67% | 5.7% | 5.873% | 6.269% | 6.036% | 5.914% | 4.351% | 2.832% | 3.48% | 3.352%
[8 empty] | Cumulative Plan | 0% | 0.07523% | 2.907% | 4.263% | 6.996% | 9.328% | 12.66% | 17.39% | 22.76% | 29.37% | 36.13% | 43% | 49.6% | 56.27% | 61.97% | 67.85% | 74.11% | 80.15% | 86.06% | 90.42% | 93.25% | 96.73% | 100.1%
[8 empty] | Month Actual | 0% | 0% | 2.504% | 2.47% | 1.737% | 1.908% | 3.892% | 2.108% | 5.121% | 3.111% | 3.911% | 3.487% | 3.685% | 4.752% | 2.184% | 3.514% | 0.03875%
[8 empty] | Cumulative Actual | 0% | 0% | 2.504% | 4.974% | 6.711% | 8.619% | 12.51% | 14.62% | 19.74% | 22.85% | 26.76% | 30.25% | 33.93% | 38.69% | 40.87% | 44.38% | 44.42%
[8 empty] | Month Forecast | 2025-05-01: 7.698%; 2025-06-01: 7.962%; 2025-07-01: 7.146%; 2025-08-01: 5.279%; 2025-09-01: 5.892%; 2025-10-01: 5.526%; 2025-11-01: 6.011%; 2025-12-01: 3.026%; 2026-01-01: 2.54%; 2026-02-01: 1.527%; 2026-03-01: 2.21%; 2026-04-01: 1.25%
[8 empty] | Cumulative Forecast | 2025-04-01: 44.38%; 2025-05-01: 52.08%; 2025-06-01: 60.04%; 2025-07-01: 67.19%; 2025-08-01: 72.47%; 2025-09-01: 78.36%; 2025-10-01: 83.89%; 2025-11-01: 89.9%; 2025-12-01: 92.92%; 2026-01-01: 95.46%; 2026-02-01: 96.99%; 2026-03-01: 99.2%; 2026-04-01: 100.5%
[8 empty] | backlog | 2024-01-01: 0%; 2024-02-01: 0%; 2025-05-01: 1.43%; 2025-06-01: 1.925%; 2025-07-01: 1.232%; 2025-08-01: 0.9276%; 2025-09-01: 3.06%; 2025-10-01: 2.045%; 2025-11-01: 2.659%; 2025-12-01: 3.026%; 2026-01-01: 2.54%; 2026-02-01: 1.527%; 2026-03-01: 2.21%; 2026-04-01: 1.25%
[25 empty] | 7.698% | 7.962% | 7.146% | 5.279% | 5.892% | 5.526% | 4.011% | 3.026% | 2.54% | 1.527% | 2.21% | 1.25%
[23 empty] | PLAN UP TO DATE |  | 74.11%
[23 empty] | Achive UP TO DATE |  | 44.42%
[9 empty] | 2025-05-01: 29.69%; 2026-01-01: Area; 2026-02-01: % Wtg.; 2026-03-01: Cum. Plan; 2026-04-01: Cum. Actual | Gap | Progress | Plan | Actual | Progress | Plan | Actual
[9 empty] | 2026-01-01: Engineering; 2026-02-01: 15%; 2026-03-01: 100%; 2026-04-01: 93.88% | 6.141% | Ordering | 99.99% | 75.7% | Ordering | 100% | 86% | -0.01% | -10.3%
[9 empty] | 2026-01-01: Ordering; 2026-02-01: 9.999%; 2026-03-01: 99.99%; 2026-04-01: 75.7% | 24.29% | Engineering | 100% | 93.88% | Engineering | 100% | 73% | 0.02% | 20.88%
[9 empty] | 2026-01-01: Deliveries; 2026-02-01: 25%; 2026-03-01: 86.94%; 2026-04-01: 45.48% | 41.46% | [6 empty] | 0% | 0%
[9 empty] | 2026-01-01: Construction; 2026-02-01: 43%; 2026-03-01: 44.77%; 2026-04-01: 22.86% | 21.9% | Delivery | 86.94% | 45.48% | Delivery | 77% | 36% | 9.936% | 9.48%
[9 empty] | 2026-01-01: Commissioning; 2026-02-01: 5%; 2026-03-01: 0%; 2026-04-01: 0% | 0% | [6 empty] | 0% | 0%
[9 empty] | 2026-01-01: Statutory Approval; 2026-02-01: 1.999%; 2026-03-01: 90%; 2026-04-01: 75% | 15% | Construction | 44.77% | 22.86% | Construction | 34% | 20% | 10.77% | 2.864%
[9 empty] | 2026-01-01: Total; 2026-02-01: 100%; 2026-03-01: 0%; 2026-04-01: 38.69% | -38.69% | Civil (Concrete) | 58.37% | 40.41% | Civil (Concrete) | 56% | 35% | 2.366% | 5.412%
[38 empty] | Fabrication PLATE | 62.36% | 17.98% | Fabrication PLATE | 59% | 14% | 3.358% | 3.975%
[44 empty] | 0% | 0%
[38 empty] | Erection | 12.26% | 5.838% | Erection | 11% | 4% | 1.259% | 1.838%
[38 empty] | E&I | 0% | 0% | E&I | 0% | 0% | 0% | 0%
[35 empty] | 2 | 100
[35 empty] | 1.5 | 75
[33 empty] | Area | Gap | Reasons | Mitigation Plan
[33 empty] | Engineering | 6.141%
[33 empty] | Ordering | 24.29%
[33 empty] | Deliveries | 41.46%
[33 empty] | Construction | 21.9%
[33 empty] | Commissioning | 0%
[33 empty] | Statutory Approval | 15%
[33 empty] | Total | -38.69%

## MARATHA QTY DISTRIBUATION
Type |  | Dept | Sec | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | Plan vs actual
Eng | Mechanical and Process | M & P |  | Month Plan | 2024-02-01: 23; 2024-03-01: 205; 2024-04-01: 76; 2024-05-01: 211; 2024-06-01: 107; 2024-07-01: 6; 2024-08-01: 31; 2024-09-01: 2; 2024-10-01: 303; 2024-11-01: 90; 2024-12-01: 16 |  | Plan | 100%
Eng |  | M & P |  | Cumm Plan | 2024-02-01: 23; 2024-03-01: 228; 2024-04-01: 304; 2024-05-01: 515; 2024-06-01: 622; 2024-07-01: 628; 2024-08-01: 659; 2024-09-01: 661; 2024-10-01: 964; 2024-11-01: 1054; 2024-12-01: 1070 | 1070 | Actual | 96.64%
Eng |  | M & P |  | Month Actual |  |  | 203 | 88 | 65 | 107 | 73 | 98 | 75 | 75 | 115 | 32 | 64 | 21 | 11 | 7
Eng |  | M & P |  | Cumm Actual |  |  | 203 | 291 | 356 | 463 | 536 | 634 | 709 | 784 | 899 | 931 | 995 | 1016 | 1027 | 1034 | 1034 | [6 empty] | 1034
Eng | E&I Engg. | E&I |  | Month Plan | 2024-05-01: 2; 2024-06-01: 18; 2024-07-01: 35; 2024-08-01: 35; 2024-09-01: 65; 2024-10-01: 65; 2024-11-01: 65; 2024-12-01: 60; 2025-01-01: 44; 2025-02-01: 20 |  | Plan | 100%
Eng |  | E&I |  | Cumm Plan | 2024-05-01: 2; 2024-06-01: 20; 2024-07-01: 55; 2024-08-01: 90; 2024-09-01: 155; 2024-10-01: 220; 2024-11-01: 285; 2024-12-01: 345; 2025-01-01: 389; 2025-02-01: 409; 2025-07-01: -237 | 409 | Actual | 84.35%
Eng |  | E&I |  | Month Actual | 2024-05-01: 2; 2024-06-01: 26; 2024-07-01: 0; 2024-08-01: 5; 2024-09-01: 20; 2024-10-01: 20; 2024-11-01: 10; 2024-12-01: 154; 2025-01-01: 1; 2025-02-01: 10; 2025-04-01: 97
Eng |  | E&I |  | Cumm Actual | 2024-05-01: 2; 2024-06-01: 28; 2024-07-01: 28; 2024-08-01: 33; 2024-09-01: 53; 2024-10-01: 73; 2024-11-01: 83; 2024-12-01: 237; 2025-01-01: 238; 2025-02-01: 248; 2025-03-01: 248; 2025-04-01: 345; 2025-05-01: 345 | 345
Eng |  | Civil | RCC | Month Plan | 2024-05-01: 12484; 2024-06-01: 12618; 2024-07-01: 8162; 2024-08-01: 3039; 2024-09-01: 11053; 2024-10-01: 11998; 2024-11-01: 11937; 2024-12-01: 7627; 2025-01-01: 4421; 2025-02-01: 3761 |  | Plan | 100%
Eng |  | Civil | RCC | Cumm Plan | 2024-05-01: 12484; 2024-06-01: 25102; 2024-07-01: 33264; 2024-08-01: 36303; 2024-09-01: 47356; 2024-10-01: 59354; 2024-11-01: 71291; 2024-12-01: 78918; 2025-01-01: 83339; 2025-02-01: 87100 | 87100 | Actual | 99.89%
Eng |  | Civil | RCC | Month Actual | 2024-03-01: 6453; 2024-04-01: 4234; 2024-05-01: 7016; 2024-06-01: 7119; 2024-07-01: 6541; 2024-08-01: 3785; 2024-09-01: 20760; 2024-10-01: 6423; 2024-11-01: 6740; 2024-12-01: 9763; 2025-01-01: 7060; 2025-02-01: 500; 2025-04-01: 606
Eng |  | Civil | RCC | Cumm Actual |  |  | 6453 | 10687 | 17703 | 24822 | 31363 | 35148 | 55908 | 62331 | 69071 | 78834 | 85894 | 86394 | 86394 | 87000 | 87000 | [6 empty] | 87000
Eng |  | Mech | Plate Fab | Month Plan | 2024-07-01: 540.6; 2024-08-01: 1341.71; 2024-09-01: 2846.09; 2024-10-01: 158.26; 2024-11-01: 71.56; 2024-12-01: 68.48; 2025-01-01: 46.9 |  | Plan | 100%
Eng |  | Mech | Plate Fab | Cumm Plan | 2024-07-01: 540.6; 2024-08-01: 1882.31; 2024-09-01: 4728.4; 2024-10-01: 4886.66; 2024-11-01: 4958.22; 2024-12-01: 5026.7; 2025-01-01: 5073.6 | 5073.6 | Actual | 88.44%
Eng |  | Mech | Plate Fab | Month Actual | 2024-07-01: 1969; 2024-09-01: 345; 2024-11-01: 1186; 2024-12-01: 862; 2025-01-01: 85; 2025-04-01: 40
Eng |  | Mech | Plate Fab | Cumm Actual | 2024-07-01: 1969; 2024-08-01: 1969; 2024-09-01: 2314; 2024-10-01: 2314; 2024-11-01: 3500; 2024-12-01: 4362; 2025-01-01: 4447; 2025-02-01: 4447; 2025-03-01: 4447; 2025-04-01: 4487; 2025-05-01: 4487 | 4487
Eng |  | Mech | Str Fab - GA | Month Plan | 2024-06-01: 154; 2024-07-01: 2473; 2024-08-01: 3911; 2024-09-01: 1753; 2024-10-01: 4439; 2024-11-01: 4456; 2024-12-01: 3719 |  | Plan | 100%
Eng |  | Mech | Str Fab - GA | Cumm Plan | 2024-06-01: 154; 2024-07-01: 2627; 2024-08-01: 6538; 2024-09-01: 8291; 2024-10-01: 12730; 2024-11-01: 17186; 2024-12-01: 20905 | 20905 | Actual | 98.44%
Eng |  | Mech | Str Fab - GA | Month Actual | 2024-07-01: 6566; 2024-08-01: 1090; 2024-09-01: 1350; 2024-10-01: 1200; 2024-11-01: 1140; 2024-12-01: 970; 2025-01-01: 3970; 2025-02-01: 4293
Eng |  | Mech | Str Fab - GA | Cumm Actual | 2024-07-01: 6566; 2024-08-01: 7656; 2024-09-01: 9006; 2024-10-01: 10206; 2024-11-01: 11346; 2024-12-01: 12316; 2025-01-01: 16286; 2025-02-01: 20579; 2025-03-01: 20579; 2025-04-01: 20579; 2025-05-01: 20579 | 20579 |  |  |  | EXCAVATION | 196956
Eng |  | Mech | Str Fab - Tekla | Month Plan | 2024-06-01: 124; 2024-07-01: 816; 2024-08-01: 4355; 2024-09-01: 84; 2024-10-01: 566; 2024-11-01: 6407; 2024-12-01: 3598 |  | Plan | 100%
Eng |  | Mech | Str Fab - Tekla | Cumm Plan | 2024-06-01: 124; 2024-07-01: 940; 2024-08-01: 5295; 2024-09-01: 5379; 2024-10-01: 5945; 2024-11-01: 12352; 2024-12-01: 15950 | 15950 | Actual | 88.82%
Eng |  | Mech | Str Fab - Tekla | Month Actual | 2024-08-01: 1090; 2024-09-01: 1023; 2024-10-01: 1200; 2024-11-01: 1140; 2024-12-01: 997; 2025-01-01: 1475; 2025-02-01: 2612; 2025-03-01: 4629
Eng |  | Mech | Str Fab - Tekla | Cumm Actual | 2024-08-01: 1090; 2024-09-01: 2113; 2024-10-01: 3313; 2024-11-01: 4453; 2024-12-01: 5450; 2025-01-01: 6925; 2025-02-01: 9537; 2025-03-01: 14166; 2025-04-01: 14166; 2025-05-01: 14166 | 14166
Const |  | Civil | Excavation | Month Plan | 2024-03-01: 12460; 2024-04-01: 18513.5; 2024-05-01: 6844.3; 2024-06-01: 2534.1; 2024-07-01: 1976.7; 2024-08-01: 6229.4; 2024-09-01: 12686.4486; 2024-10-01: 10217.3286; 2024-11-01: 21068.7586; 2024-12-01: 12683.1486; 2025-01-01: 28234.7752; 2025-02-01: 44878.8552; 2025-03-01: 14119.3852 |  | Plan | 100% |  |  |  |  | 58215.7 | -776.2093
Const |  | Civil | Excavation | Cumm Plan | 2024-03-01: 12460; 2024-04-01: 30973.5; 2024-05-01: 37817.8; 2024-06-01: 40351.9; 2024-07-01: 42328.6; 2024-08-01: 48558; 2024-09-01: 61244.4486; 2024-10-01: 71461.7771; 2024-11-01: 92530.5357; 2024-12-01: 105213.6843; 2025-01-01: 133448.4595; 2025-02-01: 178327.3148; 2025-03-01: 192446.7 | 192446.7 | Actual | 107.3% |  |  |  |  | -75
Const |  | Civil | Excavation | Month Actual |  |  | 15210 | 37239 | 25723 | 7749 | 1962 | 739 | 3370 | 6264 | 17126 | 18849 | 33285 | 12938 | 11993 | 14140 | [10 empty] | project start date | 2024-03-02
Const |  | Civil | Excavation | Cumm Actual |  |  | 15210 | 52449 | 78172 | 85921 | 87883 | 88622 | 91992 | 98256 | 115382 | 134231 | 167516 | 180454 | 192447 | 206587 | 206587 | [6 empty] | 206587 |  |  | current date | 2025-06-13
[16 empty] | 4627 | 8631 | 8114 | 0 |  | 2373
Const |  | Civil | RCC | Month Plan | [5 empty] | 716 | 3336 | 3730 | 3823 | 3638 | 4172 | 4627 | 8631 | 8648 | 9516 | 9162 | 8103 | 7693 | 5381 | 2821 | 1801 | 1302 |  |  | Plan | 58.37% | [5 empty] | # | Key Parameters (Actual/Plan/Scope) | Current Run-Rate / day | Shortfall (As per IBS) | Asking Run-Rate / day | Assumption (Asking Rate)
Const |  | Civil | RCC | Cumm Plan | [5 empty] | 716 | 4052 | 7782 | 11605 | 15243 | 19415 | 24042 | 32673 | 41321 | 50837 | 59999 | 68102 | 75795 | 81176 | 83997 | 85798 | 87100 |  | 87100 | Actual | 40.41% | start date | 2024-03-02 | end date | 2025-03-30 |  | 1 | Excavation + Area Grading (204214 /192447/267135m3) | Quantity exceeded
Const |  | Civil | RCC | Month Actual | 2024-05-01: 320; 2024-06-01: 721; 2024-07-01: 3136; 2024-08-01: 3707; 2024-09-01: 3549; 2024-10-01: 3905; 2024-11-01: 3189; 2024-12-01: 3239; 2025-01-01: 4254; 2025-02-01: 3294; 2025-03-01: 2911; 2025-04-01: 2749; 2025-05-01: 225 |  |  |  |  | 2024-06-01 |  | 2025-10-30 |  | 2 | PCC & RCC (34213/59999/87100m3) | 11.2838 | 25025 | 373.3885 | 5 (m3/Man/Month)
Const |  | Civil | RCC | Cumm Actual | 2024-05-01: 320; 2024-06-01: 1041; 2024-07-01: 4177; 2024-08-01: 7884; 2024-09-01: 11433; 2024-10-01: 15338; 2024-11-01: 18527; 2024-12-01: 21766; 2025-01-01: 26020; 2025-02-01: 29314; 2025-03-01: 32225; 2025-04-01: 34974; 2025-05-01: 35199 | 35199 |  |  |  | 2024-10-01 |  | 2025-07-30 |  | 3 | Plate fabrication (828/3849/5074 MT) | 0.92549 | 2936.94 | 88.5447 | 2 (MT/Man/Month)
[5 empty] | 2025-01-01: 715.668; 2025-02-01: 2446; 2025-03-01: 18612; 2025-04-01: 857; 2025-05-01: 761 |  |  |  |  | 2024-11-01 |  | 2025-10-30 |  | 5 | Mechanical & Str Erection (2293/9618/42410MT) | 9.567 | 7142 | 287.295 | 5 (MT/Man/Month)
Const |  | Mech | Plate Fab | Month Plan | 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 195.24; 2024-11-01: 244.05; 2024-12-01: 504.645; 2025-01-01: 715.668; 2025-02-01: 798.996; 2025-03-01: 705.18; 2025-04-01: 685.161; 2025-05-01: 594.271; 2025-06-01: 326.022; 2025-07-01: 304.367 |  | Plan | 62.36% |  | 2024-12-01 |  | 2025-10-30
Const |  | Mech | Plate Fab | Cumm Plan | 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 195.24; 2024-11-01: 439.29; 2024-12-01: 943.935; 2025-01-01: 1659.603; 2025-02-01: 2458.599; 2025-03-01: 3163.779; 2025-04-01: 3848.94; 2025-05-01: 4443.211; 2025-06-01: 4769.233; 2025-07-01: 5073.6 | 5073.6 | Actual | 17.98%
Const |  | Mech | Plate Fab | Month Actual | 2024-10-01: 35; 2024-11-01: 55; 2024-12-01: 75; 2025-01-01: 191; 2025-02-01: 236; 2025-03-01: 111; 2025-04-01: 183
Const |  | Mech | Plate Fab | Cumm Actual | 2024-10-01: 35; 2024-11-01: 90; 2024-12-01: 165; 2025-01-01: 382; 2025-02-01: 618; 2025-03-01: 729; 2025-04-01: 912; 2025-05-01: 912 | 912
[17 empty] | -3182% | 31700% | 2434.779 | 12 | 8400%
Const |  | Mech | Str Erec | Month Plan | [8 empty] | 0 | 0 | 0 | 0 | 363 | 999 | 1067 | 2541 | 3353 | 3495 | 3946 | 2983 | 1339 | 819 | 0 |  | Plan | 11.62%
Const |  | Mech | Str Erec | Cumm Plan | [8 empty] | 0 | 0 | 0 | 0 | 363 | 1362 | 2429 | 4970 | 8323 | 11818 | 15764 | 18747 | 20086 | 20905 | 20905 | 20905 | Actual | 2.966%
Const |  | Mech | Str Erec | Month Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 3; 2025-02-01: 348; 2025-03-01: 185; 2025-04-01: 84 | [6 empty] | 54875
Const |  | Mech | Str Erec | Cumm Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 351; 2025-03-01: 536; 2025-04-01: 620; 2025-05-01: 620 | 620
1893
Const |  | Mech | P&E Erec | Month Plan | 2024-12-01: 67; 2025-01-01: 378; 2025-02-01: 906; 2025-03-01: 1419; 2025-04-01: 1878; 2025-05-01: 2257; 2025-06-01: 3295; 2025-07-01: 3778; 2025-08-01: 3419; 2025-09-01: 2442; 2025-10-01: 1555; 2025-11-01: 111 |  | Plan | 12.88%
Const |  | Mech | P&E Erec | Cumm Plan | [7 empty] | 0 | 0 | 0 | 0 | 67 | 445 | 1351 | 2770 | 4648 | 6905 | 10200 | 13978 | 17397 | 19839 | 21394 | 21505 | 21505 | Actual | 8.631%
Const |  | Mech | P&E Erec | Month Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 272; 2025-01-01: 545; 2025-02-01: 455; 2025-03-01: 64; 2025-04-01: 520
Const |  | Mech | P&E Erec | Cumm Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 272; 2025-01-01: 817; 2025-02-01: 1272; 2025-03-01: 1336; 2025-04-01: 1856; 2025-05-01: 1856 | 1856
[5 empty] | 2025-02-01: -61; 2025-03-01: 41; 2025-05-01: 168 |  |  |  | 16431.4
Const |  | Process | Refractory | Month Plan | 2025-04-01: 495; 2025-05-01: 920; 2025-06-01: 1274; 2025-07-01: 1557; 2025-08-01: 1362; 2025-09-01: 1741; 2025-10-01: 1441; 2025-11-01: 145 |  | Plan | 0%
Const |  | Process | Refractory | Cumm Plan | 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 495; 2025-05-01: 1415; 2025-06-01: 2689; 2025-07-01: 4246; 2025-08-01: 5608; 2025-09-01: 7349; 2025-10-01: 8790; 2025-11-01: 8935 | 8935 | Actual | 0%
Const |  | Process | Refractory | Month Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0
Const |  | Process | Refractory | Cumm Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 0
67
Const |  | E&I | Cable Laying | Month Plan | 2025-05-01: 33; 2025-06-01: 98; 2025-07-01: 130; 2025-08-01: 163; 2025-09-01: 117; 2025-10-01: 85; 2025-11-01: 26.08 |  | Plan | 0%
Const |  | E&I | Cable Laying | Cumm Plan | 2025-05-01: 33; 2025-06-01: 131; 2025-07-01: 261; 2025-08-01: 424; 2025-09-01: 541; 2025-10-01: 626; 2025-11-01: 652.08 | 652.08 | Actual | 0%
Const |  | E&I | Cable Laying | Month Actual
Const |  | E&I | Cable Laying | Cumm Actual | 2024-12-01: 0; 2025-01-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 0
Const |  | E&I | Panels | Month Plan | 2025-05-01: 75; 2025-06-01: 95; 2025-07-01: 125; 2025-08-01: 115; 2025-09-01: 90 |  | Plan | 0%
Const |  | E&I | Panels | Cumm Plan | 2025-05-01: 75; 2025-06-01: 170; 2025-07-01: 295; 2025-08-01: 410; 2025-09-01: 500 | 500 | Actual | 0%
Const |  | E&I | Panels | Month Actual
Const |  | E&I | Panels | Cumm Actual | 2024-12-01: 0; 2025-01-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 0
Const |  | E&I | Balance | Month Plan | 2025-02-01: 0.01; 2025-03-01: 0.02; 2025-04-01: 0.03; 2025-05-01: 0.07; 2025-06-01: 11%; 2025-07-01: 17%; 2025-08-01: 17%; 2025-09-01: 19%; 2025-10-01: 16%; 2025-11-01: 7% |  | Plan | 3%
Const |  | E&I | Balance | Cumm Plan | 2025-02-01: 0.01; 2025-03-01: 0.03; 2025-04-01: 0.06; 2025-05-01: 0.13; 2025-06-01: 24%; 2025-07-01: 41%; 2025-08-01: 58%; 2025-09-01: 77%; 2025-10-01: 93%; 2025-11-01: 100% | 1 | Actual | 0%
Const |  | E&I | Balance | Month Actual
Const |  | E&I | Balance | Cumm Actual | 2024-12-01: 0; 2025-01-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 0
0
Const |  | E&I | BAL-NUMBER | Month Plan | 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 7.56; 2025-06-01: 21.23; 2025-07-01: 43.35; 2025-08-01: 47.26; 2025-09-01: 39.33; 2025-10-01: 13.6; 2025-11-01: 1.8256 |  | Plan | 0%
Const |  | E&I | BAL-NUMBER | Cumm Plan | 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 7.56; 2025-06-01: 28.79; 2025-07-01: 72.14; 2025-08-01: 119.4; 2025-09-01: 158.73; 2025-10-01: 172.33; 2025-11-01: 174.1556 | 174.1556 | Actual | 0%
Const |  | E&I | BAL-NUMBER | Month Actual
Const |  | E&I | BAL-NUMBER | Cumm Actual | 2024-12-01: 0; 2025-01-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 0
0
Const |  | E&I | Overall | Month Plan | 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 115.56; 2025-06-01: 214.23; 2025-07-01: 298.35; 2025-08-01: 325.26; 2025-09-01: 246.33; 2025-10-01: 98.6; 2025-11-01: 27.9056 |  | Plan | 0%
Const |  | E&I | Overall | Cumm Plan | 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 115.56; 2025-06-01: 329.79; 2025-07-01: 628.14; 2025-08-01: 953.4; 2025-09-01: 1199.73; 2025-10-01: 1298.33; 2025-11-01: 1326.2356 | 1326.2356 | Actual | 0%
Const |  | E&I | Overall | Month Actual | 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0
Const |  | E&I | Overall | Cumm Actual | 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0 | 0
0
Const. | OVER ALL | Mechanical | Erection | Month Plan | [7 empty] | 0 | 0 | 0 | 0 | 67 | 741 | 1905 | 2486 | 4419 | 5610 | 6790 | 7724 | 6402 | 3781 | 2374 | 111 |  | Plan | 12.26%
Const. | OVER ALL | Mechanical | Erection | Cumm Plan | [7 empty] | 0 | 0 | 0 | 0 | 67 | 808 | 2713 | 5199 | 9618 | 15228 | 22018 | 29742 | 36144 | 39925 | 42299 | 42410 | 42410 | Actual | 5.838%
Const. | OVER ALL | Mechanical | Erection | Month Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 275; 2025-01-01: 545; 2025-02-01: 803; 2025-03-01: 249; 2025-04-01: 604
Const. | OVER ALL | Mechanical | Erection | Cumm Actual | 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 275; 2025-01-01: 820; 2025-02-01: 1623; 2025-03-01: 1872; 2025-04-01: 2476; 2025-05-01: 2476 | 2476
T&C | Contractor Finalization | Cont | Contractor | Month Plan | 2024-07-01: 1; 2024-08-01: 1; 2024-09-01: 1; 2024-10-01: 1; 2024-12-01: 2 |  | Plan | 100%
T&C |  | Cont | Contractor | Cumm Plan | 2024-07-01: 1; 2024-08-01: 2; 2024-09-01: 3; 2024-10-01: 4; 2024-11-01: 4; 2024-12-01: 6 | 6 | Actual | 66.67%
T&C |  | Cont | Contractor | Month Actual | bar: 2024-06-01 to 2024-07-01; 2024-09-01; 2024-11-01
T&C |  | Cont | Contractor | Cumm Actual | 2024-06-01: 1; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 4; 2024-12-01: 4; 2025-01-01: 4; 2025-02-01: 4; 2025-03-01: 4; 2025-04-01: 4; 2025-05-01: 4 | 4
T&C | Mechanical Packages | Mech | Mechanical | Month Plan | 2024-03-01: 14; 2024-04-01: 9; 2024-05-01: 16; 2024-06-01: 13; 2024-07-01: 10; 2024-08-01: 8; 2024-09-01: 0; 2024-10-01: 1; 2024-11-01: 2; 2024-12-01: 1 |  | Plan | 100%
T&C |  | Mech | Mechanical | Cumm Plan | 2024-03-01: 14; 2024-04-01: 23; 2024-05-01: 39; 2024-06-01: 52; 2024-07-01: 62; 2024-08-01: 70; 2024-09-01: 70; 2024-10-01: 71; 2024-11-01: 73; 2024-12-01: 74 | 74 | Actual | 91.89%
T&C |  | Mech | Mechanical | Month Actual | 2024-03-01: 7; 2024-04-01: 21; 2024-05-01: 9; 2024-06-01: 6; 2024-07-01: 12; 2024-08-01: 5; 2024-09-01: 2; 2024-10-01: 1; 2024-11-01: 3; 2025-01-01: 1; 2025-03-01: 1
T&C |  | Mech | Mechanical | Cumm Actual |  |  | 7 | 28 | 37 | 43 | 55 | 60 | 62 | 63 | 66 | 66 | 67 | 67 | 68 | 68 | 68 | [6 empty] | 68
0
T&C | E & I Packages | E&I | E&I | Month Plan | 2024-03-01: 2; 2024-04-01: 4; 2024-05-01: 8; 2024-06-01: 12; 2024-07-01: 8; 2024-08-01: 10; 2024-09-01: 8; 2024-10-01: 2; 2024-11-01: 2 |  | Plan | 100%
T&C |  | E&I | E&I | Cumm Plan | 2024-03-01: 2; 2024-04-01: 6; 2024-05-01: 14; 2024-06-01: 26; 2024-07-01: 34; 2024-08-01: 44; 2024-09-01: 52; 2024-10-01: 54; 2024-11-01: 56 | 56 | Actual | 51.79% |  |  |  |  | 161 | 118 | 43
T&C |  | E&I | E&I | Month Actual | 2024-03-01: 1; 2024-04-01: 1; 2024-05-01: 2; 2024-07-01: 2; 2024-08-01: 3; 2024-09-01: 5; 2024-10-01: 4; 2024-11-01: 1; 2024-12-01: 2; 2025-01-01: 2; 2025-02-01: 3; 2025-03-01: 3 | [6 empty] | 15 | 146 | 98 | 48
T&C |  | E&I | E&I | Cumm Actual |  |  | 1 | 2 | 4 | 4 | 6 | 9 | 14 | 18 | 19 | 21 | 23 | 26 | 29 | 29 | 29 | [6 empty] | 29
[35 empty] | 56 | 23 | 33
T&C | Process Packages | Process | Process | Month Plan | 2024-09-01: 7; 2024-10-01: 3 | 0 | Plan | 100% |  |  |  |  | 58 | 26 | 32
T&C |  | Process | Process | Cumm Plan | 2024-09-01: 7; 2024-10-01: 10 | 10 | Actual | 40%
T&C |  | Process | Process | Month Actual | 2024-08-01: 3; 2024-10-01: 1 | [7 empty] | 74 | 67 | 7
T&C |  | Process | Process | Cumm Actual | 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 4; 2024-11-01: 4; 2024-12-01: 4; 2025-01-01: 4; 2025-02-01: 4; 2025-03-01: 4; 2025-04-01: 4; 2025-05-01: 4 | 4 | [6 empty] | 98 | 84 | 14
0
T&C |  | Overall | Overall | Month Plan | 2024-03-01: 16; 2024-04-01: 13; 2024-05-01: 24; 2024-06-01: 25; 2024-07-01: 19; 2024-08-01: 19; 2024-09-01: 16; 2024-10-01: 7; 2024-11-01: 4; 2024-12-01: 3 |  | Plan | 100%
T&C |  | Overall | Overall | Cumm Plan | 2024-03-01: 16; 2024-04-01: 29; 2024-05-01: 53; 2024-06-01: 78; 2024-07-01: 97; 2024-08-01: 116; 2024-09-01: 132; 2024-10-01: 139; 2024-11-01: 143; 2024-12-01: 146 | 146 | Actual | 71.92%
T&C |  | Overall | Overall | Month Actual | 2024-03-01: 8; 2024-04-01: 22; 2024-05-01: 11; 2024-06-01: 7; 2024-07-01: 15; 2024-08-01: 11; 2024-09-01: 8; 2024-10-01: 6; 2024-11-01: 5; 2024-12-01: 2; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 4
T&C |  | Overall | Overall | Cumm Actual |  |  | 8 | 30 | 41 | 48 | 63 | 74 | 82 | 88 | 93 | 95 | 98 | 101 | 105 | 105 | 105 | [6 empty] | 105
Delivery |  | TOR + STL | TOR + STEEL | Month Plan |  |  |  |  | 534 | 492 | 504 | 974 | 1431 | 1849 | 2443 | 2138 | 1728 | 1404 | 1069 | 1015 | 1082 | 409 | [6 empty] | Plan | 85.32% |  | 0
Delivery |  | TOR + STL | TOR + STEEL | Cumm Plan |  |  |  |  | 534 | 1026 | 1530 | 2504 | 3935 | 5784 | 8227 | 10365 | 12093 | 13497 | 14566 | 15581 | 16663 | 17072 | [5 empty] | 17072 | Actual | 70.18%
Delivery |  | TOR + STL | TOR + STEEL | Month Actual | 2024-04-01: 68; 2024-05-01: 234; 2024-06-01: 210; 2024-07-01: 1054; 2024-08-01: 613; 2024-09-01: 373; 2024-10-01: 1274; 2024-11-01: 1213; 2024-12-01: 413; 2025-01-01: 879; 2025-02-01: 1300; 2025-03-01: 2839; 2025-04-01: 453
Delivery |  | TOR + STL | TOR + STEEL | Cumm Actual |  |  |  | 68 | 302 | 512 | 1566 | 2179 | 2552 | 3826 | 5039 | 5452 | 6331 | 8689 | 11528 | 11981 | 11981 | [6 empty] | 11981 |  |  |  | 0
0%
Delivery |  | Workshop + SF | Str Fab | Month Plan | 2024-08-01: 40; 2024-09-01: 80; 2024-10-01: 1509; 2024-11-01: 1344; 2024-12-01: 343; 2025-01-01: 695; 2025-02-01: 1382; 2025-03-01: 2331; 2025-04-01: 3647; 2025-05-01: 4842; 2025-06-01: 3001; 2025-07-01: 1691 |  | Plan | 36.95%
Delivery |  | Workshop + SF | Str Fab | Cumm Plan | 2024-08-01: 40; 2024-09-01: 120; 2024-10-01: 1629; 2024-11-01: 2973; 2024-12-01: 3316; 2025-01-01: 4011; 2025-02-01: 5393; 2025-03-01: 7724; 2025-04-01: 11371; 2025-05-01: 16213; 2025-06-01: 19214; 2025-07-01: 20905 | 20905 | Actual | 29.7%
Delivery |  | Workshop + SF | Str Fab | Month Actual | 2024-11-01: 457; 2024-12-01: 621; 2025-01-01: 1134; 2025-02-01: 1490; 2025-03-01: 509; 2025-04-01: 1998 |  |  |  |  | 672
Delivery |  | Workshop + SF | Str Fab | Cumm Actual | 2024-11-01: 457; 2024-12-01: 1078; 2025-01-01: 2212; 2025-02-01: 3702; 2025-03-01: 4211; 2025-04-01: 6209; 2025-05-01: 6209 | 6209
[5 empty] | 2025-01-01: 32300%; 2025-03-01: -6100%; 2025-05-01: 190200% |  |  |  |  | 3971 | -240
Delivery |  | Mech (EQ) | Package | Month Plan | 2024-09-01: 164; 2024-10-01: 328; 2024-11-01: 985; 2024-12-01: 1643; 2025-01-01: 3121; 2025-02-01: 3450; 2025-03-01: 2136; 2025-04-01: 1643; 2025-05-01: 1314; 2025-06-01: 985; 2025-07-01: 662 |  | Plan | 71.98%
Delivery |  | Mech (EQ) | Package | Cumm Plan | 2024-09-01: 164; 2024-10-01: 492; 2024-11-01: 1477; 2024-12-01: 3120; 2025-01-01: 6241; 2025-02-01: 9691; 2025-03-01: 11827; 2025-04-01: 13470; 2025-05-01: 14784; 2025-06-01: 15769; 2025-07-01: 16431 | 16431 | Actual | 57.3%
Delivery |  | Mech (EQ) | Package | Month Actual | 2024-11-01: 420; 2024-12-01: 1124; 2025-01-01: 1665; 2025-02-01: 881; 2025-03-01: 665; 2025-04-01: 2705
Delivery |  | Mech (EQ) | Package | Cumm Actual | 2024-11-01: 420; 2024-12-01: 1544; 2025-01-01: 3209; 2025-02-01: 6045; 2025-03-01: 6710; 2025-04-01: 9415; 2025-05-01: 9415 | 9415 |  |  | 16482 | 4788
[19 empty] | 0 |  | 1285
Delivery |  | E&I | Package | Month Plan | 2024-11-01: 2; 2024-12-01: 1; 2025-01-01: 7; 2025-02-01: 9; 2025-03-01: 10; 2025-04-01: 8; 2025-05-01: 8; 2025-06-01: 6; 2025-07-01: 3 |  | Plan | 53.7% |  | 29.05%
Delivery |  | E&I | Package | Cumm Plan | 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 10; 2025-02-01: 19; 2025-03-01: 29; 2025-04-01: 37; 2025-05-01: 45; 2025-06-01: 51; 2025-07-01: 54 | 54 | Actual | 7.407% |  | 9.38%
Delivery |  | E&I | Package | Month Actual | bar: 2024-10-01 to 2024-11-01; 2025-03-01 to 2025-04-01
Delivery |  | E&I | Package | Cumm Actual | 2024-10-01: 1; 2024-11-01: 2; 2024-12-01: 2; 2025-01-01: 2; 2025-02-01: 2; 2025-03-01: 3; 2025-04-01: 4; 2025-05-01: 4 | 4
Delivery |  | Process | Package | Month Plan | 2025-02-01: 2; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 1; 2025-06-01: 1 |  | Plan | 50% |  | #DIV/0!
Delivery |  | Process | Package | Cumm Plan | 2025-02-01: 2; 2025-03-01: 5; 2025-04-01: 8; 2025-05-01: 9; 2025-06-01: 10 | 10 | Actual | 0% |  | #DIV/0!
Delivery |  | Process | Package | Month Actual
Delivery |  | Process | Package | Cumm Actual | 2025-04-01: 0; 2025-05-01: 0 | 0
Manuf |  | STUCTURE | Package | Month Plan |  |  | 0 | 0 | 0 | 40 | 80 | 1509 | 1344 | 343 | 695 | 1382 | 2331 | 3647 | 4842 | 3001 | 1691 | [7 empty] | Plan | 77.56%
Manuf |  | Mech | Package | Cumm Plan |  |  | 0 | 0 |  | 40 | 120 | 1629 | 2973 | 3316 | 4011 | 5393 | 7724 | 11371 | 16213 | 19214 | 20905 | [6 empty] | 20905 | Actual | 59.68%
Manuf |  | Mech | Package | Month Actual |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 621 | 1134 | 1490 | 2977 | 5798 | 0 | 0 | 0
Manuf |  | Mech | Package | Cumm Actual |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 1078 | 2212 | 3702 | 6679 | 12477 | 12477 | 0 | 0 |  |  | 1535 |  | 12477
191
Manuf |  | Mech | Package | Month Plan | 2024-08-01: 6; 2024-09-01: 10; 2024-10-01: 13; 2024-11-01: 15; 2024-12-01: 10; 2025-01-01: 10; 2025-02-01: 5; 2025-03-01: 1; 2025-04-01: 1; 2025-05-01: 1 |  | Plan | 97.22%
Manuf |  | Mech | Package | Cumm Plan | 2024-08-01: 6; 2024-09-01: 16; 2024-10-01: 29; 2024-11-01: 44; 2024-12-01: 54; 2025-01-01: 64; 2025-02-01: 69; 2025-03-01: 70; 2025-04-01: 71; 2025-05-01: 72 | 72 | Actual | 66.67%
Manuf |  | Mech | Package | Month Actual | 2024-07-01: 1; 2024-08-01: 1; 2024-09-01: 18; 2024-10-01: 10; 2024-11-01: 6; 2025-02-01: 12
Manuf |  | Mech | Package | Cumm Actual | 2024-07-01: 1; 2024-08-01: 2; 2024-09-01: 20; 2024-10-01: 30; 2024-11-01: 36; 2024-12-01: 36; 2025-01-01: 36; 2025-02-01: 48; 2025-03-01: 48; 2025-04-01: 48; 2025-05-01: 48 | 48
65 | bar: 2025-03-01
Manuf |  | E&I | Package | Month Plan | 2024-09-01: 5; 2024-10-01: 7; 2024-11-01: 8; 2024-12-01: 11; 2025-01-01: 9; 2025-02-01: 6; 2025-03-01: 4; 2025-04-01: 3; 2025-05-01: 1 |  | Plan | 92.59%
Manuf |  | E&I | Package | Cumm Plan | 2024-09-01: 5; 2024-10-01: 12; 2024-11-01: 20; 2024-12-01: 31; 2025-01-01: 40; 2025-02-01: 46; 2025-03-01: 50; 2025-04-01: 53; 2025-05-01: 54 | 54 | Actual | 24.07%
Manuf |  | E&I | Package | Month Actual | 2024-09-01: 2; 2024-11-01: 3; 2025-02-01: 6; 2025-04-01: 2
Manuf |  | E&I | Package | Cumm Actual | 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 5; 2024-12-01: 5; 2025-01-01: 5; 2025-02-01: 11; 2025-03-01: 11; 2025-04-01: 13; 2025-05-01: 13 | 13
[17 empty] | 0.27459 | 1492 | 0.14519
#DIV/0!

## SUMMARY
S No | Description | Cum | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01
| Tendering and Contracting | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.5% | 0.5% | 0.5% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0.9458% | 0.608% | 1.081% | 0.8782% | 0.6755% | 0.5404% | 0% | 0.06755% | 0.1351% | 0.06755% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0.05357% | 0.1071% | 0.2143% | 0.3214% | 0.2143% | 0.2679% | 0.2143% | 0.05357% | 0.05357% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.35% | 0.15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Plan |  | 0% | 0% | 0.9993% | 0.7151% | 1.295% | 1.2% | 1.39% | 1.308% | 1.064% | 0.7711% | 0.1887% | 1.068% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.5% | 0% | 0.5% | 0% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0.4729% | 1.419% | 0.608% | 0.4053% | 0.8106% | 0.3378% | 0.1351% | 0.06755% | 0.2027% | 0% | 0.06755% | 0% | 0.06755% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0.02679% | 0.02679% | 0.05357% | 0% | 0.05357% | 0.08036% | 0.1339% | 0.1071% | 0.02679% | 0.05357% | 0.05357% | 0.08036% | 0.08036% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tendering and Contracting |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.15% | 0% | 0.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual |  | 0% | 0% | 0.4997% | 1.445% | 0.6616% | 0.9053% | 1.364% | 0.5681% | 0.769% | 0.2247% | 0.7294% | 0.05357% | 0.1211% | 0.08036% | 0.1479% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1 | Tendering and Contracting | 4 | [15 empty] | 0
| Month Plan | 99.99% | 0% | 0% | 9.993% | 7.151% | 12.95% | 12% | 13.9% | 13.08% | 10.64% | 7.711% | 1.887% | 10.68% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual | 75.7% | 0% | 0% | 4.997% | 14.45% | 6.616% | 9.053% | 13.64% | 5.681% | 7.69% | 2.247% | 7.294% | 0.5357% | 1.211% | 0.8036% | 1.479% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Slippage | 24.29% | 0% | 0% | 4.997% | -7.303% | 6.336% | 2.943% | 0.2561% | 7.402% | 2.952% | 5.464% | -5.408% | 10.14% | -1.211% | -0.8036% | -1.479% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Forecast | 74% | -1.705% | [15 empty] | 1.286% | 1.286% | 2.285%
| Engineering | 15% | 0% | 0.07523% | 0.6706% | 0.2486% | 0.6902% | 0.35% | 0.01963% | 0.1014% | 0.006542% | 0.9911% | 0.2944% | 0.05234% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.1064% | 0.2642% | 0.5604% | 0.03116% | 0.01409% | 0.01348% | 0.009235% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0.4301% | 0.4347% | 0.2812% | 0.1047% | 0.3808% | 0.4134% | 0.4113% | 0.2628% | 0.1523% | 0.1296% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0.0221% | 0.3549% | 0.5613% | 0.2516% | 0.637% | 0.6395% | 0.5337% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0.01167% | 0.07679% | 0.4098% | 0.007905% | 0.05326% | 0.6029% | 0.3386% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0.01468% | 0.1321% | 0.2569% | 0.2569% | 0.4771% | 0.4771% | 0.4771% | 0.4404% | 0.323% | 0.1468% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Plan |  | 0% | 0.07523% | 0.6706% | 0.2486% | 1.135% | 0.9506% | 1.096% | 1.698% | 1.684% | 2.603% | 2.439% | 1.641% | 0.4845% | 0.2764% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0.664% | 0.2879% | 0.2126% | 0.35% | 0.2388% | 0.3206% | 0.2453% | 0.2453% | 0.3762% | 0.1047% | 0.2093% | 0.06869% | 0.03598% | 0.0229% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.3877% | 0% | 0.06793% | 0% | 0.2335% | 0.1697% | 0.01674% | 0% | 0% | 0.007876% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0.2223% | 0.1459% | 0.2417% | 0.2453% | 0.2254% | 0.1304% | 0.7153% | 0.2213% | 0.2322% | 0.3364% | 0.2432% | 0.01723% | 0% | 0.02088% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.9423% | 0.1564% | 0.1937% | 0.1722% | 0.1636% | 0.1392% | 0.5697% | 0.6161% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1026% | 0.09627% | 0.1129% | 0.1073% | 0.09382% | 0.1388% | 0.2458% | 0.4356% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Engineering |  | 0% | 0% | 0% | 0% | 0.01468% | 0.1908% | 0% | 0.0367% | 0.1468% | 0.1468% | 0.0734% | 1.13% | 0.00734% | 0.0734% | 0% | 0.712% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual | 7 | 0% | 0% | 0.8864% | 0.4337% | 0.469% | 0.7861% | 1.794% | 0.7467% | 1.465% | 0.8986% | 1.186% | 1.974% | 1.185% | 1.021% | 0.4716% | 0.7636% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | Engineering | 4 | [15 empty] | 0
| Month Plan | 100% | 0% | 0.5016% | 4.47% | 1.657% | 7.567% | 6.338% | 7.306% | 11.32% | 11.23% | 17.35% | 16.26% | 10.94% | 3.23% | 1.843% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual | 93.88% | 0% | 0% | 5.909% | 2.892% | 3.127% | 5.241% | 11.96% | 4.978% | 9.769% | 5.99% | 7.908% | 13.16% | 7.901% | 6.808% | 3.144% | 5.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Slippage | 6.141% | 0% | 0.5016% | -1.439% | -1.234% | 4.44% | 1.097% | -4.655% | 6.344% | 1.46% | 11.36% | 8.354% | -2.219% | -4.671% | -4.965% | -3.144% | -5.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Forecast | 71% | -22.88% | [15 empty] | 0.4465% | 0.2679% | 0.1786%
| Construction | 43% | 0% | 0% | 0.1295% | 0.1924% | 0.07113% | 0.02634% | 0.02054% | 0.06474% | 0.1318% | 0.1062% | 0.219% | 0.1318% | 0.2934% | 0.4664% | 0.1467% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0.1233% | 0.5746% | 0.6424% | 0.6584% | 0.6266% | 0.7185% | 0.7969% | 1.486% | 1.489% | 1.639% | 1.578% | 1.396% | 1.325% | 0.9268% | 0.4859% | 0.3102% | 0.2242% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1539% | 0.1924% | 0.3979% | 0.5642% | 0.6299% | 0.556% | 0.5402% | 0.4685% | 0.257% | 0.24% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1216% | 0.3346% | 0.3573% | 0.851% | 1.123% | 1.17% | 1.321% | 0.999% | 0.4484% | 0.2743% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03116% | 0.1758% | 0.4213% | 0.6599% | 0.8734% | 1.05% | 1.532% | 1.757% | 1.59% | 1.136% | 0.7232% | 0.05162%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3485% | 0.6461% | 0.8998% | 0.981% | 0.7429% | 0.2974% | 0.08416%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0554% | 0.103% | 0.1426% | 0.1743% | 0.1524% | 0.1949% | 0.1613% | 0.01623%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Plan |  | 0% | 0% | 0.1295% | 0.1924% | 0.07113% | 0.1497% | 0.5951% | 0.7071% | 0.7903% | 0.8867% | 1.13% | 1.358% | 2.642% | 3.342% | 3.359% | 3.898% | 4.488% | 5.074% | 5.319% | 4.208% | 2.832% | 1.68% | 0.152%
| Construction |  | 0% | 0% | 0.1581% | 0.387% | 0.2673% | 0.08053% | 0.02039% | 0.00768% | 0.03502% | 0.0651% | 0.178% | 0.1959% | 0.3459% | 0.1345% | 0.1246% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0.05511% | 0.1242% | 0.5401% | 0.6384% | 0.6112% | 0.6725% | 0.5492% | 0.5578% | 0.7327% | 0.5673% | 0.5014% | 0.4735% | 0.03875% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02759% | 0.04336% | 0.05913% | 0.1506% | 0.1861% | 0.08751% | 0.1443% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.001005% | 0% | 0.1165% | 0.06196% | 0.02813% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1265% | 0.2535% | 0.2116% | 0.02976% | 0.2418% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual |  | 0% | 0% | 0.1581% | 0.387% | 0.3224% | 0.2047% | 0.5605% | 0.6461% | 0.6463% | 0.7652% | 0.7706% | 0.9404% | 1.483% | 1.216% | 0.8052% | 0.8877% | 0.03875% | 0% | 0% | 0% | 0% | 0% | 0%
3 | Construction | 4 | [15 empty] | 9.0648
| Month Plan | 44.77% | 0% | 0% | 0.3011% | 0.4474% | 0.1654% | 0.348% | 1.384% | 1.645% | 1.838% | 2.062% | 2.628% | 3.157% | 6.143% | 7.771% | 7.811% | 9.065% | 10.44% | 11.8% | 12.37% | 9.787% | 6.586% | 3.908% | 0.3535%
| Month Actual | 22.86% | 0% | 0% | 0.3676% | 0.9% | 0.7499% | 0.4761% | 1.303% | 1.503% | 1.503% | 1.78% | 1.792% | 2.187% | 3.448% | 2.828% | 1.873% | 2.064% | 0.09012% | 0% | 0% | 0% | 0% | 0% | 0%
| Slippage | 32.34% | 0% | 0% | -0.06646% | -0.4526% | -0.5844% | -0.128% | 0.08046% | 0.1419% | 0.3349% | 0.2824% | 0.8356% | 0.9706% | 2.695% | 4.943% | 5.939% | 7% | 10.35% | 11.8% | 12.37% | 9.787% | 6.586% | 3.908% | 0.3535%
| Forecast | 15% | -7.864% | [15 empty] | 4.036% | 4.239% | 4.571% | 4.825% | 3.953% | 4.072% | 3.042% | 2.057% | 1.82% | 0.3766% | 0.06% | 0.1%
| Delivery | 25% | 0% | 0% | 0% | 0% | 0% | 0.001913% | 0.003827% | 0.07218% | 0.06429% | 0.01641% | 0.03325% | 0.06611% | 0.1115% | 0.1745% | 0.2316% | 0.1436% | 0.08089% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0.001913% | 0.003827% | 0.07218% | 0.06429% | 0.01641% | 0.03325% | 0.06611% | 0.1115% | 0.1745% | 0.2316% | 0.1436% | 0.08089% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.003827% | 0.007654% | 0.1444% | 0.1286% | 0.03282% | 0.06649% | 0.1322% | 0.223% | 0.3489% | 0.4632% | 0.2871% | 0.1618% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5% | 0.8333% | 1.083% | 1.25% | 0.8333% | 0.8333% | 0.4167% | 0.08333% | 0.08333% | 0.08333% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1667% | 0.2778% | 0.3611% | 0.4167% | 0.2778% | 0.2778% | 0.1389% | 0.02778% | 0.02778% | 0.02778% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0549% | 0.1098% | 0.3297% | 0.55% | 1.045% | 1.155% | 0.715% | 0.55% | 0.4398% | 0.3297% | 0.2216% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2778% | 0.3889% | 0.4444% | 0.6111% | 0.5% | 0.3333% | 0.2222% | 0.1667% | 0.05556% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.09269% | 0.1298% | 0.1483% | 0.2039% | 0.1668% | 0.1112% | 0.07415% | 0.05561% | 0.01854% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.07404% | 0.03702% | 0.2591% | 0.3332% | 0.3702% | 0.2961% | 0.2961% | 0.2221% | 0.1111% | 0% | 0% | 0% | 0%
|  |  | 0% | 0% | 0% | 0% | 0.03131% | 0.02885% | 0.02955% | 0.05711% | 0.08391% | 0.1084% | 0.1432% | 0.1254% | 0.1013% | 0.08232% | 0.06268% | 0.05951% | 0.06344% | 0.02398% | 0% | 0% | 0% | 0% | 0%
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1% | 0.1% | 0.1% | 0.1% | 0.1% | 0% | 0% | 0% | 0%
| Month Plan |  | 0% | 0% | 0% | 0% | 0.03131% | 0.03267% | 0.03721% | 0.872% | 1.757% | 2.358% | 3.001% | 2.804% | 3.473% | 3.052% | 2.342% | 1.975% | 1.71% | 0.9629% | 0.5944% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02186% | 0.02971% | 0.05425% | 0.07127% | 0.1424% | 0.2773% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02186% | 0.02971% | 0.05425% | 0.07127% | 0.1424% | 0.2773% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04372% | 0.05941% | 0.1085% | 0.1425% | 0.0487% | 0.1912% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.08333% | 0.08333% | 1.5% | 0.8333% | 0.5% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.02778% | 0.02778% | 0.5% | 0.2778% | 0.1667% | 0% | 0% | 0.3333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1406% | 0.3762% | 0.5573% | 0.2949% | 0.2226% | 0.9055% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1111% | 0% | 0.1667% | 0% | 0% | 0.3333% | 0% | 0.1111% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03707% | 0% | 0.05561% | 0% | 0% | 0.1112% | 0% | 0.03707% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Delivery |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.03702% | 0.03702% | 0% | 0% | 0% | 0.03702% | 0.03702% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | 0% | 0% | 0% | 0.003987% | 0.01372% | 0.01231% | 0.0618% | 0.03594% | 0.02187% | 0.0747% | 0.07112% | 0.02422% | 0.05154% | 0.07622% | 0.1665% | 0.02656% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Month Actual |  | 0% | 0% | 0% | 0.003987% | 0.01372% | 0.01231% | 0.1729% | 0.1471% | 2.17% | 1.223% | 1.225% | 0.5193% | 0.8259% | 2.434% | 0.7596% | 1.863% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Delivery | 4 | [15 empty] | 7.9001
| Month Plan | 86.94% | 0% | 0% | 0% | 0% | 0.1252% | 0.1307% | 0.1488% | 3.488% | 7.026% | 9.434% | 12.01% | 11.21% | 13.89% | 12.21% | 9.366% | 7.9% | 6.839% | 3.852% | 2.378% | 0% | 0% | 0% | 0%
| Month Actual | 45.48% | 0% | 0% | 0% | 0.01595% | 0.05488% | 0.04925% | 0.6916% | 0.5882% | 8.68% | 4.891% | 4.9% | 2.077% | 3.303% | 9.736% | 3.038% | 7.452% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Slippage | 48.3% | 0% | 0% | 0% | -0.01595% | 0.07036% | 0.08145% | -0.5428% | 2.9% | -1.654% | 4.543% | 7.105% | 9.137% | 10.59% | 2.47% | 6.328% | 0.4479% | 6.839% | 3.852% | 2.378% | 0% | 0% | 0% | 0%
| Forecast | 25% | -20.48% | [15 empty] | 2.93% | 2.169% | 2.111% | 1.454% | 1.939% | 1.454% | 0.9693% | 0.9693% | 0.9693%
| Commissioning | 5% | [17 empty] | 0.4% | 0.8% | 0.6% | 0.2%
| Commissioning | [19 empty] | 0.35% | 0.35% | 0.3%
| Commissioning | [21 empty] | 1%
| Commissioning | [21 empty] | 1%
| Month Plan |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4% | 1.15% | 0.95% | 2.5%
Commissioning
Commissioning
Commissioning
Commissioning
| Month Actual |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | Commissioning
| Month Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 23% | 19% | 50%
| Month Actual | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Slippage | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Forecast | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 2.15% | 2.15% | 2.15%
| T&C | 75.7% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.286% | 1.286% | 2.285% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.44%
| Engineering | 93.88% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4465% | 0.2679% | 0.1786% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.228%
| Delivery | 45.48% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.93% | 2.169% | 2.111% | 1.454% | 1.939% | 1.454% | 0.9693% | 0.9693% | 0.9693% | 0% | 0% | 0% | 41.49%
| Construction | 22.86% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.036% | 4.239% | 4.571% | 4.825% | 3.953% | 4.072% | 3.042% | 2.057% | 1.82% | 0.3766% | 0.06% | 0.1% | 48.4%
| Others | [29 empty] | 100%
| Commissioning | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 2.15% | 2.15% | 2.15% | 100%
| Total |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.698% | 7.962% | 9.146% | 6.279% | 5.892% | 5.526% | 4.011% | 3.026% | 3.54% | 2.527% | 2.21% | 2.25% | 52.49%
ORD | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-02 | 2026-01-02 | 2026-02-02
| Month Plan | 0% | 0% | 9.993% | 7.151% | 12.95% | 12% | 13.9% | 13.08% | 10.64% | 7.711% | 1.887% | 10.68% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan | 0% | 0% | 9.993% | 17.14% | 30.1% | 42.09% | 55.99% | 69.07% | 79.72% | 87.43% | 89.31% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99% | 99.99%
| Month Actual | 0% | 0% | 4.997% | 14.45% | 6.616% | 9.053% | 13.64% | 5.681% | 7.69% | 2.247% | 7.294% | 0.5357% | 1.211% | 0.8036% | 1.479% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Actual | 0% | 0% | 4.997% | 19.45% | 26.07% | 35.12% | 48.76% | 54.44% | 62.13% | 64.38% | 71.67% | 72.21% | 73.42% | 74.23% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7% | 75.7%
| Month Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.286% | 1.286% | 2.285% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.286% | 2.571% | 4.857% | 4.857% | 4.857% | 4.857% | 4.857% | 4.857% | 4.857% | 4.857%
ENGG | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-02 | 2026-01-02 | 2026-02-02
| Month Plan | 0% | 0.5016% | 4.47% | 1.657% | 7.567% | 6.338% | 7.306% | 11.32% | 11.23% | 17.35% | 16.26% | 10.94% | 3.23% | 1.843% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan | 0% | 0.5016% | 4.972% | 6.629% | 14.2% | 20.53% | 27.84% | 39.16% | 50.39% | 67.74% | 84.01% | 94.95% | 98.18% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Month Actual | 0% | 0% | 5.909% | 2.892% | 3.127% | 5.241% | 11.96% | 4.978% | 9.769% | 5.99% | 7.908% | 13.16% | 7.901% | 6.808% | 3.144% | 5.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Actual | 0% | 0% | 5.909% | 8.801% | 11.93% | 17.17% | 29.13% | 34.11% | 43.88% | 49.87% | 57.77% | 70.94% | 78.84% | 85.64% | 88.79% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88% | 93.88%
| Month Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4465% | 0.2679% | 0.1786% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4465% | 0.7144% | 0.893% | 0.893% | 0.893% | 0.893% | 0.893% | 0.893% | 0.893% | 0.893%
DEL | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-02 | 2026-01-02 | 2026-02-02 | 2026-03-05 | 2026-04-05
| Month Plan | 0% | 0% | 0% | 0% | 0.1252% | 0.1307% | 0.1488% | 3.488% | 7.026% | 9.434% | 12.01% | 11.21% | 13.89% | 12.21% | 9.366% | 7.9% | 6.839% | 3.852% | 2.378% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan | 0% | 0% | 0% | 0% | 0.1252% | 0.2559% | 0.4048% | 3.893% | 10.92% | 20.35% | 32.36% | 43.57% | 57.46% | 69.67% | 79.04% | 86.94% | 93.77% | 97.63% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Month Actual | 0% | 0% | 0% | 0.01595% | 0.05488% | 0.04925% | 0.6916% | 0.5882% | 8.68% | 4.891% | 4.9% | 2.077% | 3.303% | 9.736% | 3.038% | 7.452% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Actual | 0% | 0% | 0% | 0.01595% | 0.07083% | 0.1201% | 0.8117% | 1.4% | 10.08% | 14.97% | 19.87% | 21.95% | 25.25% | 34.99% | 38.03% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48% | 45.48%
| Month Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.93% | 2.169% | 2.111% | 1.454% | 1.939% | 1.454% | 0.9693% | 0.9693% | 0.9693% | 0% | 0% | 0%
| Cumulative Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.93% | 5.1% | 7.211% | 8.665% | 10.6% | 12.06% | 13.03% | 14% | 14.96% | 14.96% | 14.96% | 14.96%
CON | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-02 | 2026-01-02 | 2026-02-02 | 2026-03-05 | 2026-04-05
| Month Plan | 0% | 0% | 0.3011% | 0.4474% | 0.1654% | 0.348% | 1.384% | 1.645% | 1.838% | 2.062% | 2.628% | 3.157% | 6.143% | 7.771% | 7.811% | 9.065% | 10.44% | 11.8% | 12.37% | 9.787% | 6.586% | 3.908% | 0.3535% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan | 0% | 0% | 0.3011% | 0.7486% | 0.914% | 1.262% | 2.646% | 4.29% | 6.128% | 8.19% | 10.82% | 13.98% | 20.12% | 27.89% | 35.7% | 44.77% | 55.2% | 67% | 79.37% | 89.16% | 95.75% | 99.65% | 100% | 100% | 100% | 100% | 100% | 100%
| Month Actual | 0% | 0% | 0.3676% | 0.9% | 0.7499% | 0.4761% | 1.303% | 1.503% | 1.503% | 1.78% | 1.792% | 2.187% | 3.448% | 2.828% | 1.873% | 2.064% | 0.09012% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Actual | 0% | 0% | 0.3676% | 1.268% | 2.017% | 2.494% | 3.797% | 5.3% | 6.803% | 8.582% | 10.37% | 12.56% | 16.01% | 18.84% | 20.71% | 22.77% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86% | 22.86%
| Month Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.036% | 4.239% | 4.571% | 4.825% | 3.953% | 4.072% | 3.042% | 2.057% | 1.82% | 0.3766% | 0.06% | 0.1%
| Cumulative Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.036% | 8.275% | 12.85% | 17.67% | 21.62% | 25.7% | 28.74% | 30.79% | 32.61% | 32.99% | 33.05% | 33.15%
Commissioning | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-02 | 2026-01-02 | 2026-02-02 | 2026-03-05 | 2026-04-05
| Month Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 23% | 19% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 31% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Month Actual | bar: 2024-01-01 to 2026-04-05
Cumulative Actual | bar: 2024-01-01 to 2026-04-05
| Month Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 2.15% | 2.15% | 2.15%
| Cumulative Forecast | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.75% | 2.9% | 5.05% | 7.2%

## P6 Format
Description | Activity ID | Activity Name | BL Duration | BL Start | BL Finish | Original Duration | AL Start | AL Finish | Start | Expected Finish
|  | Maratha Clinkerization Unit Expansion Project | 631 | 2024-03-02 | 2025-11-22 | 702 | 2024-03-01 |  | 2024-03-01 | 2026-01-31
Statutory approvals |  |  | 606 | 2024-03-02 | 2025-10-28 | 671 | 2024-03-02 |  | 2024-03-02 | 2026-01-01
Tendering and Contracting | Civil Contractor |  | 176 | 2024-03-05 | 2024-08-27 | 176 | 2024-03-05 | 2024-08-27 | 2024-03-05 | 2024-08-27
Tendering and Contracting | Mechanical -Fabrication and Erection Contractor |  | 166 | 2024-08-28 | 2025-02-09 | 96 | 2024-08-28 |  | 2024-08-28 | 2024-12-01
|  | Plate Fabrication Contractor | 1 | 2024-08-28 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28
|  | Finalization of Structural Workshop | 1 | 2024-08-28 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28
|  | Finalization of Erection Contractors | 20 | 2025-01-21 | 2025-02-09 | 7 | 2024-11-25 | 2024-12-01 | 2024-11-25 | 2024-12-01
Tendering and Contracting | E&I Contractor | Finalization of E&I Contractors | 30 | 2025-02-10 | 2025-03-11 | 30 |  |  | 2025-04-01 | 2025-04-30
Tendering and Contracting | Refractory & Insulation Contractor | Finalization of Refractory and Insulation Contractor | 30 | 2025-03-12 | 2025-04-10 | 30 |  |  | 2025-05-01 | 2025-05-30
|  |  |  | 2024-03-03 | 2025-05-06 | 429 | 2024-03-03 | 2025-01-22 |  | 2025-07-15
Engineering | Layout Drawings | Layout Drawing | 2 | 2024-04-11 | 2024-04-12 | 2 |  |  | 2024-04-11 | 2024-04-12
Engineering | Process and Architecture |  | 361 | 2024-03-03 | 2025-02-26 | 431 | 2024-03-03 |  | 2024-03-03 | 2025-05-07
|  | 212 - LimeStone Crushing | 81 | 2024-04-17 | 2024-07-06 | 81 | 2024-04-17 | 2024-07-06 | 2024-04-17 | 2024-07-06
|  | 292 - Limestone transport to storage | 224 | 2024-06-15 | 2025-01-24 | 294 | 2024-06-15 |  | 2024-06-15 | 2025-04-04
|  | 312 - Limestone reclaiming and transport | 290 | 2024-04-14 | 2025-01-28 | 360 | 2024-04-14 | 2024-09-16 | 2024-04-14 | 2025-04-08
|  | X12 - Correctives unloading and storage | 132 | 2024-05-06 | 2024-09-14 | 132 | 2024-05-06 | 2024-09-14 | 2024-05-06 | 2024-09-14
|  | X92 - Correctives reclaiming and transport | 325 | 2024-03-03 | 2025-01-21 | 395 | 2024-03-03 | 2024-09-16 | 2024-03-03 | 2025-04-01
|  | K92 - Additives reclaiming and transport | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14
|  | L12 - Wagong tippler and conveying | 150 | 2024-09-12 | 2025-02-08 | 220 | 2024-09-12 |  | 2024-09-12 | 2025-04-19
|  | L22 - Coal reclaiming and transport | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14
|  | 332 - Raw mill feed | 244 | 2024-05-29 | 2025-01-27 | 314 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2025-04-07
|  | 362 - Raw mill | 313 | 2024-03-22 | 2025-01-28 | 379 | 2024-03-22 | 2024-03-29 | 2024-03-22 | 2025-04-04
|  | 412 - Raw meal silo | 329 | 2024-03-26 | 2025-02-17 | 372 | 2024-03-26 | 2024-10-11 | 2024-03-26 | 2025-04-01
|  | 442 - Preheater | 318 | 2024-03-24 | 2025-02-04 | 378 | 2024-03-24 | 2024-03-29 | 2024-03-24 | 2025-04-05
|  | 462 - Kiln | 297 | 2024-03-22 | 2025-01-12 | 297 | 2024-03-22 | 2025-01-12 | 2024-03-22 | 2025-01-12
|  | 472 - Cooler | 319 | 2024-03-25 | 2025-02-06 | 382 | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2025-04-10
|  | 492 - Clinker transport | 217 | 2024-06-26 | 2025-01-28 | 287 | 2024-06-26 | 2024-11-04 | 2024-06-26 | 2025-04-08
|  | 6K2 - Clinker loading silos (rail) | 313 | 2024-03-28 | 2025-02-03 | 377 | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2025-04-08
|  | L62 - Fuel grinding | 326 | 2024-03-26 | 2025-02-14 | 396 | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2025-04-25
|  | D33 - Compressed air station | 184 | 2024-08-27 | 2025-02-26 | 254 | 2024-08-27 |  | 2024-08-27 | 2025-05-07
|  | M32(1,2) - Combined Water Pump Station(1,2) | 42 | 2024-12-17 | 2025-01-27 | 112 | 2024-12-17 |  | 2024-12-17 | 2025-04-07
|  | HVAC | 164 | 2024-08-12 | 2025-01-22 | 164 | 2024-08-12 | 2025-01-22 | 2024-08-12 | 2025-01-22
Engineering | Plate Fabrication Drawing |  | 411 | 2024-03-22 | 2025-05-06 | 481 | 2024-03-22 |  | 2024-03-22 | 2025-07-15
|  | 212 - LimeStone Crushing | 5 | 2024-06-15 | 2024-06-19 | 5 | 2024-06-15 | 2024-06-19 | 2024-06-15 | 2024-06-19
|  | 292 - Limestone transport to storage | 225 | 2024-06-15 | 2025-01-25 | 295 | 2024-06-15 |  | 2024-06-15 | 2025-04-05
|  | 312 - Limestone reclaiming and transport | 156 | 2024-04-14 | 2024-09-16 | 156 | 2024-04-14 | 2024-09-16 | 2024-04-14 | 2024-09-16
|  | X12 - Correctives unloading and storage | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14
|  | X92 - Correctives reclaiming and transport | 43 | 2025-01-17 | 2025-02-28 | 113 | 2025-01-17 |  | 2025-01-17 | 2025-05-09
|  | K92 - Additives reclaiming and transport | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14
|  | L12 - Wagong tippler and conveying | 149 | 2024-11-04 | 2025-04-01 | 187 | 2024-11-04 |  | 2024-11-04 | 2025-05-09
|  | L22 - Coal reclaiming and transport | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-14
|  | 332 - Raw mill feed | 1 | 2024-05-29 | 2024-05-29 | 1 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29
|  | 362 - Raw mill | 8 | 2024-03-22 | 2024-03-29 | 8 | 2024-03-22 | 2024-03-29 | 2024-03-22 | 2024-03-29
|  | 412 - Raw meal silo | 1 | 2024-03-26 | 2024-03-26 | 1 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26
|  | 442 - Preheater | 6 | 2024-03-24 | 2024-03-29 | 6 | 2024-03-24 | 2024-03-29 | 2024-03-24 | 2024-03-29
|  | 462 - Kiln | 44 | 2024-03-22 | 2024-05-04 | 44 | 2024-03-22 | 2024-05-04 | 2024-03-22 | 2024-05-04
|  | 472 - Cooler | 5 | 2024-03-25 | 2024-03-29 | 5 | 2024-03-25 | 2024-03-29 | 2024-03-25 | 2024-03-29
|  | 492 - Clinker transport | 26 | 2024-10-10 | 2024-11-04 | 26 | 2024-10-10 | 2024-11-04 | 2024-10-10 | 2024-11-04
|  | 6K2 - Clinker loading silos (rail) | 6 | 2024-03-28 | 2024-04-02 | 6 | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2024-04-02
|  | L62 - Fuel grinding | 4 | 2024-03-26 | 2024-03-29 | 4 | 2024-03-26 | 2024-03-29 | 2024-03-26 | 2024-03-29
|  | D33 - Compressed air station | 24 | 2025-04-13 | 2025-05-06 | 24 |  |  | 2025-06-22 | 2025-07-15
Engineering | Civil Construction Drawing |  | 392 | 2024-03-20 | 2025-04-15 | 438 | 2024-03-20 |  | 2024-03-20 | 2025-05-31
|  | 212 - LimeStone Crushing | 313 | 2024-03-20 | 2025-01-26 | 383 | 2024-03-20 | 2025-01-21 | 2024-03-20 | 2025-04-06
|  | 292 - Limestone transport to storage | 53 | 2024-12-31 | 2025-02-21 | 123 | 2024-12-31 |  | 2024-12-31 | 2025-05-02
|  | 312 - Limestone reclaiming and transport | 31 | 2024-09-10 | 2024-10-10 | 228 | 2024-09-16 |  | 2024-09-16 | 2025-05-01
|  | X12 - Correctives unloading and storage | 1 | 2024-09-14 | 2024-09-14 | 1 | 2024-09-14 |  | 2024-09-14 | 2024-09-14
|  | X92 - Correctives reclaiming and transport | 151 | 2024-09-14 | 2025-02-11 | 221 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2025-04-22
|  | K92 - Additives reclaiming and transport | 160 | 2024-09-14 | 2025-02-20 | 230 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2025-05-01
|  | L12 - Wagong tippler and conveying | 179 | 2024-09-12 | 2025-03-09 | 238 | 2024-09-12 |  | 2024-09-12 | 2025-05-07
|  | L22 - Coal reclaiming and transport | 144 | 2024-09-14 | 2025-02-04 | 214 | 2024-09-14 |  | 2024-09-14 | 2025-04-15
|  | 332 - Raw mill feed | 202 | 2024-06-13 | 2024-12-31 | 202 | 2024-06-13 | 2024-12-31 | 2024-06-13 | 2024-12-31
|  | 362 - Raw mill | 6 | 2024-05-27 | 2024-06-01 | 6 | 2024-05-27 | 2024-06-01 | 2024-05-27 | 2024-06-01
|  | 412 - Raw meal silo | 130 | 2024-04-13 | 2024-08-20 | 130 | 2024-04-13 | 2024-08-20 | 2024-04-13 | 2024-08-20
|  | 442 - Preheater | 101 | 2024-04-16 | 2024-07-25 | 101 | 2024-04-16 | 2024-07-25 | 2024-04-16 | 2024-07-25
|  | 462 - Kiln | 1 | 2024-05-09 | 2024-05-09 | 1 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2024-05-09
|  | 472 - Cooler | 9 | 2024-07-23 | 2024-07-31 | 9 | 2024-07-23 | 2024-07-31 | 2024-07-23 | 2024-07-31
|  | 492 - Clinker transport | 102 | 2024-11-04 | 2025-02-13 | 172 | 2024-11-04 |  | 2024-11-04 | 2025-04-24
|  | 6K2 - Clinker loading silos (rail) | 226 | 2024-06-27 | 2025-02-07 | 296 | 2024-06-27 |  | 2024-06-27 | 2025-04-18
|  | L62 - Fuel grinding | 106 | 2024-05-15 | 2024-08-28 | 106 | 2024-05-15 | 2024-08-28 | 2024-05-15 | 2024-08-28
|  | D33 - Compressed air station | 24 | 2025-02-27 | 2025-03-22 | 24 |  |  | 2025-05-08 | 2025-05-31
|  | M32(1,2) - Combined Water Pump Station(1,2) | 8 | 2025-04-08 | 2025-04-15 | 7 | 2024-12-17 |  | 2025-05-20 | 2025-05-26
Engineering | Steel Structural GA Details |  | 364 | 2024-04-17 | 2025-04-15 | 434 | 2024-04-17 |  | 2024-04-17 | 2025-06-24
|  | 212 - LimeStone Crushing | 294 | 2024-04-17 | 2025-02-04 | 364 | 2024-04-17 |  | 2024-04-17 | 2025-04-15
|  | 292 - Limestone transport to storage | 49 | 2025-01-31 | 2025-03-20 | 112 | 2025-01-31 |  | 2025-01-31 | 2025-05-22
|  | 312 - Limestone reclaiming and transport | 17 | 2024-10-11 | 2024-10-27 | 17 |  |  | 2025-05-02 | 2025-05-18
|  | X12 - Correctives unloading and storage | 143 | 2024-09-14 | 2025-02-03 | 213 | 2024-09-14 |  | 2024-09-14 | 2025-04-14
|  | X92 - Correctives reclaiming and transport | 74 | 2025-01-01 | 2025-03-15 | 144 | 2025-01-01 |  | 2025-01-01 | 2025-05-24
|  | K92 - Additives reclaiming and transport | 92 | 2024-12-31 | 2025-04-01 | 162 | 2024-12-31 |  | 2024-12-31 | 2025-06-10
|  | L12 - Wagong tippler and conveying | 19 | 2025-02-19 | 2025-03-09 | 19 |  |  | 2025-04-19 | 2025-05-07
|  | L22 - Coal reclaiming and transport | 55 | 2024-12-31 | 2025-02-23 | 125 | 2024-12-31 |  | 2024-12-31 | 2025-05-04
|  | 332 - Raw mill feed | 212 | 2024-07-29 | 2025-02-25 | 212 | 2024-07-29 |  | 2024-07-29 | 2025-02-25
|  | 362 - Raw mill | 164 | 2024-07-29 | 2025-01-08 | 249 | 2024-07-29 |  | 2024-07-29 | 2025-04-03
|  | 412 - Raw meal silo | 140 | 2024-07-29 | 2024-12-15 | 140 | 2024-07-29 |  | 2024-07-29 | 2024-12-15
|  | 442 - Preheater | 177 | 2024-07-29 | 2025-01-21 | 247 | 2024-07-29 |  | 2024-07-29 | 2025-04-01
|  | 462 - Kiln | 73 | 2024-11-04 | 2025-01-15 | 73 | 2024-11-04 |  | 2024-11-04 | 2025-01-15
|  | 472 - Cooler | 83 | 2024-11-06 | 2025-01-27 | 153 | 2024-11-06 |  | 2024-11-06 | 2025-04-07
|  | 492 - Clinker transport | 137 | 2024-11-05 | 2025-03-21 | 193 | 2024-11-05 |  | 2024-11-05 | 2025-05-16
|  | 6K2 - Clinker loading silos (rail) | 134 | 2024-11-10 | 2025-03-23 | 204 | 2024-11-10 |  | 2024-11-10 | 2025-06-01
|  | L62 - Fuel grinding | 43 | 2024-11-08 | 2024-12-20 | 43 | 2024-11-08 |  | 2024-11-08 | 2024-12-20
|  | D33 - Compressed air station | 24 | 2025-03-23 | 2025-04-15 | 24 |  |  | 2025-06-01 | 2025-06-24
Engineering | Steel Structural - Tekla Drawings |  | 185 | 2024-10-13 | 2025-04-15 | 434 | 2024-04-17 |  | 2024-04-17 | 2025-06-24
Engineering | E&I Engineering |  | 96 | 2024-11-16 | 2025-02-19 | 159 | 2024-11-16 |  | 2024-11-16 | 2025-04-23
|  | Limestone Crusher (201-3E1 LC#31) - 214 | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Raw Material Transport to Storage (201-3E2 LC#32) | 82 | 2024-11-16 | 2025-02-05 | 152 | 2024-11-16 |  | 2024-11-16 | 2025-04-16
|  | Raw Material Handling (201-3E3 LC#33) | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Raw Mill & Preheater (401-3E1 LC#34) | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Raw mill Hopper (301-3E1 LC#34A) | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Clinker Cooler & Coal Mill (401-3E2 LC#35) | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Wagon tippler & Coal handling (L01-3E1 LC#36) | 70 | 2024-12-05 | 2025-02-12 | 140 | 2024-12-05 |  | 2024-12-05 | 2025-04-23
|  | Corrective handling (201-3E4 LC#37) | 80 | 2024-11-16 | 2025-02-03 | 150 | 2024-11-16 |  | 2024-11-16 | 2025-04-14
|  | Water Treatment & Fire Hydrant (M33-3E1 LC#38) | 19 | 2025-01-30 | 2025-02-17 | 75 | 2025-01-30 |  | 2025-01-30 | 2025-04-14
|  | Clinker Silo (401-3E5 LC#39) | 73 | 2024-11-16 | 2025-01-27 | 143 | 2024-11-16 |  | 2024-11-16 | 2025-04-07
|  | Clinker Loading (Rail) (401-3E6 LC#39A) | 73 | 2024-11-16 | 2025-01-27 | 143 | 2024-11-16 |  | 2024-11-16 | 2025-04-07
|  | 801-Powe Cable Routing | 21 | 2025-01-30 | 2025-02-19 | 21 |  |  | 2025-04-01 | 2025-04-21
Procurement | Offshore Equipment |  | 369 | 2024-03-03 | 2025-03-06 | 439 | 2024-03-03 |  | 2024-03-03 | 2025-05-15
|  | Vertical Mill For Coal | 1 | 2025-03-03 | 2025-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Roller Press | 1 | 2024-04-09 | 2024-04-09 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Seperator | 1 | 2025-03-03 | 2025-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Polyethyleue Liner | 1 | 2024-09-10 | 2024-09-10 | 1 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10
|  | Wearable Liner | 1 | 2024-07-18 | 2024-07-18 | 1 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18
|  | Wear Resistant Ceramics Material | 27 | 2024-07-31 | 2024-08-26 | 1 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31
|  | MV Motor | 33 | 2024-05-22 | 2024-06-23 | 1 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22
|  | Metal Detector | 40 | 2024-05-22 | 2024-06-30 | 1 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22
|  | Metal Separator | 44 | 2024-06-11 | 2024-07-24 | 1 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-11
|  | Sampler | 44 | 2024-04-18 | 2024-05-31 | 1 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18
|  | HT Sampler | 43 | 2024-04-29 | 2024-06-10 | 1 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29
|  | Kiln | 41 | 2024-04-09 | 2024-05-19 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Preheater (Diptube, Expansion Joint, Valves) | 42 | 2024-04-09 | 2024-05-20 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Grate Cooler | 43 | 2024-04-09 | 2024-05-21 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Burner | 1 | 2024-04-09 | 2024-04-09 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Tertiary Duct/Kiln Hood | 1 |  |  | 1
|  | Process Valve/Non Standard Valve | 1 | 2024-08-06 | 2024-08-06 | 1 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-06
|  | Explosion Valve | 1 |  |  | 1
|  | Motorized Actuator | 1 | 2024-04-12 | 2024-04-12 | 1 | 2024-04-12 | 2024-04-12 | 2024-04-12 | 2024-04-12
|  | Expansion Joint/Soft Joint | 1 | 2024-04-18 | 2024-04-18 | 1 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18
|  | Wear Resistant Bend | 1 | 2024-10-23 | 2024-10-23 | 1 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23
|  | Sinter Zone Refractory (Brick for Kiln) | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Other Refractory Brick | 1 | 2024-08-25 | 2024-08-25 | 1 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25
|  | Ceramic Fibre Plate | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Calcium Silicate | 1 | 2024-08-28 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-08-28
|  | Other Refracotry Material（Anchor Etc.) | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Water Treatment System | 1 | 2024-07-31 | 2024-07-31 | 1 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31
|  | Water Spraying System | 1 | 2024-05-29 | 2024-05-29 | 1 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29
|  | Cooling Tower/Filter | 1 | 2024-05-29 | 2024-05-29 | 1 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-29
|  | Water Pump | 1 | 2024-08-06 | 2024-08-06 | 1 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-06
|  | Water Valve | 20 | 2025-01-21 | 2025-02-09 | 20 |  |  | 2025-04-01 | 2025-04-20
|  | Water Instrument | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Bucket Elevator (Silo Feeding And Kiln Feeding) | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Bucket Elevator (Others) | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Motorized Ball Valve | 1 | 2024-04-09 | 2024-04-09 | 1 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2024-04-09
|  | Manhole/Measure Hole | 1 | 2024-11-24 | 2024-11-24 | 1 | 2024-11-24 | 2024-11-24 | 2024-11-24 | 2024-11-24
|  | Belt Conveyor | 1 | 2024-07-15 | 2024-07-15 | 1 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15
|  | OLBC - Belt Conveyor | 1 | 2024-07-10 | 2024-07-10 | 1 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10
|  | Belt (If purchase seprately) | 1 | 2024-07-10 | 2024-07-10 | 1 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10
|  | Pan Conveyor (DPC) | 1 | 2024-04-10 | 2024-04-10 | 1 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10
|  | Air Slide | 1 | 2024-04-10 | 2024-04-10 | 1 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10
|  | Screw Conveyor | 1 | 2024-04-10 | 2024-04-10 | 1 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10
|  | FU Conveyor (Chain Conveyor) | 1 | 2024-04-10 | 2024-04-10 | 1 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10
|  | Surface Feeder | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Rotor-Feeder For Coal From European | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Rotor-Feeder For Coal From China | 1 |  |  | 1
|  | Rotor-Feeder For Raw Meal From European | 1 | 2024-04-07 | 2024-04-07 | 1 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-07
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 1 | 2024-07-15 | 2024-07-15 | 1 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15
|  | Control Valve For Raw Meal Silo/Kiln Feeding System Valve | 1 | 2024-04-10 | 2024-04-10 | 1 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10
|  | Wagon Bulk Loader | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Truck Bulk Loader | 1 | 2024-03-03 | 2024-03-03 | 1 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 2024-03-03
|  | Process Bag House | 1 | 2024-04-22 | 2024-04-22 | 1 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22
|  | ESP | 1 | 2024-04-22 | 2024-04-22 | 1 | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22
|  | Roots Blower | 1 | 2024-05-22 | 2024-05-22 | 1 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22
|  | Air Compressor | 1 | 2024-07-25 | 2024-07-25 | 1 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25
|  | Air Dryer | 1 | 2024-07-25 | 2024-07-25 | 1 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25
|  | Air Tank | 1 | 2024-06-04 | 2024-06-04 | 1 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04
|  | Air Cannon | 1 | 2024-04-18 | 2024-04-18 | 1 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18
|  | Silencer | 1 |  |  | 1
Procurement | Onshore Equipment |  | 345 | 2024-04-11 | 2025-03-21 | 415 | 2024-04-11 |  | 2024-04-11 | 2025-05-30
|  | Limestone Crusher | 1 | 2024-04-11 | 2024-04-11 | 1 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-04-11
|  | Sizer | 1 | 2024-07-18 | 2024-07-18 | 1 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18
|  | X-Ray Analyzer | 1 |  |  | 1
|  | Online Cross Analyzer | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Local Fabrication - Preheater | 1 |  |  | 1
|  | Local Fabrication - Kiln | 1 | 2024-07-10 | 2024-07-10 | 1 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10
|  | Local Fabrication - Cooler | 1 | 2024-09-26 | 2024-09-26 | 1 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26
|  | Local Fabrication - Coal Mill | 1 | 2024-07-10 | 2024-07-10 | 1 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10
|  | Local Fabrication - Bag House | 1 | 2024-09-17 | 2024-09-17 | 1 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2024-09-17
|  | Local Fabrication - Bucket Elvator | 1 | 2024-07-22 | 2024-07-22 | 1 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-22
|  | Local Fabrication - ESP | 1 | 2024-09-09 | 2024-09-09 | 1 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09
|  | Other Refractory Brick | 44 | 2025-01-21 | 2025-03-05 | 44 |  |  | 2025-04-01 | 2025-05-14
|  | Pipes And Parts | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Elevator | 1 |  |  | 1
|  | Castable | 60 | 2025-01-21 | 2025-03-21 | 60 |  |  | 2025-04-01 | 2025-05-30
|  | Stacker And Reclaimer | 1 | 2024-05-17 | 2024-05-17 | 1 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-17
|  | Belt Conveyor | 1 |  |  | 1
|  | Belt | 1 |  |  | 1
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 1 | 2024-07-15 | 2024-07-15 | 1 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15
|  | Load Cell | 1 | 2024-07-15 | 2024-07-15 | 1 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15
|  | Weighing Bridge | 1 | 2024-04-26 | 2024-04-26 | 1 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26
|  | Wagon Tippler | 1 | 2024-05-23 | 2024-05-23 | 1 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23
|  | Truck Tippler | 1 | 2024-05-16 | 2024-05-16 | 1 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16
|  | Nuisance Bag Filter | 1 | 2024-08-13 | 2024-08-13 | 1 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13
|  | Grate Cooler Fan | 1 | 2024-06-27 | 2024-06-27 | 1 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27
|  | Process Fan | 1 | 2024-05-06 | 2024-05-06 | 1 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06
|  | Small Fan | 1 | 2024-08-20 | 2024-08-20 | 1 | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-08-20
|  | Air Conditioner | 40 | 2025-01-21 | 2025-03-01 | 40 |  |  | 2025-04-01 | 2025-05-10
|  | Ventilation System | 1 |  |  | 1
|  | Insulation Material | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Insulation Auxiliary Material (Steel Plate/Bolts Etc.) | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Fire Equipment (Extinguisher/Outdoor Fire Hydrant) | 1 | 2024-06-04 | 2024-06-04 | 1 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04
|  | Fire Fighting System (N2 Etc.) | 1 | 2024-06-04 | 2024-06-04 | 1 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04
|  | Electrical Hoist | 1 | 2024-11-26 | 2024-11-26 | 1 | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26
|  | Double/Single Crane | 1 | 2024-11-26 | 2024-11-26 | 1 | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26
|  | Lubrication Oil | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
Procurement | E & I Items (Onshore) |  | 371 | 2024-03-01 | 2025-03-06 | 441 | 2024-03-01 |  | 2024-03-01 | 2025-05-15
|  | MV Switchboards | 1 | 2024-12-11 | 2024-12-11 | 1 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11
|  | MV Drives | 1 | 2024-10-08 | 2024-10-08 | 1 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08
|  | LRS | 1 | 2024-08-22 | 2024-08-22 | 1 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22
|  | MV Capacitors | 1 | 2024-11-21 | 2024-11-21 | 1 | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2024-11-21
|  | Transformers - Power And Distribution | 1 | 2024-09-30 | 2024-09-30 | 1 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30
|  | Lighting Power Transformer | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | LV Panels - PCC/ MCC / MLDB/ MPDB/ EPDB | 12 | 2025-01-21 | 2025-02-01 | 21 |  |  | 2025-02-02 | 2025-02-22
|  | LV Bus Duct | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | LV Capacitor Panels | 1 | 2024-09-16 | 2024-09-16 | 1 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16
|  | SPDB (Sub Main Distribution Board) | 10 | 2025-01-21 | 2025-01-30 | 10 |  |  | 2025-04-01 | 2025-04-10
|  | LV Drives | 1 | 2024-12-09 | 2024-12-09 | 1 | 2024-12-09 | 2024-12-09 | 2024-12-09 | 2024-12-09
|  | UPS / UPS DB / DCS DB | 15 | 2025-01-21 | 2025-02-04 | 15 |  |  | 2025-04-01 | 2025-04-15
|  | Battery / Battery Charger | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Switches / Sockets/ Single Phase Receptacle/ Welding Socket Outlet/ Exit Sign Boards | 21 | 2025-01-21 | 2025-02-10 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | Local Push Buttons /Panic Stop Push Buttons/ VCS | 21 | 2025-01-21 | 2025-02-10 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | Analog / Digital Junction Box Various Sizes 5TB To 200 TB | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Magnetic Starter Panel/Power Junction Box | 21 | 2025-01-21 | 2025-02-10 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | Hooter And Flasher | 1 | 2024-09-16 | 2024-09-16 | 1 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16
|  | Ligthing SLD With Timer | 21 | 2025-01-21 | 2025-02-10 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | AAQMS (Ambient Air Quality Monitoring System) | 1 | 2024-10-08 | 2024-10-08 | 1 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08
|  | Dust Monitors | 1 | 2024-09-16 | 2024-09-16 | 1 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16
|  | Temperature Transmitters | 1 | 2024-10-01 | 2024-10-01 | 1 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01
|  | Pressure Transmitters / DP Transmitters | 44 | 2024-10-01 | 2024-11-13 | 44 | 2024-10-01 | 2024-11-13 | 2024-10-01 | 2024-11-13
|  | Radar Type Level Transmitter | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Ultrasonic Level Transmitters | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Hopper Level Switch | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Vibration Transmitters | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | RTD / Thermocouple | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Plant DCS / PLC System / DCS System / Control Desk / Computers / Servers | 1 | 2024-09-20 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20
|  | Sub Control System Panel (Part Of Mechanical Equipmentgs Package） | 1 |  |  | 1
|  | Fire Alarm System (For Load Centers) | 30 | 2025-01-21 | 2025-02-19 | 4 | 2025-01-30 | 2025-02-02 | 2025-01-30 | 2025-02-02
|  | CCTV Monitoring System | 45 | 2025-01-21 | 2025-03-06 | 6 | 2025-01-15 | 2025-01-20 | 2025-01-15 | 2025-01-20
|  | Energy Management System | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Telephone System | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | PA System | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Access Control System | 45 | 2025-01-21 | 2025-03-06 | 29 |  |  | 2025-02-09 | 2025-03-09
|  | Fiber Optic Cables / Ethernet Cable | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Cable Trays Various Sizes | 10 | 2025-01-21 | 2025-01-30 | 10 |  |  | 2025-04-01 | 2025-04-10
|  | MV Power Cables | 1 | 2024-12-19 | 2024-12-19 | 1 | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19
|  | LV Power Cables | 14 | 2025-01-21 | 2025-02-03 | 14 |  |  | 2025-04-01 | 2025-04-14
|  | Control And Signal Cables | 21 | 2025-01-21 | 2025-02-10 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | Lighting Cable Various Sizes | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Earthing Junction Box | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Earthing Electrode | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Earthing Flat / Wire - Different Sizes | 95 | 2024-04-10 | 2024-07-13 | 1 |  |  | 2024-04-10 | 2024-04-10
|  | Outdoor Led Lamps/Fluorscent Led Lamp/Emergency Led Lamps With Battery Back-Up/Road / Street Lamps | 45 | 2025-01-21 | 2025-03-06 | 1 |  |  | 2025-03-04 | 2025-03-04
|  | High Mast | 1 | 2024-08-30 | 2024-08-30 | 1 |  |  | 2024-08-30 | 2024-08-30
|  | Aviation And All Other Lighting Related Items | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Cable Glands And Lugs, Termination Kits | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Safety And PPE Equipment Exit Sign Boards | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | ETAP Study | 1 | 2024-07-24 | 2024-07-24 | 1 | 2024-07-24 | 2024-07-24 | 2024-07-24 | 2024-07-24
|  | E&I Engineering | 1 |  |  | 1
|  | LV Motors | 88 | 2024-03-01 | 2024-05-27 | 88 | 2024-03-01 | 2024-05-27 | 2024-03-01 | 2024-05-27
Manufacturing | Offshore Equipment |  | 416 | 2024-03-01 | 2025-04-20 | 486 | 2024-03-01 |  | 2024-03-01 | 2025-06-29
|  | Vertical Mill For Coal | 66 | 2024-08-19 | 2024-10-23 | 66 | 2024-08-19 | 2024-10-23 | 2024-08-19 | 2024-10-23
|  | Roller Press | 38 | 2024-06-18 | 2024-07-25 | 38 | 2024-06-18 | 2024-07-25 | 2024-06-18 | 2024-07-25
|  | Seperator | 44 | 2024-04-09 | 2024-05-22 | 44 | 2024-04-09 | 2024-05-22 | 2024-04-09 | 2024-05-22
|  | Polyethyleue Liner | 106 | 2024-10-21 | 2025-02-03 | 176 | 2024-10-21 |  | 2024-10-21 | 2025-04-14
|  | Wearable Liner | 154 | 2024-09-10 | 2025-02-10 | 224 | 2024-09-10 |  | 2024-09-10 | 2025-04-21
|  | Wear Resistant Ceramics Material | 76 | 2024-08-31 | 2024-11-14 | 76 | 2024-08-31 | 2024-11-14 | 2024-08-31 | 2024-11-14
|  | MV Motor | 64 | 2024-06-23 | 2024-08-25 | 64 | 2024-06-23 | 2024-08-25 | 2024-06-23 | 2024-08-25
|  | Metal Detector | 116 | 2024-06-23 | 2024-10-16 | 116 | 2024-06-23 | 2024-10-16 | 2024-06-23 | 2024-10-16
|  | Metal Separator | 85 | 2024-07-24 | 2024-10-16 | 85 | 2024-07-24 | 2024-10-16 | 2024-07-24 | 2024-10-16
|  | Sampler | 49 | 2024-05-31 | 2024-07-18 | 49 | 2024-05-31 | 2024-07-18 | 2024-05-31 | 2024-07-18
|  | HT Sampler | 246 | 2024-06-10 | 2025-02-10 | 316 | 2024-06-10 |  | 2024-06-10 | 2025-04-21
|  | Kiln | 68 | 2024-05-19 | 2024-07-25 | 68 | 2024-05-19 | 2024-07-25 | 2024-05-19 | 2024-07-25
|  | Preheater (Diptube, Expansion Joint, Valves) | 147 | 2024-03-01 | 2024-07-25 | 147 | 2024-03-01 | 2024-07-25 | 2024-03-01 | 2024-07-25
|  | Grate Cooler | 92 | 2024-05-21 | 2024-08-20 | 92 | 2024-05-21 | 2024-08-20 | 2024-05-21 | 2024-08-20
|  | Burner | 112 | 2024-05-01 | 2024-08-20 | 112 | 2024-05-01 | 2024-08-20 | 2024-05-01 | 2024-08-20
|  | Tertiary Duct/Kiln Hood | 1 |  |  | 1
|  | Process Valve/Non Standard Valve | 97 | 2024-08-16 | 2024-11-20 | 97 | 2024-08-16 | 2024-11-20 | 2024-08-16 | 2024-11-20
|  | Explosion Valve | 1 |  |  | 1
|  | Motorized Actuator | 165 | 2024-05-06 | 2024-10-17 | 165 | 2024-05-06 | 2024-10-17 | 2024-05-06 | 2024-10-17
|  | Expansion Joint/Soft Joint | 191 | 2024-05-08 | 2024-11-14 | 191 | 2024-05-08 | 2024-11-14 | 2024-05-08 | 2024-11-14
|  | Wear Resistant Bend | 71 | 2024-10-23 | 2025-01-01 | 71 | 2024-10-23 | 2025-01-01 | 2024-10-23 | 2025-01-01
|  | Sinter Zone Refractory (Brick for Kiln) | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Other Refractory Brick | 136 | 2024-09-07 | 2025-01-20 | 136 | 2024-09-07 | 2025-01-20 | 2024-09-07 | 2025-01-20
|  | Ceramic Fibre Plate | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Calcium Silicate | 65 | 2024-09-11 | 2024-11-14 | 65 | 2024-09-11 | 2024-11-14 | 2024-09-11 | 2024-11-14
|  | Other Refracotry Material（Anchor Etc.) | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Water Treatment System | 95 | 2024-08-10 | 2024-11-12 | 95 | 2024-08-10 | 2024-11-12 | 2024-08-10 | 2024-11-12
|  | Water Spraying System | 132 | 2024-07-12 | 2024-11-20 | 132 | 2024-07-12 | 2024-11-20 | 2024-07-12 | 2024-11-20
|  | Cooling Tower/Filter | 132 | 2024-07-12 | 2024-11-20 | 132 | 2024-07-12 | 2024-11-20 | 2024-07-12 | 2024-11-20
|  | Water Pump | 166 | 2024-08-22 | 2025-02-03 | 236 | 2024-08-22 |  | 2024-08-22 | 2025-04-14
|  | Water Valve | 45 | 2025-02-10 | 2025-03-26 | 45 |  |  | 2025-04-21 | 2025-06-04
|  | Water Instrument | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Bucket Elevator (Silo Feeding And Kiln Feeding) | 135 | 2024-04-30 | 2024-09-11 | 135 | 2024-04-30 | 2024-09-11 | 2024-04-30 | 2024-09-11
|  | Bucket Elevator (Others) | 117 | 2024-04-26 | 2024-08-20 | 117 | 2024-04-26 | 2024-08-20 | 2024-04-26 | 2024-08-20
|  | Motorized Ball Valve | 71 | 2024-05-08 | 2024-07-17 | 71 | 2024-05-08 | 2024-07-17 | 2024-05-08 | 2024-07-17
|  | Manhole/Measure Hole | 63 | 2025-01-21 | 2025-03-24 | 63 |  |  | 2025-04-01 | 2025-06-02
|  | Belt Conveyor | 143 | 2024-09-30 | 2025-02-19 | 213 | 2024-09-30 |  | 2024-09-30 | 2025-04-30
|  | OLBC - Belt Conveyor | 156 | 2024-09-17 | 2025-02-19 | 226 | 2024-09-17 |  | 2024-09-17 | 2025-04-30
|  | Belt (If purchase seprately) | 156 | 2024-09-17 | 2025-02-19 | 226 | 2024-09-17 |  | 2024-09-17 | 2025-04-30
|  | Pan Conveyor (DPC) | 116 | 2024-07-22 | 2024-11-14 | 116 | 2024-07-22 | 2024-11-14 | 2024-07-22 | 2024-11-14
|  | Air Slide | 172 | 2024-04-29 | 2024-10-17 | 172 | 2024-04-29 | 2024-10-17 | 2024-04-29 | 2024-10-17
|  | Screw Conveyor | 179 | 2024-04-22 | 2024-10-17 | 179 | 2024-04-22 | 2024-10-17 | 2024-04-22 | 2024-10-17
|  | FU Conveyor (Chain Conveyor) | 179 | 2024-04-22 | 2024-10-17 | 179 | 2024-04-22 | 2024-10-17 | 2024-04-22 | 2024-10-17
|  | Surface Feeder | 348 | 2024-03-09 | 2025-02-19 | 418 | 2024-03-09 |  | 2024-03-09 | 2025-04-30
|  | Rotor-Feeder For Coal From European | 278 | 2024-04-28 | 2025-01-30 | 348 | 2024-04-28 |  | 2024-04-28 | 2025-04-10
|  | Rotor-Feeder For Coal From China | 1 |  |  | 1
|  | Rotor-Feeder For Raw Meal From European | 310 | 2024-04-26 | 2025-03-01 | 380 | 2024-04-26 |  | 2024-04-26 | 2025-05-10
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 224 | 2024-08-10 | 2025-03-21 | 294 | 2024-08-10 |  | 2024-08-10 | 2025-05-30
|  | Control Valve For Raw Meal Silo/Kiln Feeding System Valve | 168 | 2024-04-26 | 2024-10-10 | 168 | 2024-04-26 | 2024-10-10 | 2024-04-26 | 2024-10-10
|  | Wagon Bulk Loader | 159 | 2024-04-29 | 2024-10-04 | 159 | 2024-04-29 | 2024-10-04 | 2024-04-29 | 2024-10-04
|  | Truck Bulk Loader | 159 | 2024-04-29 | 2024-10-04 | 159 | 2024-04-29 | 2024-10-04 | 2024-04-29 | 2024-10-04
|  | Process Bag House | 148 | 2024-04-30 | 2024-09-24 | 148 | 2024-04-30 | 2024-09-24 | 2024-04-30 | 2024-09-24
|  | ESP | 148 | 2024-04-30 | 2024-09-24 | 148 | 2024-04-30 | 2024-09-24 | 2024-04-30 | 2024-09-24
|  | Roots Blower | 139 | 2024-05-31 | 2024-10-16 | 139 | 2024-05-31 | 2024-10-16 | 2024-05-31 | 2024-10-16
|  | Air Compressor | 108 | 2024-07-30 | 2024-11-14 | 108 | 2024-07-30 | 2024-11-14 | 2024-07-30 | 2024-11-14
|  | Air Dryer | 108 | 2024-07-30 | 2024-11-14 | 108 | 2024-07-30 | 2024-11-14 | 2024-07-30 | 2024-11-14
|  | Air Tank | 69 | 2024-07-09 | 2024-09-15 | 69 | 2024-07-09 | 2024-09-15 | 2024-07-09 | 2024-09-15
|  | Air Cannon | 121 | 2024-06-10 | 2024-10-08 | 121 | 2024-06-10 | 2024-10-08 | 2024-06-10 | 2024-10-08
|  | Silencer | 1 |  |  | 1
Manufacturing | Onshore Equipment |  | 375 | 2024-05-17 | 2025-05-26 | 445 | 2024-05-17 |  | 2024-05-17 | 2025-08-04
|  | Limestone Crusher | 39 | 2024-08-18 | 2024-09-25 | 39 | 2024-08-18 | 2024-09-25 | 2024-08-18 | 2024-09-25
|  | Sizer | 155 | 2024-10-08 | 2025-03-11 | 225 | 2024-10-08 |  | 2024-10-08 | 2025-05-20
|  | X-Ray Analyzer | 1 |  |  | 1
|  | Online Cross Analyzer | 45 | 2025-02-20 | 2025-04-05 | 45 |  |  | 2025-05-01 | 2025-06-14
|  | Local Fabrication - Preheater | 1 |  |  | 1
|  | Local Fabrication - Kiln | 221 | 2024-07-14 | 2025-02-19 | 291 | 2024-07-14 |  | 2024-07-14 | 2025-04-30
|  | Local Fabrication - Cooler | 127 | 2024-09-27 | 2025-01-31 | 197 | 2024-09-27 |  | 2024-09-27 | 2025-04-11
|  | Local Fabrication - Coal Mill | 208 | 2024-07-12 | 2025-02-04 | 278 | 2024-07-12 |  | 2024-07-12 | 2025-04-15
|  | Local Fabrication - Bag House | 133 | 2024-09-30 | 2025-02-09 | 203 | 2024-09-30 |  | 2024-09-30 | 2025-04-20
|  | Local Fabrication - Bucket Elvator | 127 | 2024-10-16 | 2025-02-19 | 197 | 2024-10-16 |  | 2024-10-16 | 2025-04-30
|  | Local Fabrication - ESP | 127 | 2024-10-01 | 2025-02-04 | 197 | 2024-10-01 |  | 2024-10-01 | 2025-04-15
|  | Other Refractory Brick | 44 | 2025-03-06 | 2025-04-18 | 44 |  |  | 2025-05-15 | 2025-06-27
|  | Pipes And Parts | 45 | 2025-02-20 | 2025-04-05 | 45 |  |  | 2025-05-01 | 2025-06-14
|  | Elevator | 1 |  |  | 1
|  | Castable | 60 | 2025-03-22 | 2025-05-20 | 60 |  |  | 2025-05-31 | 2025-07-29
|  | Stacker And Reclaimer | 229 | 2024-05-17 | 2024-12-31 | 329 | 2024-05-17 |  | 2024-05-17 | 2025-04-10
|  | Belt Conveyor | 1 |  |  | 1
|  | Belt | 1 |  |  | 1
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Load Cell | 87 | 2024-11-05 | 2025-01-30 | 157 | 2024-11-05 |  | 2024-11-05 | 2025-04-10
|  | Weighing Bridge | 90 | 2024-07-15 | 2024-10-12 | 90 | 2024-07-15 | 2024-10-12 | 2024-07-15 | 2024-10-12
|  | Wagon Tippler | 248 | 2024-06-27 | 2025-03-01 | 318 | 2024-06-27 |  | 2024-06-27 | 2025-05-10
|  | Truck Tippler | 206 | 2024-08-08 | 2025-03-01 | 276 | 2024-08-08 |  | 2024-08-08 | 2025-05-10
|  | Nuisance Bag Filter | 145 | 2024-10-08 | 2025-03-01 | 215 | 2024-10-08 |  | 2024-10-08 | 2025-05-10
|  | Grate Cooler Fan | 186 | 2024-08-18 | 2025-02-19 | 256 | 2024-08-18 |  | 2024-08-18 | 2025-04-30
|  | Process Fan | 188 | 2024-08-16 | 2025-02-19 | 258 | 2024-08-16 |  | 2024-08-16 | 2025-04-30
|  | Small Fan | 224 | 2024-10-15 | 2025-05-26 | 294 | 2024-10-15 |  | 2024-10-15 | 2025-08-04
|  | Air Conditioner | 70 | 2025-03-02 | 2025-05-10 | 70 |  |  | 2025-05-11 | 2025-07-19
|  | Ventilation System | 1 |  |  | 1
|  | Insulation Material | 75 | 2025-03-07 | 2025-05-20 | 75 |  |  | 2025-05-16 | 2025-07-29
|  | Insulation Auxiliary Material (Steel Plate/Bolts Etc.) | 75 | 2025-03-07 | 2025-05-20 | 75 |  |  | 2025-05-16 | 2025-07-29
|  | Fire Equipment (Extinguisher/Outdoor Fire Hydrant) | 181 | 2024-08-08 | 2025-02-04 | 251 | 2024-08-08 |  | 2024-08-08 | 2025-04-15
|  | Fire Fighting System (N2 Etc.) | 181 | 2024-08-08 | 2025-02-04 | 251 | 2024-08-08 |  | 2024-08-08 | 2025-04-15
|  | Electrical Hoist | 140 | 2025-01-01 | 2025-05-20 | 210 |  |  | 2025-01-01 | 2025-07-29
|  | Double/Single Crane | 60 | 2025-01-01 | 2025-03-01 | 130 |  |  | 2025-01-01 | 2025-05-10
|  | Lubrication Oil | 60 | 2025-02-20 | 2025-04-20 | 60 |  |  | 2025-05-01 | 2025-06-29
Manufacturing | E & I Items (Onshore) |  | 474 | 2024-03-01 | 2025-06-17 | 544 | 2024-03-01 |  | 2024-03-01 | 2025-08-26
|  | MV Switchboards | 120 | 2025-01-21 | 2025-05-20 | 120 |  |  | 2025-04-01 | 2025-07-29
|  | MV Drives | 120 | 2025-01-21 | 2025-05-20 | 120 |  |  | 2025-04-01 | 2025-07-29
|  | LRS | 120 | 2025-01-21 | 2025-05-20 | 120 |  |  | 2025-04-01 | 2025-07-29
|  | MV Capacitors | 45 | 2025-01-21 | 2025-03-06 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Transformers - Power And Distribution | 126 | 2024-11-01 | 2025-03-06 | 196 | 2024-11-01 |  | 2024-11-01 | 2025-05-15
|  | Lighting Power Transformer | 120 | 2025-02-04 | 2025-06-03 | 120 |  |  | 2025-04-15 | 2025-08-12
|  | LV Panels - PCC/ MCC / MLDB/ MPDB/ EPDB | 90 | 2025-02-02 | 2025-05-02 | 90 |  |  | 2025-04-01 | 2025-06-29
|  | LV Bus Duct | 90 | 2025-02-04 | 2025-05-04 | 90 |  |  | 2025-04-15 | 2025-07-13
|  | LV Capacitor Panels | 131 | 2024-11-01 | 2025-03-11 | 201 | 2024-11-01 |  | 2024-11-01 | 2025-05-20
|  | SPDB (Sub Main Distribution Board) | 60 | 2025-01-31 | 2025-03-31 | 60 |  |  | 2025-04-11 | 2025-06-09
|  | LV Drives | 110 | 2025-01-01 | 2025-04-20 | 180 | 2025-01-01 |  | 2025-01-01 | 2025-06-29
|  | UPS / UPS DB / DCS DB | 75 | 2025-02-05 | 2025-04-20 | 75 |  |  | 2025-04-16 | 2025-06-29
|  | Battery / Battery Charger | 134 | 2025-02-04 | 2025-06-17 | 134 |  |  | 2025-04-15 | 2025-08-26
|  | Switches / Sockets/ Single Phase Receptacle/ Welding Socket Outlet/ Exit Sign Boards | 60 | 2025-02-11 | 2025-04-11 | 60 |  |  | 2025-04-22 | 2025-06-20
|  | Local Push Buttons /Panic Stop Push Buttons/ VCS | 45 | 2025-02-11 | 2025-03-27 | 45 |  |  | 2025-04-22 | 2025-06-05
|  | Analog / Digital Junction Box Various Sizes 5TB To 200 TB | 60 | 2025-02-04 | 2025-04-04 | 60 |  |  | 2025-04-15 | 2025-06-13
|  | Magnetic Starter Panel/Power Junction Box | 60 | 2025-02-11 | 2025-04-11 | 60 |  |  | 2025-04-22 | 2025-06-20
|  | Hooter And Flasher | 142 | 2024-10-01 | 2025-02-19 | 117 | 2024-10-01 |  | 2024-10-01 | 2025-01-25
|  | Ligthing SLD With Timer | 30 | 2025-02-11 | 2025-03-12 | 30 |  |  | 2025-04-22 | 2025-05-21
|  | AAQMS (Ambient Air Quality Monitoring System) | 120 | 2024-11-07 | 2025-03-06 | 190 | 2024-11-07 |  | 2024-11-07 | 2025-05-15
|  | Dust Monitors | 119 | 2024-11-13 | 2025-03-11 | 189 | 2024-11-13 |  | 2024-11-13 | 2025-05-20
|  | Temperature Transmitters | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Pressure Transmitters / DP Transmitters | 109 | 2024-11-13 | 2025-03-01 | 179 | 2024-11-13 |  | 2024-11-13 | 2025-05-10
|  | Radar Type Level Transmitter | 45 | 2025-02-04 | 2025-03-20 | 45 |  |  | 2025-04-15 | 2025-05-29
|  | Ultrasonic Level Transmitters | 45 | 2025-02-04 | 2025-03-20 | 45 |  |  | 2025-04-15 | 2025-05-29
|  | Hopper Level Switch | 45 | 2025-02-04 | 2025-03-20 | 45 |  |  | 2025-04-15 | 2025-05-29
|  | Vibration Transmitters | 45 | 2025-02-04 | 2025-03-20 | 45 |  |  | 2025-04-15 | 2025-05-29
|  | RTD / Thermocouple | 45 | 2025-02-04 | 2025-03-20 | 45 |  |  | 2025-04-15 | 2025-05-29
|  | Plant DCS / PLC System / DCS System / Control Desk / Computers / Servers | 172 | 2024-10-01 | 2025-03-21 | 242 | 2024-10-01 |  | 2024-10-01 | 2025-05-30
|  | Sub Control System Panel (Part Of Mechanical Equipmentgs Package） | 1 |  |  | 1
|  | Fire Alarm System (For Load Centers) | 60 | 2025-02-20 | 2025-04-20 | 60 |  |  | 2025-04-01 | 2025-05-30
|  | CCTV Monitoring System | 30 | 2025-03-07 | 2025-04-05 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Energy Management System | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Telephone System | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | PA System | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Access Control System | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | Fiber Optic Cables / Ethernet Cable | 45 | 2025-02-20 | 2025-04-05 | 45 |  |  | 2025-05-01 | 2025-06-14
|  | Cable Trays Various Sizes | 45 | 2025-01-31 | 2025-03-16 | 45 |  |  | 2025-04-11 | 2025-05-25
|  | MV Power Cables | 80 | 2025-01-01 | 2025-03-21 | 150 | 2025-01-01 |  | 2025-01-01 | 2025-05-30
|  | LV Power Cables | 60 | 2025-02-04 | 2025-04-04 | 60 |  |  | 2025-04-15 | 2025-06-13
|  | Control And Signal Cables | 60 | 2025-02-11 | 2025-04-11 | 60 |  |  | 2025-04-22 | 2025-06-20
|  | Lighting Cable Various Sizes | 60 | 2025-02-20 | 2025-04-20 | 60 |  |  | 2025-05-01 | 2025-06-29
|  | Earthing Junction Box | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Earthing Electrode | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Earthing Flat / Wire - Different Sizes | 176 | 2024-08-28 | 2025-02-19 | 246 | 2024-08-28 |  | 2024-08-28 | 2025-04-30
|  | Outdoor Led Lamps/Fluorscent Led Lamp/Emergency Led Lamps With Battery Back-Up/Road / Street Lamps | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-04-01 | 2025-05-15
|  | High Mast | 78 | 2024-09-04 | 2024-11-20 | 78 | 2024-09-04 |  | 2024-09-04 | 2024-11-20
|  | Aviation And All Other Lighting Related Items | 45 | 2025-03-07 | 2025-04-20 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Cable Glands And Lugs, Termination Kits | 60 | 2025-02-20 | 2025-04-20 | 60 |  |  | 2025-05-01 | 2025-06-29
|  | Safety And PPE Equipment Exit Sign Boards | 30 | 2025-03-07 | 2025-04-05 | 30 |  |  | 2025-05-16 | 2025-06-14
|  | LV Motors | 77 | 2024-03-01 | 2024-05-16 | 77 | 2024-03-01 |  | 2024-03-01 | 2024-05-16
|  |  |  | 2024-09-25 | 2025-07-19 |  | 2024-09-25 | 2025-01-31 |  | 2025-09-27
Inspection | Offshore Equipment |  | 60 | 2025-03-07 | 2025-05-05 | 60 | 2024-10-23 |  | 2025-05-16 | 2025-07-14
Inspection | Onshore Equipment |  | 81 | 2025-03-22 | 2025-06-10 | 81 | 2024-11-05 |  | 2025-05-31 | 2025-08-19
Inspection | E & I Items (Onshore) |  | 123 | 2025-03-07 | 2025-07-07 | 123 | 2025-01-01 |  | 2025-05-16 | 2025-09-15
Delivery | Offshore Equipment |  | 253 | 2024-09-25 | 2025-06-04 | 323 | 2024-09-25 |  | 2024-09-25 | 2025-08-13
|  | Vertical Mill For Coal | 121 | 2024-11-01 | 2025-03-01 | 191 | 2024-11-01 |  | 2024-11-01 | 2025-05-10
|  | Roller Press | 102 | 2024-11-01 | 2025-02-10 | 172 | 2024-11-01 |  | 2024-11-01 | 2025-04-21
|  | Seperator | 111 | 2024-11-01 | 2025-02-19 | 181 | 2024-11-01 |  | 2024-11-01 | 2025-04-30
|  | Polyethyleue Liner | 64 | 2025-01-01 | 2025-03-05 | 134 | 2025-01-01 |  | 2025-01-01 | 2025-05-14
|  | Wearable Liner | 30 | 2025-02-11 | 2025-03-12 | 30 |  |  | 2025-04-22 | 2025-05-21
|  | Wear Resistant Ceramics Material | 60 | 2025-01-01 | 2025-03-01 | 130 | 2025-01-01 |  | 2025-01-01 | 2025-05-10
|  | MV Motor | 120 | 2024-10-23 | 2025-02-19 | 190 | 2024-10-23 |  | 2024-10-23 | 2025-04-30
|  | Metal Detector | 119 | 2024-10-24 | 2025-02-19 | 189 | 2024-10-24 |  | 2024-10-24 | 2025-04-30
|  | Metal Separator | 129 | 2024-10-24 | 2025-03-01 | 199 | 2024-10-24 |  | 2024-10-24 | 2025-05-10
|  | Sampler | 129 | 2024-10-24 | 2025-03-01 | 199 | 2024-10-24 |  | 2024-10-24 | 2025-05-10
|  | HT Sampler | 40 | 2025-02-11 | 2025-03-22 | 40 |  |  | 2025-04-22 | 2025-05-31
|  | Kiln | 92 | 2024-11-20 | 2025-02-19 | 162 | 2024-11-20 |  | 2024-11-20 | 2025-04-30
|  | Preheater (Diptube, Expansion Joint, Valves) | 158 | 2024-09-25 | 2025-03-01 | 228 | 2024-09-25 |  | 2024-09-25 | 2025-05-10
|  | Grate Cooler | 158 | 2024-09-25 | 2025-03-01 | 228 | 2024-09-25 |  | 2024-09-25 | 2025-05-10
|  | Burner | 132 | 2024-09-25 | 2025-02-03 | 202 | 2024-09-25 |  | 2024-09-25 | 2025-04-14
|  | Tertiary Duct/Kiln Hood | 1 |  |  | 1
|  | Process Valve/Non Standard Valve | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Explosion Valve | 1 |  |  | 1
|  | Motorized Actuator | 15 | 2025-01-01 | 2025-01-15 | 15 | 2025-01-01 | 2025-01-15 | 2025-01-01 | 2025-01-15
|  | Expansion Joint/Soft Joint | 74 | 2024-11-20 | 2025-02-01 | 144 | 2024-11-20 |  | 2024-11-20 | 2025-04-12
|  | Wear Resistant Bend | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Sinter Zone Refractory (Brick for Kiln) | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Other Refractory Brick | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Ceramic Fibre Plate | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Calcium Silicate | 15 | 2025-01-01 | 2025-01-15 | 15 | 2025-01-01 | 2025-01-15 | 2025-01-01 | 2025-01-15
|  | Other Refracotry Material（Anchor Etc.) | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Water Treatment System | 13 | 2025-01-02 | 2025-01-14 | 13 | 2025-01-02 | 2025-01-14 | 2025-01-02 | 2025-01-14
|  | Water Spraying System | 30 | 2024-12-02 | 2024-12-31 | 30 | 2024-12-02 | 2024-12-31 | 2024-12-02 | 2024-12-31
|  | Cooling Tower/Filter | 30 | 2024-12-02 | 2024-12-31 | 30 | 2024-12-02 | 2024-12-31 | 2024-12-02 | 2024-12-31
|  | Water Pump | 30 | 2025-02-04 | 2025-03-05 | 30 |  |  | 2025-04-15 | 2025-05-14
|  | Water Valve | 15 | 2025-03-27 | 2025-04-10 | 15 |  |  | 2025-06-05 | 2025-06-19
|  | Water Instrument | 30 | 2025-03-22 | 2025-04-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | Bucket Elevator (Silo Feeding And Kiln Feeding) | 72 | 2024-11-20 | 2025-01-30 | 142 | 2024-11-20 |  | 2024-11-20 | 2025-04-10
|  | Bucket Elevator (Others) | 97 | 2024-10-30 | 2025-02-03 | 167 | 2024-10-30 |  | 2024-10-30 | 2025-04-14
|  | Motorized Ball Valve | 92 | 2024-11-20 | 2025-02-19 | 162 | 2024-11-20 |  | 2024-11-20 | 2025-04-30
|  | Manhole/Measure Hole | 30 | 2025-03-25 | 2025-04-23 | 30 |  |  | 2025-06-03 | 2025-07-02
|  | Belt Conveyor | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | OLBC - Belt Conveyor | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Belt (If purchase seprately) | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Pan Conveyor (DPC) | 31 | 2024-12-01 | 2024-12-31 | 31 | 2024-12-01 | 2024-12-31 | 2024-12-01 | 2024-12-31
|  | Air Slide | 123 | 2024-10-30 | 2025-03-01 | 193 | 2024-10-30 |  | 2024-10-30 | 2025-05-10
|  | Screw Conveyor | 123 | 2024-10-30 | 2025-03-01 | 193 | 2024-10-30 |  | 2024-10-30 | 2025-05-10
|  | FU Conveyor (Chain Conveyor) | 123 | 2024-10-30 | 2025-03-01 | 193 | 2024-10-30 |  | 2024-10-30 | 2025-05-10
|  | Surface Feeder | 40 | 2025-02-20 | 2025-03-31 | 40 |  |  | 2025-05-01 | 2025-06-09
|  | Rotor-Feeder For Coal From European | 40 | 2025-01-31 | 2025-03-11 | 40 |  |  | 2025-04-11 | 2025-05-20
|  | Rotor-Feeder For Coal From China | 1 |  |  | 1
|  | Rotor-Feeder For Raw Meal From European | 40 | 2025-03-02 | 2025-04-10 | 40 |  |  | 2025-05-11 | 2025-06-19
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 30 | 2025-03-22 | 2025-04-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | Control Valve For Raw Meal Silo/Kiln Feeding System Valve | 62 | 2024-12-01 | 2025-01-31 | 62 | 2024-12-01 | 2025-01-31 | 2024-12-01 | 2025-01-31
|  | Wagon Bulk Loader | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Truck Bulk Loader | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Process Bag House | 60 | 2025-01-01 | 2025-03-01 | 130 | 2025-01-01 |  | 2025-01-01 | 2025-05-10
|  | ESP | 60 | 2025-01-01 | 2025-03-01 | 130 | 2025-01-01 |  | 2025-01-01 | 2025-05-10
|  | Roots Blower | 118 | 2024-10-30 | 2025-02-24 | 188 | 2024-10-30 |  | 2024-10-30 | 2025-05-05
|  | Air Compressor | 72 | 2024-11-20 | 2025-01-30 | 142 | 2024-11-20 |  | 2024-11-20 | 2025-04-10
|  | Air Dryer | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Air Tank | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Air Cannon | 113 | 2024-10-30 | 2025-02-19 | 183 | 2024-10-30 |  | 2024-10-30 | 2025-04-30
|  | Silencer | 1 |  |  | 1
Delivery | Onshore Equipment |  | 200 | 2025-01-01 | 2025-07-19 | 270 | 2025-01-01 |  | 2025-01-01 | 2025-09-27
|  | Limestone Crusher | 50 | 2025-01-01 | 2025-02-19 | 140 | 2025-01-01 |  | 2025-01-01 | 2025-05-20
|  | Sizer | 1 | 2025-03-11 | 2025-03-11 | 1 |  |  | 2025-05-20 | 2025-05-20
|  | X-Ray Analyzer | 1 |  |  | 1
|  | Online Cross Analyzer | 45 | 2025-04-06 | 2025-05-20 | 45 |  |  | 2025-06-15 | 2025-07-29
|  | Local Fabrication - Preheater | 1 |  |  | 1
|  | Local Fabrication - Kiln | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Local Fabrication - Cooler | 40 | 2025-02-01 | 2025-03-12 | 40 |  |  | 2025-04-12 | 2025-05-21
|  | Local Fabrication - Coal Mill | 44 | 2025-02-05 | 2025-03-20 | 44 |  |  | 2025-04-16 | 2025-05-29
|  | Local Fabrication - Bag House | 44 | 2025-02-10 | 2025-03-25 | 44 |  |  | 2025-04-21 | 2025-06-03
|  | Local Fabrication - Bucket Elvator | 44 | 2025-02-20 | 2025-04-04 | 44 |  |  | 2025-05-01 | 2025-06-13
|  | Local Fabrication - ESP | 44 | 2025-02-05 | 2025-03-20 | 44 |  |  | 2025-04-16 | 2025-05-29
|  | Other Refractory Brick | 44 | 2025-04-19 | 2025-06-01 | 44 |  |  | 2025-06-28 | 2025-08-10
|  | Pipes And Parts | 30 | 2025-04-06 | 2025-05-05 | 30 |  |  | 2025-06-15 | 2025-07-14
|  | Elevator | 1 |  |  | 1
|  | Castable | 60 | 2025-05-21 | 2025-07-19 | 60 |  |  | 2025-07-30 | 2025-09-27
|  | Stacker And Reclaimer | 1 | 2025-01-30 | 2025-01-30 | 1 |  |  | 2025-04-10 | 2025-04-10
|  | Belt Conveyor | 1 |  |  | 1
|  | Belt | 1 |  |  | 1
|  | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Load Cell | 30 | 2025-01-31 | 2025-03-01 | 30 |  |  | 2025-04-11 | 2025-05-10
|  | Weighing Bridge | 30 | 2025-01-21 | 2025-02-19 | 30 |  |  | 2025-04-01 | 2025-04-30
|  | Wagon Tippler | 1 | 2025-03-01 | 2025-03-01 | 1 |  |  | 2025-05-10 | 2025-05-10
|  | Truck Tippler | 1 | 2025-03-01 | 2025-03-01 | 1 |  |  | 2025-05-10 | 2025-05-10
|  | Nuisance Bag Filter | 40 | 2025-03-02 | 2025-04-10 | 40 |  |  | 2025-05-11 | 2025-06-19
|  | Grate Cooler Fan | 44 | 2025-02-20 | 2025-04-04 | 44 |  |  | 2025-05-01 | 2025-06-13
|  | Process Fan | 44 | 2025-02-20 | 2025-04-04 | 44 |  |  | 2025-05-01 | 2025-06-13
|  | Small Fan | 41 | 2025-05-26 | 2025-07-05 | 41 |  |  | 2025-08-04 | 2025-09-13
|  | Air Conditioner | 60 | 2025-05-11 | 2025-07-09 | 60 |  |  | 2025-07-20 | 2025-09-17
|  | Ventilation System | 1 |  |  | 1 |  |  | 2025-06-29 | 2025-06-29
|  | Insulation Material | 45 | 2025-05-21 | 2025-07-04 | 45 |  |  | 2025-07-30 | 2025-09-12
|  | Insulation Auxiliary Material (Steel Plate/Bolts Etc.) | 45 | 2025-05-21 | 2025-07-04 | 45 |  |  | 2025-07-30 | 2025-09-12
|  | Fire Equipment (Extinguisher/Outdoor Fire Hydrant) | 30 | 2025-02-05 | 2025-03-06 | 30 |  |  | 2025-04-16 | 2025-05-15
|  | Fire Fighting System (N2 Etc.) | 30 | 2025-02-05 | 2025-03-06 | 30 |  |  | 2025-04-16 | 2025-05-15
|  | Electrical Hoist | 45 | 2025-05-21 | 2025-07-04 | 45 |  |  | 2025-07-30 | 2025-09-12
|  | Double/Single Crane | 44 | 2025-03-02 | 2025-04-14 | 44 |  |  | 2025-05-11 | 2025-06-23
|  | Lubrication Oil | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
Delivery | E & I Items (Onshore) |  | 214 | 2024-11-30 | 2025-07-01 | 291 |  |  | 2024-11-30 | 2025-09-09
|  | MV Switchboards | 30 | 2025-05-21 | 2025-06-19 | 30 |  |  | 2025-07-30 | 2025-08-28
|  | MV Drives | 30 | 2025-05-21 | 2025-06-19 | 30 |  |  | 2025-07-30 | 2025-08-28
|  | LRS | 21 | 2025-05-21 | 2025-06-10 | 21 |  |  | 2025-07-30 | 2025-08-19
|  | MV Capacitors | 21 | 2025-03-07 | 2025-03-27 | 21 |  |  | 2025-05-16 | 2025-06-05
|  | Transformers - Power And Distribution | 21 | 2025-03-07 | 2025-03-27 | 21 |  |  | 2025-05-16 | 2025-06-05
|  | Lighting Power Transformer | 14 | 2025-06-04 | 2025-06-17 | 14 |  |  | 2025-08-13 | 2025-08-26
|  | LV Panels - PCC/ MCC / MLDB/ MPDB/ EPDB | 14 | 2025-05-03 | 2025-05-16 | 14 |  |  | 2025-06-30 | 2025-07-13
|  | LV Bus Duct | 12 | 2025-05-05 | 2025-05-16 | 12 |  |  | 2025-07-14 | 2025-07-25
|  | LV Capacitor Panels | 21 | 2025-03-12 | 2025-04-01 | 21 |  |  | 2025-05-21 | 2025-06-10
|  | SPDB (Sub Main Distribution Board) | 15 | 2025-04-01 | 2025-04-15 | 15 |  |  | 2025-06-10 | 2025-06-24
|  | LV Drives | 21 | 2025-04-21 | 2025-05-11 | 21 |  |  | 2025-06-30 | 2025-07-20
|  | UPS / UPS DB / DCS DB | 14 | 2025-04-21 | 2025-05-04 | 14 |  |  | 2025-06-30 | 2025-07-13
|  | Battery / Battery Charger | 14 | 2025-06-18 | 2025-07-01 | 14 |  |  | 2025-08-27 | 2025-09-09
|  | Switches / Sockets/ Single Phase Receptacle/ Welding Socket Outlet/ Exit Sign Boards | 15 | 2025-04-12 | 2025-04-26 | 15 |  |  | 2025-06-21 | 2025-07-05
|  | Local Push Buttons /Panic Stop Push Buttons/ VCS | 21 | 2025-03-28 | 2025-04-17 | 21 |  |  | 2025-06-06 | 2025-06-26
|  | Analog / Digital Junction Box Various Sizes 5TB To 200 TB | 21 | 2025-04-05 | 2025-04-25 | 21 |  |  | 2025-06-14 | 2025-07-04
|  | Magnetic Starter Panel/Power Junction Box | 14 | 2025-04-12 | 2025-04-25 | 14 |  |  | 2025-06-21 | 2025-07-04
|  | Hooter And Flasher | 21 | 2025-02-20 | 2025-03-12 | 21 |  |  | 2025-04-01 | 2025-04-21
|  | Ligthing SLD With Timer | 14 | 2025-03-13 | 2025-03-26 | 14 |  |  | 2025-05-22 | 2025-06-04
|  | AAQMS (Ambient Air Quality Monitoring System) | 21 | 2025-03-07 | 2025-03-27 | 21 |  |  | 2025-05-16 | 2025-06-05
|  | Dust Monitors | 21 | 2025-03-12 | 2025-04-01 | 21 |  |  | 2025-05-21 | 2025-06-10
|  | Temperature Transmitters | 21 | 2025-02-20 | 2025-03-12 | 21 |  |  | 2025-05-01 | 2025-05-21
|  | Pressure Transmitters / DP Transmitters | 14 | 2025-03-21 | 2025-04-03 | 14 |  |  | 2025-05-30 | 2025-06-12
|  | Radar Type Level Transmitter | 14 | 2025-03-21 | 2025-04-03 | 14 |  |  | 2025-05-30 | 2025-06-12
|  | Ultrasonic Level Transmitters | 14 | 2025-03-21 | 2025-04-03 | 14 |  |  | 2025-05-30 | 2025-06-12
|  | Hopper Level Switch | 14 | 2025-03-21 | 2025-04-03 | 14 |  |  | 2025-05-30 | 2025-06-12
|  | Vibration Transmitters | 14 | 2025-03-21 | 2025-04-03 | 14 |  |  | 2025-05-30 | 2025-06-12
|  | RTD / Thermocouple | 21 | 2025-03-21 | 2025-04-10 | 21 |  |  | 2025-05-30 | 2025-06-19
|  | Plant DCS / PLC System / DCS System / Control Desk / Computers / Servers | 30 | 2025-03-22 | 2025-04-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | Sub Control System Panel (Part Of Mechanical Equipmentgs Package） | 1 |  |  | 1
|  | Fire Alarm System (For Load Centers) | 30 | 2025-04-21 | 2025-05-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | CCTV Monitoring System | 30 | 2025-04-06 | 2025-05-05 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Energy Management System | 30 | 2025-04-21 | 2025-05-20 | 30 |  |  | 2025-06-30 | 2025-07-29
|  | Telephone System | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | PA System | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Access Control System | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | Fiber Optic Cables / Ethernet Cable | 30 | 2025-04-06 | 2025-05-05 | 30 |  |  | 2025-06-15 | 2025-07-14
|  | Cable Trays Various Sizes | 30 | 2025-03-17 | 2025-04-15 | 30 |  |  | 2025-05-26 | 2025-06-24
|  | MV Power Cables | 30 | 2025-03-22 | 2025-04-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | LV Power Cables | 21 | 2025-04-05 | 2025-04-25 | 21 |  |  | 2025-06-14 | 2025-07-04
|  | Control And Signal Cables | 21 | 2025-04-12 | 2025-05-02 | 21 |  |  | 2025-06-21 | 2025-07-11
|  | Lighting Cable Various Sizes | 21 | 2025-04-21 | 2025-05-11 | 21 |  |  | 2025-06-30 | 2025-07-20
|  | Earthing Junction Box | 30 | 2025-03-22 | 2025-04-20 | 30 |  |  | 2025-05-31 | 2025-06-29
|  | Earthing Electrode | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Earthing Flat / Wire - Different Sizes | 30 | 2025-02-20 | 2025-03-21 | 30 |  |  | 2025-05-01 | 2025-05-30
|  | Outdoor Led Lamps/Fluorscent Led Lamp/Emergency Led Lamps With Battery Back-Up/Road / Street Lamps | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-05-16 | 2025-06-29
|  | High Mast | 14 | 2024-12-01 | 2024-12-14 | 14 | 2024-12-01 | 2024-12-14 | 2024-12-01 | 2024-12-14
|  | Aviation And All Other Lighting Related Items | 45 | 2025-04-21 | 2025-06-04 | 45 |  |  | 2025-06-30 | 2025-08-13
|  | Cable Glands And Lugs, Termination Kits | 30 | 2025-04-21 | 2025-05-20 | 30 |  |  | 2025-06-30 | 2025-07-29
|  | Safety And PPE Equipment Exit Sign Boards | 30 | 2025-04-06 | 2025-05-05 | 30 |  |  | 2025-06-15 | 2025-07-14
|  | LV Motors | 44 | 2024-11-30 | 2025-01-12 | 44 |  |  | 2024-11-30 | 2025-01-12
|  |  | 614 | 2024-03-11 | 2025-11-15 | 357 | 2024-03-11 | 2025-03-03 |  | 2026-01-24
Construction | Excavation |  | 386 | 2024-03-11 | 2025-03-31 | 479 | 2024-03-11 |  | 2024-03-11 | 2025-07-02
|  | Limestone Crusher & Transport | 184 | 2024-09-01 | 2025-03-03 | 234 | 2024-09-01 |  | 2024-09-01 | 2025-04-22
|  | LimeStone Stockpile and Feeding | 135 | 2024-10-10 | 2025-02-21 | 194 | 2024-10-10 | 2025-03-03 | 2024-10-10 | 2025-04-21
|  | Raw Material Hopper | 34 | 2024-12-07 | 2025-01-09 | 34 | 2024-12-07 | 2025-01-09 | 2024-12-07 | 2025-01-09
|  | Raw Mill (Roller Press Building 1 & 2) | 38 | 2024-04-01 | 2024-05-08 | 38 | 2024-04-01 | 2024-05-08 | 2024-04-01 | 2024-05-08
|  | Raw Mill Bag House | 289 | 2024-04-29 | 2025-02-11 | 345 | 2024-04-29 | 2024-05-30 | 2024-04-29 | 2025-04-08
|  | Raw Meal Silo (Blending Silo) | 38 | 2024-03-11 | 2024-04-17 | 38 | 2024-03-11 | 2024-04-17 | 2024-03-11 | 2024-04-17
|  | PreHeater | 140 | 2024-03-16 | 2024-08-02 | 140 | 2024-03-16 | 2024-08-02 | 2024-03-16 | 2024-08-02
|  | Kiln | 41 | 2024-03-30 | 2024-05-09 | 41 | 2024-03-30 | 2024-05-09 | 2024-03-30 | 2024-05-09
|  | Clinker Cooler | 51 | 2024-05-10 | 2024-06-29 | 51 | 2024-05-10 | 2024-06-29 | 2024-05-10 | 2024-06-29
|  | Cooler ESP Building | 80 | 2024-05-10 | 2024-07-28 | 80 | 2024-05-10 | 2024-07-28 | 2024-05-10 | 2024-07-28
|  | Reject Silo | 156 | 2024-09-18 | 2025-02-20 | 226 | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2025-05-01
|  | Clinker Loading Silos (3S 01, 02) | 70 | 2025-01-21 | 2025-03-31 | 93 |  |  | 2025-04-01 | 2025-07-02
|  | Correctives Unloading and Transport | 36 | 2025-02-16 | 2025-03-23 | 36 |  |  | 2025-04-27 | 2025-06-01
|  | Correctives Storage and Transport | 184 | 2024-09-24 | 2025-03-26 | 282 | 2024-09-24 | 2025-01-01 | 2024-09-24 | 2025-07-02
|  | Receiving of Coal & Additives Transport | 54 | 2025-01-02 | 2025-02-24 | 121 | 2025-01-02 |  | 2025-01-02 | 2025-05-02
|  | Coal Reclaming and Transport | 70 | 2025-01-21 | 2025-03-31 | 90 |  |  | 2025-03-12 | 2025-06-09
|  | Fuel Grinding | -11 | 2024-04-12 | 2024-03-31 | 19 | 2024-04-12 | 2024-04-30 | 2024-04-12 | 2024-04-30
|  | LS Crusher Sub Station LC 31 | 23 | 2024-12-23 | 2025-01-14 | 23 | 2024-12-23 | 2025-01-14 | 2024-12-23 | 2025-01-14
|  | Raw Material Transport to Storage LC 32 | 15 | 2025-01-21 | 2025-02-04 | 15 |  |  | 2025-04-01 | 2025-04-15
|  | Raw Material Handling LC 33 | 10 | 2024-10-11 | 2024-10-20 | 10 |  |  | 2025-05-02 | 2025-05-11
|  | Clinker Cooler & Coal Mill LC 35 | 36 | 2024-10-07 | 2024-11-11 | 36 | 2024-10-07 | 2024-11-11 | 2024-10-07 | 2024-11-11
|  | Wagon Tippler & Coal Handling LC 36 | 22 | 2025-02-19 | 2025-03-12 | 22 |  |  | 2025-04-19 | 2025-05-10
|  | Corrective Handling LC 37 | 10 | 2025-01-21 | 2025-01-30 | 10 |  |  | 2025-04-01 | 2025-04-10
|  | Water Treatment & Fire Hydrant LC 38 | 11 | 2025-02-18 | 2025-02-28 | 11 | 2025-02-09 | 2025-02-19 | 2025-02-09 | 2025-02-19
|  | Clinker Silo LC 39 | 10 | 2025-02-14 | 2025-02-23 | 10 |  |  | 2025-04-25 | 2025-05-04
|  | Clinker Loading LC 39 A | 1 |  |  | 1
Construction | Civil construction (RCC Works) |  | 460 | 2024-06-14 | 2025-09-16 | 527 | 2024-06-14 |  | 2024-06-14 | 2025-11-22
|  | Limestone Crusher & Transport | 204 | 2024-12-19 | 2025-07-10 | 251 |  |  | 2025-01-11 | 2025-09-18
|  | LimeStone Stockpile and Feeding | 178 | 2024-12-08 | 2025-06-03 | 156 |  |  | 2025-02-17 | 2025-07-22
|  | Raw Material Hopper | 192 | 2025-01-23 | 2025-08-02 | 244 | 2025-01-20 |  | 2025-01-20 | 2025-09-20
|  | Raw Mill (Roller Press Building 1 & 2) | 386 | 2024-06-14 | 2025-07-04 | 432 | 2024-06-14 |  | 2024-06-14 | 2025-08-19
|  | Raw Mill Bag House | 266 | 2024-07-19 | 2025-04-10 | 326 | 2024-07-19 |  | 2024-07-19 | 2025-06-09
|  | Raw Meal Silo (Blending Silo) | 359 | 2024-07-31 | 2025-07-24 | 416 | 2024-07-31 |  | 2024-07-31 | 2025-09-19
|  | PreHeater | 434 | 2024-07-10 | 2025-09-16 | 501 | 2024-07-10 |  | 2024-07-10 | 2025-11-22
|  | Kiln | 232 | 2024-08-08 | 2025-03-27 | 303 | 2024-08-08 |  | 2024-08-08 | 2025-06-06
|  | Clinker Cooler | 281 | 2024-08-12 | 2025-05-19 | 305 | 2024-08-12 |  | 2024-08-12 | 2025-06-12
|  | Cooler ESP Building | 189 | 2024-09-24 | 2025-03-31 | 233 | 2024-09-24 |  | 2024-09-24 | 2025-05-14
|  | Reject Silo | 198 | 2024-10-14 | 2025-04-29 | 295 | 2024-10-14 |  | 2024-10-14 | 2025-08-04
|  | Clinker Loading Silos (3S 01, 02) | 155 | 2025-02-05 | 2025-07-09 | 155 |  |  | 2025-04-16 | 2025-09-17
|  | Correctives Unloading and Transport | 104 | 2025-02-21 | 2025-06-04 | 104 |  |  | 2025-05-02 | 2025-08-13
|  | Correctives Storage and Transport | 143 | 2025-01-08 | 2025-05-30 | 213 |  |  | 2025-01-08 | 2025-08-08
|  | Receiving of Coal & Additives Transport | 194 | 2025-02-05 | 2025-08-17 | 195 |  |  | 2025-04-12 | 2025-10-23
|  | Coal Reclaming and Transport | 153 | 2025-03-14 | 2025-08-13 | 154 |  |  | 2025-05-22 | 2025-10-22
|  | Fuel Grinding | 348 | 2024-08-04 | 2025-07-17 | 348 | 2024-08-04 |  | 2024-08-04 | 2025-07-17
|  | LS Crusher Sub Station LC 31 | 160 | 2025-01-23 | 2025-07-01 | 204 | 2025-01-24 |  | 2025-01-24 | 2025-08-15
|  | Raw Material Transport to Storage LC 32 | 178 | 2025-02-08 | 2025-08-04 | 178 |  |  | 2025-04-19 | 2025-10-13
|  | Raw Material Handling LC 33 | 173 | 2024-10-24 | 2025-04-14 | 173 |  |  | 2025-05-15 | 2025-11-03
|  | Clinker Cooler & Coal Mill LC 35 | 220 | 2024-11-01 | 2025-06-08 | 241 | 2024-11-01 |  | 2024-11-01 | 2025-06-29
|  | Wagon Tippler & Coal Handling LC 36 | 144 | 2025-03-14 | 2025-08-04 | 144 |  |  | 2025-05-12 | 2025-10-02
|  | Corrective Handling LC 37 | 125 | 2025-02-02 | 2025-06-06 | 125 |  |  | 2025-04-13 | 2025-08-15
|  | Water Treatment & Fire Hydrant LC 38 | 145 | 2025-03-02 | 2025-07-24 | 144 |  |  | 2025-04-03 | 2025-08-24
|  | Clinker Silo LC 39 | 144 | 2025-02-26 | 2025-07-19 | 144 |  |  | 2025-05-07 | 2025-09-27
Clinker Loading LC 39 A
|  | Compressed Air Station | 91 | 2025-05-21 | 2025-08-19 | 91 |  |  | 2025-07-30 | 2025-10-28
|  | WTP | 121 | 2025-04-11 | 2025-08-09 | 121 |  |  | 2025-06-20 | 2025-10-18
|  | Cable Gallery - Foundation | 91 | 2025-02-20 | 2025-05-21 | 91 |  |  | 2025-04-22 | 2025-07-21
Construction | Plate Fabrication |  | 298 | 2024-10-07 | 2025-07-31 | 368 | 2024-10-07 |  | 2024-10-07 | 2025-10-09
|  | Limestone Crusher & Transport | 46 | 2025-01-25 | 2025-03-11 | 46 |  |  | 2025-04-26 | 2025-06-10
|  | LimeStone Stockpile and Feeding | 16 | 2025-02-19 | 2025-03-06 | 16 |  |  | 2025-05-21 | 2025-06-05
|  | Raw Material Hopper | 75 | 2025-01-21 | 2025-04-05 | 75 |  |  | 2025-04-01 | 2025-06-14
|  | Raw Mill (Roller Press Building 1 & 2) | 183 | 2024-12-17 | 2025-06-17 | 235 | 2024-12-17 |  | 2024-12-17 | 2025-08-08
|  | Raw Mill Bag House | 112 | 2025-02-08 | 2025-05-30 | 113 |  |  | 2025-04-13 | 2025-08-03
|  | Raw Meal Silo (Blending Silo) | 90 | 2025-04-24 | 2025-07-22 | 91 |  |  | 2025-06-27 | 2025-09-25
|  | PreHeater | 296 | 2024-10-07 | 2025-07-29 | 336 | 2024-10-07 |  | 2024-10-07 | 2025-09-07
|  | Kiln | 44 | 2025-04-11 | 2025-05-24 | 44 |  |  | 2025-06-10 | 2025-07-23
|  | Clinker Cooler | 70 | 2025-02-22 | 2025-05-02 | 70 |  |  | 2025-05-03 | 2025-07-11
|  | Cooler ESP Building | 85 | 2025-02-22 | 2025-05-17 | 85 |  |  | 2025-05-03 | 2025-07-26
|  | Reject Silo | 30 | 2025-05-18 | 2025-06-16 | 30 |  |  | 2025-07-27 | 2025-08-25
|  | Clinker Loading Silos (3S 01, 02) | 45 | 2025-06-17 | 2025-07-31 | 45 |  |  | 2025-08-26 | 2025-10-09
|  | Correctives Unloading and Transport | 75 | 2025-05-04 | 2025-07-17 | 75 |  |  | 2025-07-13 | 2025-09-25
|  | Receiving of Coal & Additives Transport | 56 | 2025-04-22 | 2025-06-16 | 56 |  |  | 2025-05-30 | 2025-07-24
|  | Fuel Grinding | 167 | 2025-02-05 | 2025-07-21 | 183 |  |  | 2025-03-04 | 2025-09-02
Construction | Structural Fabrication |  | 364 | 2024-08-01 | 2025-07-30 | 434 | 2024-08-01 |  | 2024-08-01 | 2025-10-08
|  | Limestone Crusher & Transport | 153 | 2025-02-01 | 2025-07-03 | 157 |  |  | 2025-04-01 | 2025-09-04
|  | LimeStone Stockpile and Feeding | 25 | 2024-10-28 | 2024-11-21 | 25 |  |  | 2025-05-19 | 2025-06-12
|  | Raw Material Hopper | 90 | 2025-02-07 | 2025-05-07 | 90 |  |  | 2025-04-01 | 2025-06-29
|  | Raw Mill (Roller Press Building 1 & 2) | 160 | 2025-01-01 | 2025-06-09 | 167 |  |  | 2025-04-03 | 2025-09-16
|  | Raw Mill Bag House | 55 | 2025-02-08 | 2025-04-03 | 56 |  |  | 2025-05-17 | 2025-07-11
|  | Raw Meal Silo (Blending Silo) | 132 | 2025-01-29 | 2025-06-09 | 131 |  |  | 2025-04-01 | 2025-08-09
|  | PreHeater | 355 | 2024-08-01 | 2025-07-21 | 425 | 2024-08-01 |  | 2024-08-01 | 2025-09-29
|  | Kiln | 131 | 2024-12-12 | 2025-04-21 | 197 | 2024-12-12 |  | 2024-12-12 | 2025-06-26
|  | Clinker Cooler | 40 | 2025-04-26 | 2025-06-04 | 41 |  |  | 2025-06-21 | 2025-07-31
|  | Cooler ESP Building | 91 | 2025-03-03 | 2025-06-01 | 91 |  |  | 2025-05-12 | 2025-08-10
|  | Reject Silo | 115 | 2025-03-22 | 2025-07-14 | 115 |  |  | 2025-04-01 | 2025-07-24
|  | Clinker Loading Silos (3S 01, 02) | 100 | 2025-04-14 | 2025-07-22 | 100 |  |  | 2025-06-23 | 2025-09-30
|  | Correctives Unloading and Transport | 75 | 2025-05-04 | 2025-07-17 | 75 |  |  | 2025-07-13 | 2025-09-25
|  | Correctives Storage and Transport | 121 | 2025-04-01 | 2025-07-30 | 121 |  |  | 2025-06-10 | 2025-10-08
|  | Receiving of Coal & Additives Transport | 146 | 2025-03-06 | 2025-07-29 | 146 |  |  | 2025-05-04 | 2025-09-26
|  | Coal Reclaming and Transport | 126 | 2025-03-09 | 2025-07-12 | 126 |  |  | 2025-05-18 | 2025-09-20
|  | Fuel Grinding | 170 | 2025-01-21 | 2025-07-09 | 170 |  |  | 2025-04-01 | 2025-09-17
|  | Cable Gallery - Fabrication | 91 | 2025-04-21 | 2025-07-20 | 91 |  |  | 2025-06-21 | 2025-09-19
Construction | Structural Erection |  | 297 | 2025-01-01 | 2025-10-24 | 364 | 2025-01-01 |  | 2025-01-01 | 2025-12-30
|  | Limestone Crusher & Transport | 102 | 2025-04-15 | 2025-07-25 | 166 |  |  | 2025-04-21 | 2025-10-03
|  | LimeStone Stockpile and Feeding | 157 | 2025-02-10 | 2025-07-16 | 157 |  |  | 2025-06-13 | 2025-11-16
|  | Raw Material Hopper | 139 | 2025-04-11 | 2025-08-27 | 127 |  |  | 2025-06-11 | 2025-10-15
|  | Raw Mill (Roller Press Building 1 & 2) | 216 | 2025-02-04 | 2025-09-07 | 178 |  |  | 2025-04-29 | 2025-10-23
|  | Raw Mill Bag House | 165 | 2025-04-11 | 2025-09-22 | 169 |  |  | 2025-06-10 | 2025-11-25
|  | Raw Meal Silo (Blending Silo) | 73 | 2025-06-17 | 2025-08-28 | 73 |  |  | 2025-08-13 | 2025-10-24
|  | PreHeater | 277 | 2025-01-21 | 2025-10-24 | 333 | 2025-02-01 |  | 2025-02-01 | 2025-12-30
|  | Kiln | 231 | 2025-01-01 | 2025-08-19 | 255 | 2025-01-01 |  | 2025-01-01 | 2025-09-12
|  | Clinker Cooler | 77 | 2025-05-06 | 2025-07-21 | 78 |  |  | 2025-07-01 | 2025-09-16
|  | Cooler ESP Building | 102 | 2025-03-24 | 2025-07-03 | 102 |  |  | 2025-06-02 | 2025-09-11
|  | Reject Silo | 123 | 2025-04-13 | 2025-08-13 | 67 |  |  | 2025-07-19 | 2025-09-23
|  | Clinker Loading Silos (3S 01, 02) | 89 | 2025-05-27 | 2025-08-23 | 89 |  |  | 2025-08-05 | 2025-11-01
|  | Correctives Unloading and Transport | 147 | 2025-03-23 | 2025-08-16 | 147 |  |  | 2025-06-01 | 2025-10-25
|  | Correctives Storage and Transport | 157 | 2025-04-16 | 2025-09-19 | 150 |  |  | 2025-06-25 | 2025-11-21
|  | Receiving of Coal & Additives Transport | 75 | 2025-07-19 | 2025-10-01 | 76 |  |  | 2025-09-23 | 2025-12-07
|  | Coal Reclaming and Transport | 113 | 2025-04-23 | 2025-08-13 | 113 |  |  | 2025-07-02 | 2025-10-22
|  | Fuel Grinding | 235 | 2025-02-25 | 2025-10-17 | 205 |  |  | 2025-04-26 | 2025-11-16
|  | Cable Gallery - Erection | 90 | 2025-05-21 | 2025-08-18 | 90 |  |  | 2025-07-21 | 2025-10-18
Construction | Plate & Equipment Erection |  | 316 | 2024-12-30 | 2025-11-10 | 382 | 2024-12-30 |  | 2024-12-30 | 2026-01-15
|  | Limestone Crusher & Transport | 130 | 2025-04-22 | 2025-08-29 | 214 |  |  | 2025-04-08 | 2025-11-07
|  | LimeStone Stockpile and Feeding | 141 | 2025-03-16 | 2025-08-03 | 141 |  |  | 2025-07-17 | 2025-12-04
|  | Raw Material Hopper | 184 | 2025-04-11 | 2025-10-11 | 172 |  |  | 2025-06-11 | 2025-11-29
|  | Raw Mill (Roller Press Building 1 & 2) | 302 | 2024-12-30 | 2025-10-27 | 348 | 2024-12-30 |  | 2024-12-30 | 2025-12-12
|  | Raw Mill Bag House | 220 | 2025-04-05 | 2025-11-10 | 214 |  |  | 2025-06-14 | 2026-01-13
|  | Raw Meal Silo (Blending Silo) | 208 | 2025-03-24 | 2025-10-17 | 208 |  |  | 2025-05-20 | 2025-12-13
|  | PreHeater | 266 | 2025-02-07 | 2025-10-30 | 309 |  |  | 2025-03-03 | 2026-01-05
|  | Kiln | 182 | 2025-04-09 | 2025-10-07 | 298 | 2025-01-07 |  | 2025-01-07 | 2025-10-31
|  | Clinker Cooler | 229 | 2025-03-13 | 2025-10-27 | 230 |  |  | 2025-04-05 | 2025-11-20
|  | Cooler ESP Building | 172 | 2025-03-09 | 2025-08-27 | 199 |  |  | 2025-04-21 | 2025-11-05
|  | Reject Silo | 131 | 2025-05-10 | 2025-09-17 | 88 |  |  | 2025-08-02 | 2025-10-28
|  | Clinker Loading Silos (3S 01, 02) | 111 | 2025-06-20 | 2025-10-08 | 111 |  |  | 2025-08-29 | 2025-12-17
|  | Correctives Unloading and Transport | 127 | 2025-05-22 | 2025-09-25 | 127 |  |  | 2025-07-31 | 2025-12-04
|  | Correctives Storage and Transport | 216 | 2025-02-15 | 2025-09-18 | 219 |  |  | 2025-04-16 | 2025-11-20
|  | Receiving of Coal & Additives Transport | 130 | 2025-06-19 | 2025-10-26 | 131 |  |  | 2025-08-24 | 2026-01-01
|  | Coal Reclaming and Transport | 155 | 2025-06-03 | 2025-11-04 | 154 |  |  | 2025-08-12 | 2026-01-12
|  | Fuel Grinding | 250 | 2025-01-21 | 2025-09-27 | 201 |  |  | 2025-04-01 | 2025-10-18
|  | Compressed Air Station and Pipeline Erection | 60 | 2025-08-19 | 2025-10-17 | 60 |  |  | 2025-10-28 | 2025-12-26
|  | WTP Readiness with Water Pipeline Erection | 90 | 2025-08-09 | 2025-11-06 | 90 |  |  | 2025-10-18 | 2026-01-15
Construction | Refractory Works |  | 212 | 2025-04-11 | 2025-11-08 | 232 |  |  | 2025-05-31 | 2026-01-17
|  | PreHeater | 212 | 2025-04-11 | 2025-11-08 | 232 |  |  | 2025-05-31 | 2026-01-17
|  | Kiln | 20 | 2025-09-25 | 2025-10-14 | 20 |  |  | 2025-10-19 | 2025-11-07
|  | Clinker Cooler | 55 | 2025-08-12 | 2025-10-05 | 55 |  |  | 2025-10-04 | 2025-11-27
Construction | E & I works - Buildings |  | 176 | 2025-05-24 | 2025-11-15 | 188 |  |  | 2025-07-21 | 2026-01-24
|  | Limestone Crusher & Transport | 56 | 2025-07-16 | 2025-09-09 | 56 |  |  | 2025-09-24 | 2025-11-18
|  | LimeStone Stockpile and Feeding | 41 | 2025-07-20 | 2025-08-29 | 41 |  |  | 2025-11-20 | 2025-12-30
|  | Raw Material Hopper | 71 | 2025-08-03 | 2025-10-12 | 72 |  |  | 2025-09-20 | 2025-11-30
|  | Raw Mill (Roller Press Building 1 & 2) | 77 | 2025-08-29 | 2025-11-13 | 102 |  |  | 2025-10-13 | 2026-01-22
|  | Raw Mill Bag House | 93 | 2025-08-14 | 2025-11-14 | 99 |  |  | 2025-10-16 | 2026-01-22
|  | Raw Meal Silo (Blending Silo) | 76 | 2025-08-09 | 2025-10-23 | 76 |  |  | 2025-10-05 | 2025-12-19
|  | PreHeater | 176 | 2025-05-24 | 2025-11-15 | 188 |  |  | 2025-07-21 | 2026-01-24
|  | Kiln | 71 | 2025-09-04 | 2025-11-13 | 117 |  |  | 2025-09-28 | 2026-01-22
|  | Clinker Cooler | 137 | 2025-06-25 | 2025-11-08 | 107 |  |  | 2025-08-20 | 2025-12-04
|  | Cooler ESP Building | 84 | 2025-06-12 | 2025-09-03 | 84 |  |  | 2025-08-21 | 2025-11-12
|  | Reject Silo | 72 | 2025-07-15 | 2025-09-24 | 50 |  |  | 2025-09-24 | 2025-11-12
|  | Clinker Loading Silos (3S 01, 02) | 70 | 2025-07-22 | 2025-09-29 | 70 |  |  | 2025-09-30 | 2025-12-08
|  | Correctives Unloading and Transport | 42 | 2025-09-16 | 2025-10-27 | 42 |  |  | 2025-11-25 | 2026-01-05
|  | Correctives Storage and Transport | 33 | 2025-09-12 | 2025-10-14 | 34 |  |  | 2025-11-13 | 2025-12-16
|  | Receiving of Coal & Additives Transport | 66 | 2025-08-28 | 2025-11-01 | 67 |  |  | 2025-11-02 | 2026-01-07
|  | Coal Reclaming and Transport | 38 | 2025-10-08 | 2025-11-14 | 38 |  |  | 2025-12-17 | 2026-01-23
|  | Fuel Grinding | 157 | 2025-06-09 | 2025-11-12 | 251 |  |  | 2025-05-16 | 2026-01-21
Construction | E & I works - Substations |  | 273 | 2025-02-10 | 2025-11-09 | 282 |  |  | 2025-04-12 | 2026-01-18
|  | LS Crusher Sub Station LC 31 | 164 | 2025-04-11 | 2025-09-21 | 170 |  |  | 2025-05-31 | 2025-11-16
|  | Raw Material Transport to Storage LC 32 | 201 | 2025-04-11 | 2025-10-28 | 209 |  |  | 2025-06-12 | 2026-01-06
|  | Raw Material Handling LC 33 | 127 | 2025-04-11 | 2025-08-15 | 223 |  |  | 2025-06-09 | 2026-01-17
|  | Raw Mill and Pre Heater LC 34 | 186 | 2025-03-14 | 2025-09-15 | 196 |  |  | 2025-05-13 | 2025-11-24
|  | Raw Mill Hopper LC 34 A | 166 | 2025-04-11 | 2025-09-23 | 178 |  |  | 2025-05-31 | 2025-11-24
|  | Clinker Cooler & Coal Mill LC 35 | 143 | 2025-04-26 | 2025-09-15 | 163 |  |  | 2025-06-15 | 2025-11-24
|  | Wagon Tippler & Coal Handling LC 36 | 193 | 2025-04-26 | 2025-11-04 | 202 |  |  | 2025-06-15 | 2026-01-02
|  | Corrective Handling LC 37 | 157 | 2025-05-11 | 2025-10-14 | 162 |  |  | 2025-06-30 | 2025-12-08
|  | Water Treatment & Fire Hydrant LC 38 | 135 | 2025-05-11 | 2025-09-22 | 127 |  |  | 2025-06-30 | 2025-11-03
|  | Clinker Silo LC 39 | 163 | 2025-05-26 | 2025-11-04 | 183 |  |  | 2025-07-15 | 2026-01-13
|  | Clinker Loading LC 39 A | 1 |  |  | 1
|  | Transmission Line Readiness | 241 | 2025-02-10 | 2025-10-08 | 241 |  |  | 2025-04-12 | 2025-12-08
|  | Cable Laying Throught Plant | 182 | 2025-05-12 | 2025-11-09 | 182 |  |  | 2025-07-21 | 2026-01-18
Construction | E & I works - Substation Charging |  | 1 | 2025-11-07 | 2025-11-07 | 2 |  |  | 2026-01-16 | 2026-01-17
|  | LS Crusher Sub Station LC 31 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Raw Material Transport to Storage LC 32 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Raw Material Handling LC 33 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-17 | 2026-01-17
|  | Raw Mill and Pre Heater LC 34 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Raw Mill Hopper LC 34 A | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Clinker Cooler & Coal Mill LC 35 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Wagon Tippler & Coal Handling LC 36 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Corrective Handling LC 37 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Water Treatment & Fire Hydrant LC 38 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Clinker Silo LC 39 | 1 | 2025-11-07 | 2025-11-07 | 1 |  |  | 2026-01-16 | 2026-01-16
|  | Clinker Loading LC 39 A | 1 |  |  | 1
|  |  |  | 2025-11-06 | 2025-11-22 |  |  |  |  | 2026-01-31
Commissioning | No load Trials |  | 12 | 2025-11-06 | 2025-11-17 | 12 |  |  | 2026-01-15 | 2026-01-26
Commissioning | Group Trials |  | 11 | 2025-11-09 | 2025-11-19 | 11 |  |  | 2026-01-18 | 2026-01-28
Commissioning | Clinker Commissioning |  | 2 | 2025-11-21 | 2025-11-22 | 2 |  |  | 2026-01-30 | 2026-01-31
Commissioning | Commissioning With WT |  | 1 | 2025-11-13 | 2025-11-13 | 1 |  |  | 2026-01-22 | 2026-01-22
Formulas:
BL Start = MIN([BL Start, row below]:E558)
BL Finish = MAX([BL Finish, row below]:F558)
AL Start = MIN([AL Start, row below]:H558)
AL Finish = MAX([AL Finish, row below]:I558)
Expected Finish = MAX([Expected Finish, row below]:K558)

## Site Photograph
STRUCTURE NAME | LAST MONTH | CURRENT MONTH
Limestone Crusher & Transport
LimeStone Stockpile and Feeding
RMH
RM
RMBH
RM SILO
PreHeater
Kiln
COOLER
ESP
Reject Silo
Clinker Silos
Correctives Unloading and Transport
Correctives Storage and Transport
Receiving of Coal & Additives Transport
Coal Reclaming and Transport
Fuel Grinding
LS Crusher LC 21 | https://1drv.ms/i/c/5f17c22cd9dfa169/IQS2iltEIt_4RpGTbPKyPSkNAaeTnwUes_PFlBrpTv1C5VA?width=1024
Raw Material Transport to Storage LC 22
Raw Material Handling LC 23
Raw Mill and Pre Heater LC 24
Raw Mill Hopper LC 24 A
Clinker Cooler & Coal Mill LC 25
Wagon Trippler & Coal Handling LC 26
Corrective Handling LC 27
Water Treatment & Fire Hydrant LC 28
LC-23A MCC Room near TT3
Utility

## % data sheet
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | backlog | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date | Pading Left | Today
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 2024-03-02 | 2025-10-28 | -65 | 2026-01-01 | 74.11% | 162 | 2025-06-13
2024-02-01 | 0.07523% | 0.07523% | 0% | 0% | 0% | 0% | 0
2024-03-01 | 2.832% | 2.907% | 2.504% | 2.504% | 0% | 0% | 0
2024-04-01 | 1.356% | 4.263% | 2.47% | 4.974% | 0% | 0% | 0
2024-05-01 | 2.733% | 6.996% | 1.737% | 6.711% | 0% | 0% | 0
2024-06-01 | 2.333% | 9.328% | 1.908% | 8.619% | 0% | 0% | 0
2024-07-01 | 3.332% | 12.66% | 3.892% | 12.51% | 0% | 0% | 0
2024-08-01 | 4.729% | 17.39% | 2.108% | 14.62% | 0% | 0% | 0
2024-09-01 | 5.366% | 22.76% | 5.121% | 19.74% | 0% | 0% | 0
2024-10-01 | 6.619% | 29.37% | 3.111% | 22.85% | 0% | 0% | 0
2024-11-01 | 6.759% | 36.13% | 3.911% | 26.76% | 0% | 0% | 0
2024-12-01 | 6.87% | 43% | 3.487% | 30.25% | 0% | 0% | 0
2025-01-01 | 6.599% | 49.6% | 3.685% | 33.93% | 0% | 0% | 0
2025-02-01 | 6.67% | 56.27% | 4.752% | 38.69% | 0% | 0% | 0
2025-03-01 | 5.7% | 61.97% | 2.184% | 40.87% | 0% | 0% | 0
2025-04-01 | 5.873% | 67.85% | 3.514% | 44.38% | 0% | 44.38% | 0
2025-05-01 | 6.269% | 74.11% | 0.03875% | 44.42% | 7.698% | 52.08% | 0.014295
2025-06-01 | 6.036% | 80.15% | 0% | 0% | 7.962% | 60.04% | 0.019253
2025-07-01 | 5.914% | 86.06% | 0% | 0% | 7.146% | 67.19% | 0.012323
2025-08-01 | 4.351% | 90.42% | 0% | 0% | 5.279% | 72.47% | 0.0092764
2025-09-01 | 2.832% | 93.25% | 0% | 0% | 5.892% | 78.36% | 0.030595
2025-10-01 | 3.48% | 96.73% | 0% | 0% | 5.526% | 83.89% | 0.020454
2025-11-01 | 3.352% | 100.1% | 0% | 0% | 6.011% | 89.9% | 0.026588
2025-12-01 | 0% | 0% | 0% | 0% | 3.026% | 92.92% | 0.03026
2026-01-01 | 0% | 0% | 0% | 0% | 2.54% | 95.46% | 0.025397
2026-02-01 | 0% | 0% | 0% | 0% | 1.527% | 96.99% | 0.015266
2026-03-01 | 0% | 0% | 0% | 0% | 2.21% | 99.2% | 0.0221
2026-04-01 | 0% | 0% | 0% | 0% | 1.25% | 100.5% | 0.0125

## Ordering
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 2025-03-07 | 2025-07-07 | -70 | 2025-09-15 | 99.99%
2024-02-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-03-01 | 9.993% | 9.993% | 4.997% | 4.997% | 0% | 0%
2024-04-01 | 7.151% | 17.14% | 14.45% | 19.45% | 0% | 0%
2024-05-01 | 12.95% | 30.1% | 6.616% | 26.07% | 0% | 0%
2024-06-01 | 12% | 42.09% | 9.053% | 35.12% | 0% | 0%
2024-07-01 | 13.9% | 55.99% | 13.64% | 48.76% | 0% | 0%
2024-08-01 | 13.08% | 69.07% | 5.681% | 54.44% | 0% | 0%
2024-09-01 | 10.64% | 79.72% | 7.69% | 62.13% | 0% | 0%
2024-10-01 | 7.711% | 87.43% | 2.247% | 64.38% | 0% | 0%
2024-11-01 | 1.887% | 89.31% | 7.294% | 71.67% | 0% | 0%
2024-12-01 | 10.68% | 99.99% | 0.5357% | 72.21% | 0% | 0%
2025-01-01 | 0% | 99.99% | 1.211% | 73.42% | 0% | 0%
2025-02-01 | 0% | 99.99% | 0.8036% | 74.23% | 0% | 0%
2025-03-01 | 0% | 99.99% | 1.479% | 75.7% | 0% | 0%
2025-04-01 | 0% | 99.99% | 0% | 75.7% | 0% | 0%
2025-05-01 | 0% | 99.99% | 0% | 75.7% | 1.286% | 1.286%
2025-06-01 | 0% | 99.99% | 0% | 75.7% | 1.286% | 2.571%
2025-07-01 | 0% | 99.99% | 0% | 75.7% | 2.285% | 4.857%
2025-08-01 | 0% | 99.99% | 0% | 75.7% | 0% | 4.857%
2025-09-01 | 0% | 99.99% | 0% | 75.7% | 0% | 4.857%
2025-10-01 | 0% | 99.99% | 0% | 75.7% | 0% | 4.857%
2025-11-01 | 0% | 99.99% | 0% | 75.7% | 0% | 4.857%

## Enggineering
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 2024-03-03 | 2025-05-06 | -70 | 2025-07-15 | 100%
2024-02-01 | 0.5016% | 0.5016% | 0% | 0% | 0% | 0%
2024-03-01 | 4.47% | 4.972% | 5.909% | 5.909% | 0% | 0%
2024-04-01 | 1.657% | 6.629% | 2.892% | 8.801% | 0% | 0%
2024-05-01 | 7.567% | 14.2% | 3.127% | 11.93% | 0% | 0%
2024-06-01 | 6.338% | 20.53% | 5.241% | 17.17% | 0% | 0%
2024-07-01 | 7.306% | 27.84% | 11.96% | 29.13% | 0% | 0%
2024-08-01 | 11.32% | 39.16% | 4.978% | 34.11% | 0% | 0%
2024-09-01 | 11.23% | 50.39% | 9.769% | 43.88% | 0% | 0%
2024-10-01 | 17.35% | 67.74% | 5.99% | 49.87% | 0% | 0%
2024-11-01 | 16.26% | 84.01% | 7.908% | 57.77% | 0% | 0%
2024-12-01 | 10.94% | 94.95% | 13.16% | 70.94% | 0% | 0%
2025-01-01 | 3.23% | 98.18% | 7.901% | 78.84% | 0% | 0%
2025-02-01 | 1.843% | 100% | 6.808% | 85.64% | 0% | 0%
2025-03-01 | 0% | 100% | 3.144% | 88.79% | 0% | 0%
2025-04-01 | 0% | 100% | 5.091% | 93.88% | 0% | 0%
2025-05-01 | 0% | 100% | 0% | 93.88% | 0.4465% | 0.4465%
2025-06-01 | 0% | 100% | 0% | 93.88% | 0.2679% | 0.7144%
2025-07-01 | 0% | 100% | 0% | 93.88% | 0.1786% | 0.893%
2025-08-01 | 0% | 100% | 0% | 93.88% | 0% | 0.893%
2025-09-01 | 0% | 100% | 0% | 93.88% | 0% | 0.893%
2025-10-01 | 0% | 100% | 0% | 93.88% | 0% | 0.893%
2025-11-01 | 0% | 100% | 0% | 93.88% | 0% | 0.893%

## delivery
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 2024-09-25 | 2025-07-19 | -70 | 2025-09-27 | 86.94%
2024-02-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-03-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-04-01 | 0% | 0% | 0.01595% | 0.01595% | 0% | 0%
2024-05-01 | 0.1252% | 0.1252% | 0.05488% | 0.07083% | 0% | 0%
2024-06-01 | 0.1307% | 0.2559% | 0.04925% | 0.1201% | 0% | 0%
2024-07-01 | 0.1488% | 0.4048% | 0.6916% | 0.8117% | 0% | 0%
2024-08-01 | 3.488% | 3.893% | 0.5882% | 1.4% | 0% | 0%
2024-09-01 | 7.026% | 10.92% | 8.68% | 10.08% | 0% | 0%
2024-10-01 | 9.434% | 20.35% | 4.891% | 14.97% | 0% | 0%
2024-11-01 | 12.01% | 32.36% | 4.9% | 19.87% | 0% | 0%
2024-12-01 | 11.21% | 43.57% | 2.077% | 21.95% | 0% | 0%
2025-01-01 | 13.89% | 57.46% | 3.303% | 25.25% | 0% | 0%
2025-02-01 | 12.21% | 69.67% | 9.736% | 34.99% | 0% | 0%
2025-03-01 | 9.366% | 79.04% | 3.038% | 38.03% | 0% | 0%
2025-04-01 | 7.9% | 86.94% | 7.452% | 45.48% | 0% | 0%
2025-05-01 | 6.839% | 93.77% | 0% | 45.48% | 2.93% | 2.93%
2025-06-01 | 3.852% | 97.63% | 0% | 45.48% | 2.169% | 5.1%
2025-07-01 | 2.378% | 100% | 0% | 45.48% | 2.111% | 7.211%
2025-08-01 | 0% | 100% | 0% | 45.48% | 1.454% | 8.665%
2025-09-01 | 0% | 100% | 0% | 45.48% | 1.939% | 10.6%
2025-10-01 | 0% | 100% | 0% | 45.48% | 1.454% | 12.06%
2025-11-01 | 0% | 100% | 0% | 45.48% | 0.9693% | 13.03%
2025-12-02 | 0% | 100% | 0% | 45.48% | 0.9693% | 14%
2026-01-02 | 0% | 100% | 0% | 45.48% | 0.9693% | 14.96%
2026-02-02 | 0% | 100% | 0% | 45.48% | 0% | 14.96%
2026-03-05 | 0% | 100% | 0% | 45.48% | 0% | 14.96%
2026-04-05 | 0% | 100% | 0% | 45.48% | 0% | 14.96%

## Construction
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 2024-03-11 | 2025-11-15 | -70 | 2026-01-24 | 44.77%
2024-02-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-03-01 | 0.3011% | 0.3011% | 0.3676% | 0.3676% | 0% | 0%
2024-04-01 | 0.4474% | 0.7486% | 0.9% | 1.268% | 0% | 0%
2024-05-01 | 0.1654% | 0.914% | 0.7499% | 2.017% | 0% | 0%
2024-06-01 | 0.348% | 1.262% | 0.4761% | 2.494% | 0% | 0%
2024-07-01 | 1.384% | 2.646% | 1.303% | 3.797% | 0% | 0%
2024-08-01 | 1.645% | 4.29% | 1.503% | 5.3% | 0% | 0%
2024-09-01 | 1.838% | 6.128% | 1.503% | 6.803% | 0% | 0%
2024-10-01 | 2.062% | 8.19% | 1.78% | 8.582% | 0% | 0%
2024-11-01 | 2.628% | 10.82% | 1.792% | 10.37% | 0% | 0%
2024-12-01 | 3.157% | 13.98% | 2.187% | 12.56% | 0% | 0%
2025-01-01 | 6.143% | 20.12% | 3.448% | 16.01% | 0% | 0%
2025-02-01 | 7.771% | 27.89% | 2.828% | 18.84% | 0% | 0%
2025-03-01 | 7.811% | 35.7% | 1.873% | 20.71% | 0% | 0%
2025-04-01 | 9.065% | 44.77% | 2.064% | 22.77% | 0% | 0%
2025-05-01 | 10.44% | 55.2% | 0.09012% | 22.86% | 4.036% | 4.036%
2025-06-01 | 11.8% | 67% | 0% | 22.86% | 4.239% | 8.275%
2025-07-01 | 12.37% | 79.37% | 0% | 22.86% | 4.571% | 12.85%
2025-08-01 | 9.787% | 89.16% | 0% | 22.86% | 4.825% | 17.67%
2025-09-01 | 6.586% | 95.75% | 0% | 22.86% | 3.953% | 21.62%
2025-10-01 | 3.908% | 99.65% | 0% | 22.86% | 4.072% | 25.7%
2025-11-01 | 0.3535% | 100% | 0% | 22.86% | 3.042% | 28.74%
2025-12-02 | 0% | 100% | 0% | 22.86% | 2.057% | 30.79%
2026-01-02 | 0% | 100% | 0% | 22.86% | 1.82% | 32.61%
2026-02-02 | 0% | 100% | 0% | 22.86% | 0.3766% | 32.99%
2026-03-05 | 0% | 100% | 0% | 22.86% | 0.06% | 33.05%
2026-04-05 | 0% | 100% | 0% | 22.86% | 0.1% | 33.15%

## COMMISSIONING
Description | Month Plan | Cumulative Plan | Month Actual | Cumulative Actual | Month Forecast | Cumulative Forecast | BASELINE START | BASELINE FINISH | Delay | Expected Finish | Plan till date
2024-01-01 | 0% | 0% | 0% | 0% | 0% | 0% | 2025-11-06 | 2025-11-22 | -70 | 2026-01-31 | 0%
2024-02-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-03-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-04-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-05-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-06-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-07-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-08-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-09-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-10-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-11-01 | 0% | 0% | 0% | 0% | 0% | 0%
2024-12-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-01-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-02-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-03-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-04-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-05-01 | 0% | 0% | 0% | 0% | 0% | 0%
2025-06-01 | 8% | 8% | 0% | 0% | 0% | 0%
2025-07-01 | 23% | 31% | 0% | 0% | 0% | 0%
2025-08-01 | 19% | 50% | 0% | 0% | 0% | 0%
2025-09-01 | 50% | 100% | 0% | 0% | 0% | 0%
2025-10-01 | 0% | 100% | 0% | 0% | 0% | 0%
2025-11-01 | 0% | 100% | 0% | 0% | 0% | 0%
2025-12-02 | 0% | 100% | 0% | 0% | 0% | 0%
2026-01-02 | 0% | 100% | 0% | 0% | 0.75% | 0.75%
2026-02-02 | 0% | 100% | 0% | 0% | 2.15% | 2.9%
2026-03-05 | 0% | 100% | 0% | 0% | 2.15% | 5.05%
2026-04-05 | 0% | 100% | 0% | 0% | 2.15% | 7.2%

## Focus Area
Pages | Focus Area
Overall | 1. Drawing Approval by Director of Safety
Overall | 2. EC and CTE for Mines
Overall | 3. Insufficient manpower for Civil Works
Ordering | 1. Finailzation of Structure Fabrication workshop
Ordering | 2. Ordering of balance Mechnaical, E&I and Process Packages
Engineering
Delivery | 1. Delivery of Onshore and offshore material (Mechanical & E&I)
Delivery | 2. Delivery of Plate for site fabrication work
Construction | Wagon Tippler construction work ASAP

## Saftey data
P |  | 3 | 143 | 1469 | 0 | 0 | 11891 | 2192577
P | 663 | 1003 | 1000 | 1108 | 1217 | 1326 | 1454 | 1467 | 1544 | 1544
P | 20 | 80 | 150 | 200 | 250 | 350 | 576 | 643 | 1140 | 1140
P
P
A
A | 178 | 384 | 529 | 367 | 368 | 532 | 882 | 865 | 865 | 865
A | 9 | 11 | 29 | 29 | 29 | 44 | 44 | 289 | 314 | 314
A
A

## QA&QC
QAQC - NCR Summary
Descriptions | Total Issued | Closed | Open | 0-15 Days | 15-30 Days | 30-60 Days | 60-90 Days | 90-120 Days | >120 Days
Non-Conformity Reports | 12 | 9 | 3 |  | 3
Observations | 82 | 67 | 15 | 3 | 7 | 2 | 2 | 1

## Summary Qty
S No | Particulars | UOM | Scope | Drawing Released | Current Month Plan | Current Month Actual | Cumulative Planned | Cumulative completed | Balance
1 | Excavation | Nos | 192446.7 | 93451 | 0 | 1352 | 63537 | 181806 | 10640.7
2 | RCC | Cum | 94070.32 | 54084.519 | 6980 | 1989.14 | 50837 | 34288.1 | 59782.22
3 | Plate Fabrication | MT | 5073.6 | 4569 | 552 | 99.4 | 2215 | 819.3 | 4254.3
4 | Structure Fabrication | MT | 20905.3095 | 6211.73 | 0 | 0 | 4341.5932 | 4171.81 | 16733.4995
5 | Erection | MT | 42410.6745 | 14969 | 1288 | 465.4432 | 1609.921 | 2338.5289 | 40072.1456
6 | Cable Laying | RM
7 | Panels Erection | Nos
8 | Refractory | MT | [6 empty] | 0
9 | Drives Erection | Nos
10 | Drives Trial | Nos
11 | Group Trials | Nos

## RCC UPDATED SEP(3)
Items | UOM | Total Scope | Cumulative |  |  | 2025-04-01 |  |  | 3-months plan |  |  | Manpower – 24 |  |  |  | Original Target Compl’n | Revised Commitment | Remark / Reason for Slippage in preceding month, if any
|  |  | Plan till date (as per L5) | Actual till date | % | Monthly Plan | Monthly Plan | Actual | 2025-05-25 | 2025-06-26 | 2025-07-27 | Commitment / Reqd | 2025-04-01
[6 empty] | (As per L5) | (Forecast) | [5 empty] | Contractor Deployment | AAA Supply | Total
Equipment Ordering | Nos. | 146 | 146 | 105 | 71.92% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-11-30
Civil Excavation | m3 | 192446.7 | 192446.7 | 206587 | 107.3% | 0 | 15000 | 14140 | 0 | 0 | 0 | 40 | 30 | 0 | 30 | 2025-03-30
Civil (RCC+PCC) | m3 | 87100 | 59999 | 35199 | 58.67% | 9162 | 7296 | 2749 | 8103 | 7693 | 5381 | 1320 | 574 | 0 | 574 | 2025-10-30
Fabrication | MT | 5073.6 | 3848.94 | 912 | 23.69% | 685.161 | 553 | 183 | 594.271 | 326.022 | 304.367 | 315 | 135 |  | 135 | 2025-07-30
Structure (in china) | MT | 20905 | 10672 | 5237 | 49.07% | 0 |  | 0 | 4842 | 4842 | 45868 |  | 0 |  | 0 | 2025-07-30
Plate | MT | 5073.6 | 3848.94 | 912 | 23.69% | 685.161 | 553 | 183 | 594.271 | 326.022 | 304.367 | 315 | 135 |  | 135 | 2025-07-30
Erection | MT | 20905 | 4970 | 620 | 12.47% | 2541 | 0 | 84 | 3353 | 3495 | 3946 | 100 | 29 |  |  | 2025-08-30 |  |  | a
Structure | MT | 20905 | 4970 | 620 | 12.47% | 2541 | 395 | 84 | 3353 | 3495 | 3946 | 100 | 29 |  | 29 | 2025-08-30
Equipment & Plate Erection(M) | MT | 21505 | 4648 | 1856 | 39.93% | 1878 | 893 | 520 | 2257 | 3295 | 3778 | 300 | 108 | 0 | 108 | 2025-08-30
Equipment & Plate Erection | MT | 21505 | 4648 | 1856 | 39.93% | 1878 | 893 | 520 | 2257 | 3295 | 3778 | 300 | 108 |  | 108 | 2025-10-30
2790
Items | Total Scope | Actual till date
Civil (RCC+PCC) | 87100 | 35199 | 40.41%
Fabrication | 5073.6 | 912 | 17.98%
Structure | 20905 | 620 | 2.966%
Equipment & Plate Erection | 42410 | 2476 | 5.838%
Formulas:
Original Target Compl’n = '[2]RCC UPDATED SEP(2)'!Q11

## PPT-2
Description | UOM | 1st Cement |  |  |  | Monthly Progress |  | Manpower Mar-25 |  | 2025-04-25 | 2025-05-25 | 2025-06-25 | Committed Completion Date
|  | Scope | Actual | Actual | % | Mar-25 Plan | Mar-25 Actual | Plan | Actual
Equipment Ordering | Nos. | 146 | 91 | 105 | 71.92% | - | 0 | 0 | 0 |  |  |  | 2025-11-30
Civil Excavation | m3 | 182446.7 | 154776 | 206587 | 113.2% | 0 | 14140 | 40 | 30 | 0 | 0 | 0 | 2025-03-30
CIVIL RCC | m3 | 67540 | 33799 | 35199 | 52.12% | 9162 | 2749 | 1320 | 574 | 8103 | 7693 | 5381 | 2025-10-30
Fabrication | MT | 25979 | 6149 | 7478 | 28.78% | 2067.161 | 183 | 315 | 135 | 4241.271 | 5168.022 | 5146.367 | 2025-07-30
Structure | MT | 20905 | 5237 | 6566 | 31.41% | 1382 | 0 | 0 | 0 | 3647 | 4842 | 4842 | 2025-07-30
Plate | MT | 5074 | 912 | 912 | 17.97% | 685.161 | 183 | 315 | 135 | 594.271 | 326.022 | 304.367 | 2025-07-30
Erection | MT | 42410 | 2476 | 2476 | 5.838% | 4419 | 604 | 400 | 137 | 5610 | 6790 | 7724 | 2025-10-30
Structure | MT | 20905 | 620 | 620 | 2.966% | 2541 | 84 | 100 | 29 | 3353 | 3495 | 3946 | 2025-10-30
Equipment & Plate Erection | MT | 21505 | 1856 | 1856 | 8.631% | 1878 | 520 | 300 | 108 | 2257 | 3295 | 3778 | 2025-10-30
E&I | Km
Cable Tray | Km | 63 |  | 0 | 0%
Cable Laying | Km | 652 |  | 0 | 0%
Panels | Nos | 500 |  | 0 | 0%
Transformer | Nos | 21 |  | 0 | 0%
[8 empty] | 2075 | 876
|  | on+off |  | 6566 |  | 6566
28300

## CHART
Excavation | Description | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
| Month Plan | 0 | 0 | 12460 | 18513.5 | 6844.3 | 2534.1 | 1976.7 | 6229.4 | 12686.4486 | 10217.3286 | 21068.7586 | 12683.1486 | 28234.7752 | 44878.8552 | 14119.3852
| Cumm Plan | 0 | 0 | 12460 | 30973.5 | 37817.8 | 40351.9 | 42328.6 | 48558 | 61244.4486 | 71461.7771 | 92530.5357 | 105213.6843 | 133448.4595 | 178327.3148 | 192446.7
| Month Actual | 0 | 0 | 15210 | 37239 | 25723 | 7749 | 1962 | 739 | 3370 | 6264 | 17126 | 18849 | 33285 | 12938 | 11993 | 14140
| Cumm Actual | 0 | 0 | 15210 | 52449 | 78172 | 85921 | 87883 | 88622 | 91992 | 98256 | 115382 | 134231 | 167516 | 180454 | 192447 | 206587
PCC/RCC | Description | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-06-01 | 2025-07-01
| Month Plan | 716 | 3336 | 3730 | 3823 | 3638 | 4172 | 4627 | 8631 | 8648 | 9516 | 9162 | 8103 | 7693 | 5381 | 2821 | 1801 | 1302
| Cumm Plan | 716 | 4052 | 7782 | 11605 | 15243 | 19415 | 24042 | 32673 | 41321 | 50837 | 59999 | 68102 | 75795 | 81176 | 83997 | 85798 | 87100
| Month Actual | 2024-01-01: 721; 2024-02-01: 3136; 2024-03-01: 3707; 2024-04-01: 3549; 2024-05-01: 3905; 2024-06-01: 3189; 2024-07-01: 3239; 2024-08-01: 4254; 2024-09-01: 3294; 2024-10-01: 2911; 2024-11-01: 2749
| Cumm Actual | 2024-01-01: 1041; 2024-02-01: 4177; 2024-03-01: 7884; 2024-04-01: 11433; 2024-05-01: 15338; 2024-06-01: 18527; 2024-07-01: 21766; 2024-08-01: 26020; 2024-09-01: 29314; 2024-10-01: 32225; 2024-11-01: 34974
PLATE FABRICATION | Description | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
| Month Plan | 2024-01-01: 195.24; 2024-02-01: 244.05; 2024-03-01: 504.645; 2024-04-01: 715.668; 2024-05-01: 798.996; 2024-06-01: 705.18; 2024-07-01: 685.161; 2024-08-01: 594.271; 2024-09-01: 326.022; 2024-10-01: 304.367
| Cumm Plan | 2024-01-01: 195.24; 2024-02-01: 439.29; 2024-03-01: 943.935; 2024-04-01: 1659.603; 2024-05-01: 2458.599; 2024-06-01: 3163.779; 2024-07-01: 3848.94; 2024-08-01: 4443.211; 2024-09-01: 4769.233; 2024-10-01: 5073.6
| Month Actual | 2024-01-01: 35; 2024-02-01: 55; 2024-03-01: 75; 2024-04-01: 191; 2024-05-01: 236; 2024-06-01: 111; 2024-07-01: 183
| Cumm Actual | 2024-01-01: 35; 2024-02-01: 90; 2024-03-01: 165; 2024-04-01: 382; 2024-05-01: 618; 2024-06-01: 729; 2024-07-01: 912
STRUCTURE ERECTION | Description | 2024-01-01: 2025-01-01; 2024-02-01: 2025-02-01; 2024-03-01: 2025-03-01; 2024-04-01: 2025-04-01; 2024-05-01: 2025-05-01; 2024-06-01: 2025-06-01; 2024-07-01: 2025-07-01; 2024-08-01: 2025-08-01; 2024-09-01: 2025-09-01; 2024-10-01: 2025-10-01; 2024-11-01: 1899-12-31
| Month Plan | 2024-01-01: 363; 2024-02-01: 999; 2024-03-01: 1067; 2024-04-01: 2541; 2024-05-01: 3353; 2024-06-01: 3495; 2024-07-01: 3946; 2024-08-01: 2983; 2024-09-01: 1339; 2024-10-01: 819
| Cumm Plan | 2024-01-01: 363; 2024-02-01: 1362; 2024-03-01: 2429; 2024-04-01: 4970; 2024-05-01: 8323; 2024-06-01: 11818; 2024-07-01: 15764; 2024-08-01: 18747; 2024-09-01: 20086; 2024-10-01: 20905
| Month Actual | 2024-01-01: 0; 2024-02-01: 348; 2024-03-01: 185; 2024-04-01: 84
| Cumm Actual | 2024-01-01: 3; 2024-02-01: 351; 2024-03-01: 536; 2024-04-01: 620
P&E ERECTION | Description | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01
| Month Plan | 67 | 378 | 906 | 1419 | 1878 | 2257 | 3295 | 3778 | 3419 | 2442 | 1555 | 111
| Cumm Plan | 67 | 445 | 1351 | 2770 | 4648 | 6905 | 10200 | 13978 | 17397 | 19839 | 21394 | 21505
| Month Actual | 2024-12-01: 272; 2025-01-01: 545; 2025-02-01: 455; 2025-03-01: 64; 2025-04-01: 520
| Cumm Actual | 2024-12-01: 272; 2025-01-01: 817; 2025-02-01: 1272; 2025-03-01: 1336; 2025-04-01: 1856
| MONTH | 2024-12-01: PLAN; 2025-01-01: ACTUAL
| 2024-03-01 | 2024-12-01: 100; 2025-01-01: 22
| 2024-04-01 | 2024-12-01: 250; 2025-01-01: 62
| 2024-05-01 | 2024-12-01: 470; 2025-01-01: 86
| 2024-06-01 | 2024-12-01: 663; 2025-01-01: 144
| 2024-07-01 | 2024-12-01: 978; 2025-01-01: 346
| 2024-08-01 | 2024-12-01: 1128; 2025-01-01: 428
| 2024-09-01 | 2024-12-01: 1177; 2025-01-01: 780
| 2024-10-01 | 2024-12-01: 1774; 2025-01-01: 631
| 2024-11-01 | 2024-12-01: 2279; 2025-01-01: 708
| 2024-12-01 | 2024-12-01: 2453; 2025-01-01: 1006
| 2025-01-01 | 2024-12-01: 2560; 2025-01-01: 1056
| 2025-02-01 | 2024-12-01: 2680; 2025-01-01: 1140
| 2025-03-01 | 2024-12-01: 2830; 2025-01-01: 1029
| 2025-04-01 | 2024-12-01: 2390; 2025-01-01: 1016
| MONTH | 2024-12-01: PLAN; 2025-01-01: ACTUAL
| previous week | 2024-12-01: 15000; 2025-01-01: 13847
16000 | Week-1 | 2024-12-01: 3200; 2025-01-01: 2429
| Week-2 | 2024-12-01: 3200; 2025-01-01: 6193
| Week-3 | 2024-12-01: 3200; 2025-01-01: 3145
| Week-4 | 2024-12-01: 3200
| Week-5 | 2024-12-01: 3200
| Total | 2024-12-01: 16000; 2025-01-01: 11767
0
| MONTH | 2024-12-01: PLAN; 2025-01-01: ACTUAL
| previous week | 2024-12-01: 9516; 2025-01-01: 3136
7296 | Week-1 | 2024-12-01: 1459.2; 2025-01-01: 699; 2025-02-01: 20%
| Week-2 | 2024-12-01: 1824; 2025-01-01: 721; 2025-02-01: 25%
| Week-3 | 2024-12-01: 2188.8; 2025-01-01: 568; 2025-02-01: 30%
| Week-4 | 2024-12-01: 1094.4; 2025-02-01: 15%
| Week-5 | 2024-12-01: 729.6; 2025-02-01: 10%
| Total | 2024-12-01: 7296; 2025-01-01: 1988; 2025-02-01: 100%
0
568

## Exc
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance | 12460 | 18513.5 | 6844.3 | 2534.1 | 1976.7 | 6229.4 | 12686.4486 | 10217.3286 | 21068.7586 | 12683.1486 | 28234.7752 | 44878.8552 | 14119.3852
[7 empty] | 192446.7 |  | 184684 |  | 2024-03-11 | 2025-03-31 | [5 empty] | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31
1 | C | Civil | Construction | Excavation | Limestone Crusher & Transport | Cum | 19113.8 |  | 20162 |  | 2024-09-01 | 2025-03-03 |  |  |  |  | -1048.2 | 2024-09-30: 7645.52; 2024-11-30: 6689.83; 2025-02-28: 3822.76; 2025-03-31: 955.69 | 19113.8
2 | C | Civil | Construction | Excavation | LimeStone Stockpile and Feeding | Cum | 17657 |  | 36009 |  | 2024-10-10 | 2025-02-21 |  |  |  |  | -18352 | 2024-10-31: 3531.4; 2024-11-30: 8828.5; 2024-12-31: 3531.4; 2025-02-28: 1765.7 | 17657
3 | C | Civil | Construction | Excavation | Raw Material Hopper | Cum | 1425.8 |  | 4782 |  | 2024-12-07 | 2025-01-09 |  |  |  |  | -3356.2 | 2024-12-31: 570.32; 2025-01-31: 855.48 | 1425.8
4 | C | Civil | Construction | Excavation | Raw Mill (Roller Press Building 1 & 2) | Cum | 5152 |  | 18897 |  | 2024-04-01 | 2024-05-08 |  |  |  |  | -13745 | 2024-04-30: 3091.2; 2024-05-31: 2060.8 | 5152
5 | C | Civil | Construction | Excavation | Raw Mill Bag House | Cum | 2000 |  | 13326 |  | 2024-04-29 | 2025-02-11 |  |  |  |  | -11326 | 2024-04-30: 1600; 2025-02-28: 400 | 2000
6 | C | Civil | Construction | Excavation | Raw Meal Silo (Blending Silo) | Cum | 3183 |  | 5937 |  | 2024-03-11 | 2024-04-17 |  |  |  |  | -2754 | 2024-03-31: 1200; 2024-04-30: 1983 | 3183
7 | C | Civil | Construction | Excavation | PreHeater | Cum | 24772 |  | 20573 |  | 2024-03-16 | 2024-08-02 |  |  |  |  | 4199 | 2024-03-31: 9908.8; 2024-04-30: 9908.8; 2024-08-31: 4954.4 | 24772
8 | C | Civil | Construction | Excavation | Kiln | Cum | 1471 |  | 3710 |  | 2024-03-30 | 2024-05-09 |  |  |  |  | -2239 | 2024-04-30: 1029.7; 2024-05-31: 441.3 | 1471
9 | C | Civil | Construction | Excavation | Clinker Cooler | Cum | 3618.5 |  | 18140 |  | 2024-05-10 | 2024-06-29 |  |  |  |  | -14521.5 | 2024-05-31: 2532.95; 2024-06-30: 1085.55 | 3618.5
10 | C | Civil | Construction | Excavation | Cooler ESP Building | Cum | 3618.5 |  | 3619 |  | 2024-05-10 | 2024-07-28 |  |  |  |  | -0.5 | 2024-05-31: 1809.25; 2024-06-30: 1085.55; 2024-07-31: 723.7 | 3618.5
11 | C | Civil | Construction | Excavation | Reject Silo | Cum | 427 |  | 1804 |  | 2024-09-18 | 2025-02-20 |  |  |  |  | -1377 | 2024-09-30: 427 | 427
12 | C | Civil | Construction | Excavation | Clinker Loading Silos (3S 01, 02) | Cum | 2667 |  |  |  | 2025-01-21 | 2025-03-31 |  |  |  |  | 2667 | 2025-01-31: 889; 2025-02-28: 889; 2025-03-31: 889 | 2667
13 | C | Civil | Construction | Excavation | Correctives Unloading and Transport | Cum | 6108.5 |  | 6406 |  | 2025-02-16 | 2025-03-23 |  |  |  |  | -297.5 | 2025-02-28: 3665.1; 2025-03-31: 2443.4 | 6108.5
14 | C | Civil | Construction | Excavation | Correctives Storage and Transport | Cum | 5270.5 |  | 2652 |  | 2024-09-24 | 2025-03-26 |  |  |  |  | 2618.5 | 2024-09-30: 752.9286; 2024-10-31: 752.9286; 2024-11-30: 752.9286; 2024-12-31: 752.9286; 2025-01-31: 752.9286; 2025-02-28: 752.9286; 2025-03-31: 752.9286 | 5270.5
15 | C | Civil | Construction | Excavation | Receiving of Coal & Additives Transport | Cum | 40445 |  | 9964 |  | 2025-01-02 | 2025-02-24 |  |  |  |  | 30481 | 2025-01-31: 16178; 2025-02-28: 24267 | 40445
16 | C | Civil | Construction | Excavation | Coal Reclaming and Transport | Cum | 9161.6 |  |  |  | 2025-01-21 | 2025-03-31 |  |  |  |  | 9161.6 | 2025-01-31: 3053.8667; 2025-02-28: 3053.8667; 2025-03-31: 3053.8667 | 9161.6
17 | C | Civil | Construction | Excavation | Fuel Grinding | Cum | 2252 |  | 5662 |  | 2024-04-12 | 2024-03-31 |  |  |  |  | -3410 | 2024-03-31: 1351.2; 2024-04-30: 900.8 | 2252
18 | C | Civil | Construction | Excavation | LS Crusher Sub Station LC 31 | Cum | 617 |  | 3407 |  | 2024-12-23 | 2025-01-14 |  |  |  |  | -2790 | 2024-12-31: 617 | 617
19 | C | Civil | Construction | Excavation | Raw Material Transport to Storage LC 32 | Cum | 472 |  |  |  | 2025-01-21 | 2025-02-04 |  |  |  |  | 472 | 2025-01-31: 472 | 472
20 | C | Civil | Construction | Excavation | Raw Material Handling LC 33 | Cum | 474 |  |  |  | 2024-10-11 | 2024-10-20 |  |  |  |  | 474 | 2024-10-31: 474 | 474
21 | C | Civil | Construction | Excavation | Clinker Cooler & Coal Mill LC 35 | Cum | 1869 |  | 9024 |  | 2024-10-07 | 2024-11-11 |  |  |  |  | -7155 | 2024-10-31: 1869 | 1869
22 | C | Civil | Construction | Excavation | Wagon Tippler & Coal Handling LC 36 | Cum | 378 |  |  |  | 2025-02-19 | 2025-03-12 |  |  |  |  | 378 | 2025-03-31: 378 | 378
23 | C | Civil | Construction | Excavation | Corrective Handling LC 37 | Cum | 387 |  |  |  | 2025-01-21 | 2025-01-30 |  |  |  |  | 387 | 2025-01-31: 387 | 387
24 | C | Civil | Construction | Excavation | Water Treatment & Fire Hydrant LC 38 | Cum | 308 |  | 610 |  | 2025-02-18 | 2025-02-28 |  |  |  |  | -302 | 2025-02-28: 308 | 308
25 | C | Civil | Construction | Excavation | Clinker Silo LC 39 | Cum | 308 |  |  |  | 2025-02-14 | 2025-02-23 |  |  |  |  | 308 | 2025-02-28: 308 | 308
26 | C | Civil | Construction | Excavation | Clinker Loading LC 39 A | Cum | 196 | [9 empty] | 196 | 2024-08-31: 196 | 196
27 | C | Civil | Construction | Excavation | D33 - Compressed Air Station | Cum | 185 | [9 empty] | 185 | 2024-11-30: 185 | 185
28 | C | Civil | Construction | Excavation | 801 - Power cable routing | Cum | 4612.5 | [9 empty] | 4612.5 | 2024-11-30: 4612.5 | 4612.5
29 | C | Civil | Construction | Excavation | M32(1) - Combined Water Pump Station(1) | Cum | 3384 | [9 empty] | 3384 | 2024-09-30: 3384 | 3384
30 | C | Civil | Construction | Excavation | M32(2) - Combined Water Pump Station(2) | Cum | 477 | [9 empty] | 477 | 2024-09-30: 477 | 477
31 | C | Civil | Construction | Excavation | M53(1) - Fire Water Pump House(1) | Cum | 2514 | [9 empty] | 2514 | 2024-10-31: 2514 | 2514
32 | C | Civil | Construction | Excavation | M53(2) - Fire Water Pump House(2) | Cum | 1076 | [9 empty] | 1076 | 2024-10-31: 1076 | 1076
33 | C | Civil | Construction | Excavation | Process Water Piping System | Cum | 928 | [9 empty] | 928 | 2024-12-31: 928 | 928
34 | C | Civil | Construction | Excavation | N0 - Sewage Treatment Plant | Cum | 230 | [9 empty] | 230 | 2024-12-31: 230 | 230
35 | C | Civil | Construction | Excavation | D0 - General Plant Services | Cum | 407 | [9 empty] | 407 | 2024-12-31: 407 | 407
36 | C | Civil | Construction | Excavation | Roads & Drains | Cum | 22586 | [9 empty] | 22586 | 2024-12-31: 5646.5; 2025-01-31: 5646.5; 2025-02-28: 5646.5; 2025-03-31: 5646.5 | 22586
37 | C | Civil | Construction | Excavation | 301-3E1 - Raw Mil Hopper BLED ER. | Cum | 363 | [9 empty] | 363 | 2024-06-30: 363 | 363
38 | C | Civil | Construction | Excavation | 401-3E1 - Raw Mill & Preheater ER. | Cum | 1253 | [9 empty] | 1253 | 2024-07-31: 1253 | 1253
39 | C | Civil | Construction | Excavation | H0 - CCR | Cum | 1079 | [9 empty] | 1079 | 2024-08-31: 1079 | 1079
40 | C | Civil | Construction | Excavation | EarthWork & Leveling | Cum | 74688 | [9 empty] | 74688
[5 empty] | Total |  | 267134.7 | 0 | 184684 | [8 empty] | 12460 | 18513.5 | 6844.3 | 2534.1 | 1976.7 | 6229.4 | 12686.4486 | 10217.3286 | 21068.7586 | 12683.1486 | 28234.7752 | 44878.8552 | 14119.3852
[18 empty] | 12460 | 18514 | 6845 | 2534 | 1977 | 6229 | 12686 | 10217 | 21069 | 12683 | 28235 | 44879 | 14119

## RCC
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance
[7 empty] | 107988.02 |  |  |  | 2024-05-30 | 2025-05-27 | [5 empty] | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01
S No | C | Civil | Construction | Excavation | STRUCTURE NAME |  | SCOPE | [9 empty] | #VALUE! | 2025-04-01: 2025-04-01; 2025-05-01: 2025-05-01; 2025-06-01: 2025-06-01; 2025-07-01: 2025-07-01; 2025-08-01: 2025-08-01; 2025-09-01: 2025-09-01; 2025-10-01: 2025-10-01; 2025-11-01: 2025-11-01 | 0
1 | C | Civil | Construction | Excavation | Limestone Crusher & Transport |  | 7544.8 |  | 0 | 220 | 2024-05-30 | 2025-01-04 |  |  |  |  | 7544.8 | 2024-11-01: 150; 2024-12-01: 181; 2025-01-01: 655; 2025-02-01: 1019; 2025-03-01: 724; 2025-04-01: 885; 2025-05-01: 412; 2025-06-01: 473; 2025-07-01: 170; 2025-11-01: 1770 | 2021
2 | C | Civil | Construction | Excavation | LimeStone Stockpile and Feeding |  | 5983.7 |  | 0 | 127 | 2024-09-17 | 2025-01-21 |  |  |  |  | 5983.7 | 2024-10-01: 450; 2024-11-01: 500; 2024-12-01: 670; 2025-01-01: 1334; 2025-02-01: 1367; 2025-03-01: 990; 2025-04-01: 792; 2025-05-01: 618; 2025-06-01: 231; 2025-11-01: 1641 | 2400
3 | C | Civil | Construction | Excavation | Raw Material Hopper |  | 796.6 |  | 0 | 260 | 2024-07-05 | 2025-03-21 |  |  |  |  | 796.6 | 2024-12-01: 80; 2025-01-01: 198; 2025-02-01: 176; 2025-03-01: 166; 2025-04-01: 220; 2025-05-01: 199; 2025-06-01: 176; 2025-11-01: 595 | 585
4 | C | Civil | Construction | Excavation | Raw Mill (Roller Press Building 1 & 2) |  | 3780 |  | 2745 | 249 | 2024-06-01 | 2025-02-04 |  |  |  |  | 1035 |  |  |  | 716 | 390 | 638 | 1005 | 338 | 100 | 125 | 359 | 447 | 291 | 155 | 406 | 200 |  |  |  |  | 761 | 852
5 | C | Civil | Construction | Excavation | Raw Mill Bag House |  | 2246 |  | 799 | 182 | 2024-08-12 | 2025-02-09 |  |  |  |  | 1447 | 2024-08-01: 120; 2024-09-01: 120; 2024-10-01: 120; 2024-11-01: 103; 2024-12-01: 142; 2025-01-01: 100; 2025-02-01: 140; 2025-03-01: 549; 2025-04-01: 160; 2025-11-01: 160 | 709
6 | C | Civil | Construction | Excavation | Raw Meal Silo (Blending Silo) |  | 5648.8 |  | 2071 | 239 | 2024-06-03 | 2025-01-27 |  |  |  |  | 3577.8 |  |  |  |  | 1920 | 40 | 40 | 500 | 420 | 450 | 810 | 420 | 30 | 511 | 609 | 20 | 20 |  |  |  | 1140 | 1150
7 | C | Civil | Construction | Excavation | PreHeater |  | 9051.7 |  | 6026 | 331 | 2024-07-01 | 2025-05-27 |  |  |  |  | 3025.7 |  |  |  |  | 1026 | 1994 | 516 | 611 | 885 | 737 | 1074 | 150 | 130 | 30 | 332 | 321 | 280 | 280 |  |  | 683 | 492
8 | C | Civil | Construction | Excavation | Kiln |  | 2703.1 |  | 2008 | 100 | 2024-07-01 | 2024-10-08 |  |  |  |  | 695.1 | 2024-08-01: 540; 2024-09-01: 695; 2024-10-01: 260; 2024-11-01: 220; 2024-12-01: 15; 2025-11-01: 0 | 0
9 | C | Civil | Construction | Excavation | Clinker Cooler |  | 2107.8073 |  | 2702 | 244 | 2024-07-06 | 2025-03-06 |  |  |  |  | -594.1927 | 2024-08-01: 100; 2024-09-01: 470; 2024-10-01: 204; 2024-11-01: 448; 2024-12-01: 70; 2025-01-01: 550; 2025-02-01: 400; 2025-11-01: 0 | 0
10 | C | Civil | Construction | Excavation | Cooler ESP Building |  | 1670.4927 |  |  | 183 | 2024-08-03 | 2025-02-01 |  |  |  |  | 1670.4927 | 2024-10-01: 113; 2024-11-01: 233; 2024-12-01: 269; 2025-01-01: 230; 2025-02-01: 187; 2025-03-01: 55; 2025-11-01: 0 | 55
11 | C | Civil | Construction | Excavation | Reject Silo |  | 1655 |  | 315 | 137 | 2024-07-10 | 2024-11-23 |  |  |  |  | 1340 | 2024-10-01: 520; 2024-11-01: 45; 2024-12-01: 105; 2025-01-01: 479; 2025-04-01: 81; 2025-05-01: 127; 2025-11-01: 208 | 208
12 | C | Civil | Construction | Excavation | Clinker Loading Silos (3S 01, 02) |  | 3977.2 |  | 0 | 155 | 2024-07-16 | 2024-12-17 |  |  |  |  | 3977.2 | 2025-02-01: 125; 2025-03-01: 280; 2025-04-01: 807; 2025-05-01: 177; 2025-06-01: 821; 2025-07-01: 191; 2025-11-01: 1805 | 1264
13 | C | Civil | Construction | Excavation | Correctives Unloading and Transport |  | 1359.9666 |  | 0 | 100 | 2024-08-10 | 2024-11-17 |  |  |  |  | 1359.9666 | 2025-02-01: 605; 2025-03-01: 1200; 2025-04-01: 485; 2025-05-01: 203; 2025-11-01: 688 | 1888
14 | C | Civil | Construction | Excavation | Correctives Storage and Transport |  | 3717.6334 |  | 0 | 201 | 2024-07-31 | 2025-02-16 |  |  |  |  | 3717.6334 | 2025-01-01: 1200; 2025-02-01: 1440; 2025-03-01: 2805; 2025-04-01: 2464; 2025-05-01: 1145; 2025-11-01: 3609 | 6414
15 | C | Civil | Construction | Excavation | Receiving of Coal & Additives Transport |  | 5266.7 |  | 0 | 165 | 2024-11-25 | 2025-05-08 |  |  |  |  | 5266.7 | 2025-02-01: 850; 2025-03-01: 850; 2025-04-01: 508; 2025-05-01: 1174; 2025-06-01: 1220; 2025-07-01: 1500; 2025-08-01: 351; 2025-11-01: 2902 | 2532
16 | C | Civil | Construction | Excavation | Coal Reclaming and Transport |  | 4646.02 |  | 0 | 233 | 2024-07-29 | 2025-03-18 |  |  |  |  | 4646.02 | 2024-12-01: 627; 2025-01-01: 625; 2025-02-01: 742; 2025-03-01: 882; 2025-04-01: 971; 2025-05-01: 1538; 2025-06-01: 764; 2025-07-01: 392; 2025-08-01: 189; 2025-11-01: 3273 | 3391
17 | C | Civil | Construction | Excavation | Fuel Grinding |  | 2728.9 |  | 1592 | 275 | 2024-06-23 | 2025-03-24 |  |  |  |  | 1136.9 | [5 empty] | 228 | 802 | 62 | 144 | 441 | 81 | 196 | 130 | 213 | 125 | 44 | 16 |  |  |  | 382 | 468
18 | C | Civil | Construction | Excavation | LS Crusher Sub Station LC 21 |  | 673.1 |  |  | 156 | 2024-08-18 | 2025-01-20 |  |  |  |  | 673.1 | 2025-01-01: 131; 2025-02-01: 182; 2025-03-01: 230; 2025-04-01: 230; 2025-05-01: 0; 2025-06-01: 61; 2025-11-01: 291 | 460
19 | C | Civil | Construction | Excavation | Raw Material Transport to Storage LC 22 |  | 523.8 |  |  | 174 | 2024-09-23 | 2025-03-15 |  |  |  |  | 523.8 | 2025-02-01: 67; 2025-03-01: 159; 2025-04-01: 135; 2025-05-01: 22; 2025-06-01: 80; 2025-07-01: 48; 2025-11-01: 237 | 316
20 | C | Civil | Construction | Excavation | Raw Material Handling LC 23 |  | 524.7 |  |  | 174 | 2024-10-28 | 2025-04-19 |  |  |  |  | 524.7 | 2024-10-01: 60; 2024-11-01: 134; 2024-12-01: 135; 2025-01-01: 55; 2025-02-01: 80; 2025-06-01: 48; 2025-11-01: 48 | 0
21 | C | Civil | Construction | Excavation | Clinker Cooler & Coal Mill LC 25 |  | 1975.1 |  | 430 | 198 | 2024-08-25 | 2025-03-10 |  |  |  |  | 1545.1 | 2024-11-01: 320; 2024-12-01: 280; 2025-01-01: 320; 2025-04-01: 160; 2025-05-01: 320; 2025-06-01: 146; 2025-07-01: 144; 2025-11-01: 626 | 480
22 | C | Civil | Construction | Excavation | Wagon Tippler & Coal Handling LC 26 |  | 343.7 |  |  | 179 | 2024-11-09 | 2025-05-06 |  |  |  |  | 343.7 | 2025-04-01: 160; 2025-05-01: 160; 2025-06-01: 200; 2025-07-01: 216; 2025-11-01: 520 | 320
23 | C | Civil | Construction | Excavation | Corrective Handling LC 27 |  | 392.6 |  |  | 179 | 2024-09-04 | 2025-03-01 |  |  |  |  | 392.6 | 2024-08-01: 70; 2024-09-01: 175; 2024-10-01: 100; 2024-11-01: 170; 2025-06-01: 49; 2025-11-01: 49 | 0
24 | C | Civil | Construction | Excavation | Water Treatment & Fire Hydrant LC 28 |  | 298.1 |  |  | 179 | 2024-08-17 | 2025-02-11 |  |  |  |  | 298.1 | 2025-04-01: 120; 2025-05-01: 116; 2025-06-01: 90; 2025-07-01: 203; 2025-11-01: 326 | 236
25 | C | Civil | Construction | Excavation | Raw Mill Hopper LC 24 A |  | 298.1 |  |  | 179 | 2024-08-27 | 2025-02-21 |  |  |  |  | 298.1 | 2025-01-01: 130; 2025-02-01: 55; 2025-03-01: 45; 2025-04-01: 75; 2025-05-01: 120; 2025-06-01: 48; 2025-11-01: 243 | 240
26 | C | Civil | Construction | Excavation | LC-23A MCC Room near TT3 |  | 166.9 |  |  | 179 | 2024-08-27 | 2025-02-21 |  |  |  |  | 166.9 | 2025-11-01: 0 | 0
27 | C | Civil | Construction | Excavation | Compressed Air Station |  | 176.3 |  |  | 91 | 2025-01-19 | 2025-04-19 |  |  |  |  | 176.3 | 2025-11-01: 0 | 0
28 | C | Civil | Construction | Excavation | WTP |  | 1951.2 |  |  | 121 | 2024-10-13 | 2025-02-10 |  |  |  |  | 1951.2 | 2025-11-01: 0 | 0
29 | C | Civil | Construction | Excavation | Cable Gallery - Foundation |  | 1584.4 |  |  | 91 | 2024-12-31 | 2025-03-31 |  |  |  |  | 1584.4 | 2024-10-01: 300; 2024-11-01: 300; 2024-12-01: 300; 2025-01-01: 300; 2025-05-01: 300; 2025-11-01: 300 | 300
30 | C | Civil | Construction | Excavation | H0 - CCR |  | 1362.9 | [9 empty] | 1362.9 | 2025-11-01: 0 | 0
31 | C | Civil | Construction | Excavation | 401-3E1 - Raw mill & Preheater ER. |  | 1927.8 | [9 empty] | 1927.8 | 2025-11-01: 0 | 0
32 | C | Civil | Construction | Excavation | 301-3E1 - Raw Mil Hopper BLED ER. |  | 355 | [9 empty] | 355 | 2025-11-01: 0 | 0
33 | C | Civil | Construction | Excavation | D0 - General Plant Services |  | 6496.7 | [9 empty] | 6496.7 | 2025-11-01: 0 | 0
34 | C | Civil | Construction | Excavation | N0 - Sewage Treatment Plant |  | 64.2 | [9 empty] | 64.2 | 2025-11-01: 0 | 0
35 | C | Civil | Construction | Excavation | Roads & Drains |  | 10060.6 | [9 empty] | 10060.6 | 2025-06-01: 2701; 2025-07-01: 2201; 2025-08-01: 2001; 2025-09-01: 1801; 2025-10-01: 1302; 2025-11-01: 2701 | 0
| C | Civil | Construction | Excavation | [12 empty] | 0 | [21 empty] | 0 | bar: 2025-07-01
| C | Civil | Construction | Excavation | [34 empty] | 0 | bar: 2025-07-01
[5 empty] | Total |  | 87100 | [10 empty] | 0 | 0 | 0 | 716 | 3336 | 3730 | 3823 | 3638 | 4172 | 4627 | 8631 | 8648 | 9516 | 9162 | 8103 | 7693 | 5381 | 2821 | 1801 | 1302 | 24958
[21 empty] | 1159 | 4114 | 6923 | 6308 | 6648 | 7185 | 6440 | 6409 | 6627 | 6381 | 6807 | 6559 | 4310 | 3900 | 4500 | 4300 | 3500 | 2000
0
[7 empty] | -87100 | [13 empty] | -443 | -778 | -3193 | -2485 | -3010 | -3013 | -1813 | 2222 | 2021 | 3135 | 2355 | 1544 | 3383 | 1481 | -1679 | -2499 | -2198 | 22958
a

## BACKUP MSP (hidden)
2025-11-22 | Task Name | Duration | Baseline Duration | Baseline Start | Baseline Finish | % Complete | Start | Finish | DAYS | MONTH
5 | Limestone Crusher & Transport | 413 days | 404 days | 2024-04-02 | 2025-05-10 | 1% | 2024-09-01 | 2025-10-18 | 412 | 13.7333
| EXCAVATION | 30 days | 30 days | 2024-04-02 | 2024-05-01 |  | 2024-09-01 | 2024-12-27 | 117 | 3.9
| PCC+RCC | 5 days | 5 days | 2024-05-02 | 2024-05-06 |  | 2024-12-11 | 2025-06-16 | 187 | 6.2333
| Plate Fabrication | 61 days | 100 days | 2024-10-03 | 2025-01-10 | 0% | 2024-12-17 | 2025-02-15 | 60 | 2
| Structure Fabrication and Delivery to Site | 96 days | 160 days | 2024-09-12 | 2025-02-18 | 0% | 2025-04-12 | 2025-07-16 | 95 | 3.1667
| Structure Erection | 107 days | 170 days | 2024-10-02 | 2025-03-20 | 0% | 2025-05-02 | 2025-08-16 | 106 | 3.5333
| Plate and Equipment Erection | 149.1 days | 217 days | 2024-09-25 | 2025-04-29 | 0% | 2025-04-28 | 2025-09-24 | 149 | 4.9667
| Electrical and Instumentation | 88 days | 76 days | 2025-02-24 | 2025-05-10 | 0% | 2025-07-23 | 2025-10-18 | 87 | 2.9
2025-11-22 | Task Name | Duration | Baseline Duration | Baseline Start | Baseline Finish | % Complete | Start | Finish | DAYS | MONTH
-63 | LimeStone Stockpile and Feeding | 387 days | 381 days | 2024-08-23 | 2025-09-07 | 0% | 2024-12-04 | 2025-12-25 | 386 | 12.8667 | Start | Finish
| EXCAVATION | 30 days | 30 days | 2024-04-02 | 2024-05-01 |  | 2024-12-04 | 2024-12-27 | 23 | 0.76667 | 2024-12-04 | 2024-12-27
| PCC+RCC | 5 days | 5 days | 2024-05-02 | 2024-05-06 |  | 2024-12-27 | 2025-05-12 | 136 | 4.5333
| Plate Fabrication | 15 days | 15 days | 2024-12-12 | 2024-12-26 | 0% | 2024-12-17 | 2024-12-31 | 14 | 0.46667 |  | 2025-05-12
| Structure Fabrication and Delivery to Site | 45 days | 45 days | 2024-11-27 | 2025-01-10 | 0% | 2025-02-06 | 2025-03-22 | 44 | 1.4667
| Structure Erection | 198.8 days | 97 days | 2025-01-01 | 2025-04-07 | 0% | 2025-03-13 | 2025-09-27 | 198 | 6.6
| Plate and Equipment Erection | 230.2 days | 211 days | 2024-12-08 | 2025-07-06 | 0% | 2025-03-13 | 2025-10-29 | 230 | 7.6667
| Electrical and Instumentation | 107.8 days | 47 days | 2025-07-23 | 2025-09-07 | 0% | 2025-09-09 | 2025-12-25 | 107 | 3.5667
| Task Name | Duration | Baseline Duration | Baseline Start | Baseline Finish | % Complete | Start | Finish | DAYS | MONTH
| Raw Material Hopper | 355.8 days | 349 days | 2024-06-24 | 2025-06-07 | 0% | 2024-12-07 | 2025-11-27 | 355 | 11.8333
| EXCAVATION | [5 empty] | 2024-12-07 | 2025-01-02 | 232 | 7.7333 | Start | Finish
| PCC+RCC | 277.8 days | 271 days | 2024-06-24 | 2025-03-21 | 1% | 2025-01-02 | 2025-08-22 | 79 | 2.6333 | 2024-12-07 | 2025-01-02
| Plate Fabrication | 80 days | 80 days | 2024-10-15 | 2025-01-02 | 0% | 2024-12-17 | 2025-03-06 | 157 | 5.2333 | 2025-01-02
| Structure Fabrication and Delivery to Site | 158 days | 140 days | 2024-07-24 | 2024-12-10 | 0% | 2024-12-17 | 2025-05-23 | 177 | 5.9
| Structure Erection | 177 days | 177 days | 2024-11-29 | 2025-05-24 | 0% | 2025-05-20 | 2025-11-13 | 180 | 6
| Plate and Equipment Erection | 180 days | 180 days | 2024-11-29 | 2025-05-27 | 0% | 2025-05-20 | 2025-11-16 | 51 | 1.7
| Electrical and Instumentation | 51 days | 51 days | 2025-04-18 | 2025-06-07 | 0% | 2025-10-07 | 2025-11-27 | 0 | 0

## PLATE FAB
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance
S No |  |  |  |  | Sections |  | Scope |  |  | Duration | BL Start | BL Finish | [5 empty] | 0 | 0 | 195.24 | 244.05 | 504.645 | 715.668 | 798.996 | 705.18 | 685.161 | 594.271 | 326.022 | 304.367
S No |  |  |  |  | STRUCTURE NAME |  | SCOPE |  |  |  | 2024-08-23 | 2025-03-24 | [5 empty] | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
1 |  |  |  |  | Limestone Crusher & Transport |  | 102 |  |  | 100 | 2024-10-03 | 2025-01-10 | [5 empty] | 2025-01-01: 40.8; 2025-02-01: 32.64; 2025-03-01: 28.56 | 0
2 |  |  |  |  | LimeStone Stockpile and Feeding |  | 19.2 |  |  | 15 | 2024-12-12 | 2024-12-26 | [5 empty] | 2025-02-01: 10.56; 2025-03-01: 8.64 | 0
3 |  |  |  |  | Raw Material Hopper |  | 168 |  |  | 80 | 2024-10-15 | 2025-01-02 | [5 empty] | 2025-01-01: 47.04; 2025-02-01: 43.68; 2025-03-01: 40.32; 2025-04-01: 36.96 | 36.96
4 |  |  |  |  | Raw Mill (Roller Press Building 1 & 2) |  | 1249.2 |  |  | 121 | 2024-09-13 | 2025-01-11 | [5 empty] | 2024-12-01: 187.38; 2025-01-01: 237.348; 2025-02-01: 262.332; 2025-03-01: 199.872; 2025-04-01: 149.904; 2025-05-01: 124.92; 2025-06-01: 87.444 | 362.268
5 |  |  |  |  | Raw Mill Bag House |  |  |  |  | 60 | 2024-09-13 | 2024-11-11 | [17 empty] | 0
6 |  |  |  |  | Raw Meal Silo (Blending Silo) |  | 15 |  |  | 90 | 2024-08-23 | 2024-11-20 | [5 empty] | 2025-04-01: 15 | 15
7 |  |  |  |  | PreHeater |  | 2440.5 |  |  | 121 | 2024-09-10 | 2025-01-08 | [7 empty] | 195.24 | 244.05 | 317.265 | 390.48 | 341.67 | 292.86 | 219.645 | 170.835 | 146.43 | 122.025 | 536.91
8 |  |  |  |  | Kiln |  | 234.5 |  |  | 10 | 2024-08-23 | 2024-09-01 | [5 empty] | 2025-04-01: 105.525; 2025-05-01: 128.975 | 234.5
9 |  |  |  |  | Clinker Cooler |  | 336 |  |  | 70 | 2024-09-08 | 2024-11-16 | [5 empty] | 2025-02-01: 47.04; 2025-03-01: 80.64; 2025-04-01: 114.24; 2025-05-01: 94.08 | 208.32
10 |  |  |  |  | Cooler ESP Building |  |  |  |  | 65 | 2024-09-08 | 2024-11-11 | [17 empty] | 0
11 |  |  |  |  | Reject Silo |  | 22 |  |  | 30 | 2024-10-06 | 2024-11-04 | [5 empty] | 2025-05-01: 9.9; 2025-06-01: 12.1 | 22
12 |  |  |  |  | Clinker Loading Silos (3S 01, 02) |  | 18 |  |  | 70 | 2024-08-29 | 2024-11-06 | [5 empty] | 2025-06-01: 8.1; 2025-07-01: 9.9 | 0
13 |  |  |  |  | Correctives Unloading and Transport |  | 83 |  |  | 45 | 2024-10-10 | 2024-11-23 | [5 empty] | 2025-05-01: 24.9; 2025-06-01: 37.35; 2025-07-01: 20.75 | 62.25
14 |  |  |  |  | Receiving of Coal & Additives Transport |  | 44.5 |  |  | 55 | 2025-01-29 | 2025-03-24 | [5 empty] | 2025-04-01: 13.35; 2025-05-01: 16.91; 2025-06-01: 14.24 | 44.5
15 |  |  |  |  | Fuel Grinding |  | 339.3 |  |  | 155 | 2024-09-20 | 2025-02-21 | [5 empty] | 2025-02-01: 61.074; 2025-03-01: 54.288; 2025-04-01: 30.537; 2025-05-01: 23.751; 2025-06-01: 20.358; 2025-07-01: 149.292 | 74.646
16 |  |  |  |  | D33 - Compressed Air Station |  | 2.4 | [10 empty] | 2025-07-01: 2.4 | 0
[5 empty] | Total |  | 5076 | [10 empty] | 0 | 0 | 195.24 | 244.05 | 504.645 | 715.668 | 798.996 | 705.18 | 685.161 | 594.271 | 326.022 | 304.367

## Str Fab
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance | 0 | 40 | 80 | 1509.4608 | 1343.6148 | 342.6857 | 695.3436 | 1382.3772 | 2331.2919 | 3646.8705 | 4842.2185 | 3000.6384 | 1690.8082 |  | 4238.724 |  | 0
[7 empty] | 20905.3095 |  |  |  | 2024-08-01 | 2025-07-30 | [5 empty] | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31
1 |  |  |  |  | Limestone Crusher & Transport |  | 2222.1842 |  |  | 153 | 2025-02-01 | 2025-07-03 | [5 empty] | 2025-02-28: 399.9932; 2025-03-31: 444.4368; 2025-04-30: 488.8805; 2025-05-31: 377.7713; 2025-06-30: 288.8839; 2025-07-31: 222.2184 |  | 0 |  | 0 | 1311.0887
2 |  |  |  |  | LimeStone Stockpile and Feeding |  | 2573.0756 |  |  | 25 | 2024-10-28 | 2024-11-21 | [5 empty] | 2024-10-31: 1389.4608; 2024-11-30: 1183.6148 |  | 2573.0756 |  | 0 | 0
3 |  |  |  |  | Raw Material Hopper |  | 701.6303 |  |  | 90 | 2025-02-07 | 2025-05-07 | [5 empty] | 2025-02-28: 140.3261; 2025-03-31: 161.375; 2025-04-30: 210.4891; 2025-05-31: 189.4402 |  | 0 |  | 0 | 561.3042
4 |  |  |  |  | Raw Mill (Roller Press Building 1 & 2) |  | 966.0899 |  |  | 160 | 2025-01-01 | 2025-06-09 | [5 empty] | 2025-01-31: 125.5917; 2025-02-28: 202.8789; 2025-03-31: 251.1834; 2025-04-30: 212.5398; 2025-05-31: 125.5917; 2025-06-30: 48.3045 |  | 125.5917 |  | 0 | 589.3148
5 |  |  |  |  | Raw Mill Bag House |  |  |  |  | 55 | 2025-02-08 | 2025-04-03 | [19 empty] | 0 |  | 0 | 0
6 |  |  |  |  | Raw Meal Silo (Blending Silo) |  | 163.3662 |  |  | 132 | 2025-01-29 | 2025-06-09 | [5 empty] | 2025-01-31: 32.6732; 2025-04-30: 71.8811; 2025-06-30: 58.8118 |  | 32.6732 |  | 0 | 71.8811
7 |  |  |  |  | PreHeater |  | 4025.5819 |  |  | 355 | 2024-08-01 | 2025-07-21 | [6 empty] | 40 | 80 | 120 | 160 | 322.0466 | 483.0698 | 563.5815 | 724.6047 | 563.5815 | 442.814 | 322.0466 | 203.8373 |  | 1205.1164 |  | 0 | 1731.0002
8 |  |  |  |  | Kiln |  | 103.1959 |  |  | 131 | 2024-12-12 | 2025-04-21 | [5 empty] | 2024-12-31: 20.6392; 2025-01-31: 30.9588; 2025-02-28: 23.7351; 2025-03-31: 17.5433; 2025-04-30: 10.3196 |  | 51.5979 |  | 0 | 27.8629
9 |  |  |  |  | Clinker Cooler |  | 459.3082 |  |  | 40 | 2025-04-26 | 2025-06-04 | [5 empty] | 2025-04-30: 68.8962; 2025-05-31: 252.6195; 2025-06-30: 137.7924 |  | 0 |  | 0 | 321.5157
10 |  |  |  |  | Cooler ESP Building |  |  |  |  | 91 | 2025-03-03 | 2025-06-01 | [19 empty] | 0 |  | 0 | 0
11 |  |  |  |  | Reject Silo |  | 108.5416 |  |  | 115 | 2025-03-22 | 2025-07-14 | [5 empty] | 2025-03-31: 15.1958; 2025-04-30: 23.8792; 2025-05-31: 37.9896; 2025-06-30: 18.4521; 2025-07-31: 13.025 |  | 0 |  | 0 | 77.0645
12 |  |  |  |  | Clinker Loading Silos (3S 01, 02) |  | 233.1415 |  |  | 100 | 2025-04-14 | 2025-07-22 | [5 empty] | 2025-04-30: 55.954; 2025-05-31: 86.2624; 2025-06-30: 62.9482; 2025-07-31: 27.977 |  | 0 |  | 0 | 142.2163
13 |  |  |  |  | Correctives Unloading and Transport |  | 741.6117 |  |  | 75 | 2025-05-04 | 2025-07-17 | [5 empty] | 2025-05-31: 244.7319; 2025-06-30: 274.3963; 2025-07-31: 222.4835 |  | 0 |  | 0 | 244.7319
14 |  |  |  |  | Correctives Storage and Transport |  | 1606.9216 |  |  | 121 | 2025-04-01 | 2025-07-30 | [5 empty] | 2025-04-30: 385.6612; 2025-05-31: 594.561; 2025-06-30: 433.8688; 2025-07-31: 192.8306 |  | 0 |  | 0 | 980.2222
15 |  |  |  |  | Receiving of Coal & Additives Transport |  | 2549.1073 |  |  | 146 | 2025-03-06 | 2025-07-29 | [5 empty] | 2025-03-31: 356.875; 2025-04-30: 560.8036; 2025-05-31: 892.1876; 2025-06-30: 433.3482; 2025-07-31: 305.8929 |  | 0 |  | 0 | 1809.8662
16 |  |  |  |  | Coal Reclaming and Transport |  | 1995.7333 |  |  | 126 | 2025-03-09 | 2025-07-12 | [5 empty] | 2025-03-31: 279.4027; 2025-04-30: 439.0613; 2025-05-31: 698.5067; 2025-06-30: 339.2747; 2025-07-31: 239.488 |  | 0 |  | 0 | 1416.9707
17 |  |  |  |  | Fuel Grinding |  | 288.1255 |  |  | 170 | 2025-01-21 | 2025-07-09 | [5 empty] | 2025-01-31: 23.05; 2025-02-28: 51.8626; 2025-03-31: 80.6751; 2025-04-30: 57.6251; 2025-05-31: 37.4563; 2025-06-30: 23.05; 2025-07-31: 14.4063 |  | 250.6691 |  | 0 | 175.7565
18 |  |  |  |  | Cable Gallery - Fabrication |  | 2072.0768 |  |  | 91 | 2025-04-21 | 2025-07-20 | [5 empty] | 2025-04-30: 497.2984; 2025-05-31: 766.6684; 2025-06-30: 559.4607; 2025-07-31: 248.6492 |  | 0 |  | 0 | 1263.9668
19 |  |  |  |  | D33 - Compressed Air Station |  | 1.8 | [10 empty] | 2025-05-31: 1.8 |  | 0 |  | 0 | 1.8
20 |  |  |  |  | Substation Staircase |  | 35.8972 | [10 empty] | 2025-05-31: 35.8972 |  | 0 |  | 0 | 35.8972
21 |  |  |  |  | M32/53 - Combined/Fire Water Pump Station |  | 10.1209 | [10 empty] | 2025-05-31: 10.1209 |  | 0 |  | 0 | 10.1209
22 |  |  |  |  | Process Water Piping System |  | 47.8 | [10 empty] | 2025-05-31: 47.8 |  | 0 |  | 0 | 47.8
[19 empty] | 40 | 80 | 1509.4608 | 1343.6148 | 342.6857 | 695.3436 | 1382.3772 | 2331.2919 | 3646.8705 | 4842.2185 | 3000.6384 | 1690.8082 | 0 | 4238.724 | 0 | 0
[18 empty] | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31
[5 empty] | Str Fab Engineering |  | 18739.4146 |  |  |  | 2024-04-17 | 2025-04-15 | [5 empty] | 0 | 0 | 163.3662 | 2625.2419 | 4151.8312 | 1861.3961 | 4280.02 | 4253.7502 | 1403.809
[5 empty] | 212 - LimeStone Crushing to storage |  | 2222.1842 |  |  |  | 2024-04-17 | 2025-03-20 | [5 empty] | 2024-09-30: 555.5461; 2024-10-31: 777.7645; 2024-11-30: 888.8737
[5 empty] | 312 - Limestone reclaiming and transport |  | 2573.0756 |  |  |  | 2024-10-11 | 2024-10-27 | [5 empty] | 2024-10-31: 1286.5378; 2024-11-30: 1286.5378
[5 empty] | X12 - Correctives unloading and storage |  | 741.6117 |  |  |  | 2024-09-14 | 2025-02-03 | [5 empty] | 2024-09-30: 296.6447; 2024-10-31: 444.967
[5 empty] | X92 - Correctives reclaiming and transport |  | 1606.9216 |  |  |  | 2025-01-01 | 2025-03-15 | [5 empty] | 2024-09-30: 401.7304; 2024-10-31: 562.4225; 2024-11-30: 642.7686
[5 empty] | L12 - Wagong tippler and conveying |  | 2549.1073 |  |  |  | 2025-02-19 | 2025-03-09 | [5 empty] | 2024-10-31: 509.8215; 2024-11-30: 637.2768; 2024-12-31: 1402.009
[5 empty] | L22 - Coal reclaiming and transport |  | 1995.7333 |  |  |  | 2024-12-31 | 2025-02-23 | [5 empty] | 2024-09-30: 498.9333; 2024-10-31: 698.5067; 2024-11-30: 798.2933
[5 empty] | 332 - Raw mill feed |  | 701.6303 |  |  |  | 2024-07-29 | 2025-02-25 | [5 empty] | 2024-07-31: 210.4891; 2024-08-31: 491.1412
[5 empty] | 362 - Raw mill |  | 966.0899 |  |  |  | 2024-07-29 | 2025-01-08 | [5 empty] | 2024-07-31: 966.0899
[5 empty] | 412 - Raw meal silo |  | 163.3662 |  |  |  | 2024-07-29 | 2024-12-15 | [5 empty] | 2024-06-30: 163.3662
[5 empty] | 442 - Preheater |  | 4025.5819 |  |  |  | 2024-07-29 | 2025-01-21 | [5 empty] | 2024-07-31: 1207.6746; 2024-08-31: 2817.9074
[5 empty] | 462 - Kiln |  | 103.1959 |  |  |  | 2024-11-04 | 2025-01-15 | [5 empty] | 2024-07-31: 103.1959
[5 empty] | 472 - Cooler |  | 459.3082 |  |  |  | 2024-11-06 | 2025-01-27 | [5 empty] | 2024-07-31: 137.7924; 2024-08-31: 321.5157
[5 empty] | 492 - Clinker transport |  | 108.5416 |  |  |  | 2024-11-05 | 2025-03-21 | [5 empty] | 2024-09-30: 108.5416
[5 empty] | 6K2 - Clinker loading silos (rail) |  | 233.1415 |  |  |  | 2024-11-10 | 2025-03-23 | [5 empty] | 2024-08-31: 233.1415
[5 empty] | L62 - Fuel grinding |  | 288.1255 |  |  |  | 2024-11-08 | 2024-12-20 | [5 empty] | 2024-08-31: 288.1255
[5 empty] | D33 - Compressed air station |  | 1.8 |  |  |  | 2025-03-23 | 2025-04-15 | [5 empty] | 2024-12-31: 1.8
[5 empty] | Others |  | 2165.8949 | [10 empty] | 2024-10-31: 433.179; 2024-11-30: 476.4969; 2024-12-31: 1256.219
[18 empty] | 0 | 0 | 163.3662 | 2625.2419 | 4151.8312 | 1861.3961 | 4713.199 | 4730.2471 | 2660.028 | 0
[5 empty] | Tekla Drawing | [12 empty] | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31
[5 empty] | 212 - LimeStone Crushing to storage |  | 2222.1842 |  |  |  | 2025-03-06 | 2025-03-20 | [5 empty] | 2024-11-30: 2222.1842
[5 empty] | 312 - Limestone reclaiming and transport |  | 2573.0756 |  |  |  | 2024-10-13 | 2024-10-27 | [5 empty] | 2024-11-30: 2573.0756
[5 empty] | X12 - Correctives unloading and storage |  | 741.6117 |  |  |  | 2025-01-20 | 2025-02-03 | [5 empty] | 2024-10-31: 741.6117
[5 empty] | X92 - Correctives reclaiming and transport |  | 1606.9216 |  |  |  | 2025-03-01 | 2025-03-15 | [5 empty] | 2024-11-30: 1606.9216
[5 empty] | L12 - Wagong tippler and conveying |  | 2549.1073 |  |  |  | 2025-02-23 | 2025-03-09 | [5 empty] | 2024-12-31: 2549.1073
[5 empty] | L22 - Coal reclaiming and transport |  | 1995.7333 |  |  |  | 2025-02-09 | 2025-02-23 | [5 empty] | 2024-11-30: 1995.7333
[5 empty] | 332 - Raw mill feed |  | 701.6303 |  |  |  | 2025-02-11 | 2025-02-25 | [5 empty] | 2024-08-31: 701.6303
[5 empty] | 362 - Raw mill |  | 966.0899 |  |  |  | 2024-12-25 | 2025-01-08 | [5 empty] | 2024-07-31: 966.0899
[5 empty] | 412 - Raw meal silo |  | 163.3662 |  |  |  | 2024-12-01 | 2024-12-15 | [5 empty] | 2024-06-30: 163.3662
[5 empty] | 442 - Preheater |  | 4025.5819 |  |  |  | 2025-01-07 | 2025-01-21 | [5 empty] | 2024-08-31: 4025.5819
[5 empty] | 462 - Kiln |  | 103.1959 |  |  |  | 2025-01-01 | 2025-01-15 | [5 empty] | 2024-07-31: 103.1959
[5 empty] | 472 - Cooler |  | 459.3082 |  |  |  | 2025-01-13 | 2025-01-27 | [5 empty] | 2024-08-31: 459.3082
[5 empty] | 492 - Clinker transport |  | 108.5416 |  |  |  | 2025-03-07 | 2025-03-21 | [5 empty] | 2024-09-30: 108.5416
[5 empty] | 6K2 - Clinker loading silos (rail) |  | 233.1415 |  |  |  | 2025-03-09 | 2025-03-23 | [5 empty] | 2024-08-31: 233.1415
[5 empty] | L62 - Fuel grinding |  | 288.1255 |  |  |  | 2024-12-06 | 2024-12-20 | [5 empty] | 2024-08-31: 288.1255
[5 empty] | D33 - Compressed air station |  | 1.8 |  |  |  | 2025-04-01 | 2025-04-15 | [5 empty] | 2024-12-31: 1.8
[5 empty] | Others |  | 2165.8949 | [10 empty] | 2024-12-31: 2165.8949
[11 empty] | 2024-10-13 | 2025-04-15
[11 empty] | 2025-06-13 | 2025-12-14
[7 empty] | 243 |  |  |  |  | Plan | [5 empty] | 0 | 0 | 163.3662 | 1069.2858 | 5707.7873 | 108.5416 | 741.6117 | 8397.9147 | 4716.8022 | 0
Actual

## STRUCTURE ERECTION
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance |  |  |  |  | 0 | 0 | 57.3258 | 221.0023 | 284.138 | 317.7316 | 260.0939 | -335.9898 | -769.6979 | -0.81468 | HO
Structure Erection Plan for 3 month (Based on L5 schedule) with backlog | [21 empty] | 363 | 999 | 1067 | 2541 | 3353 | 3495 | 3946 | 2983 | 1339 | 819
S No |  |  |  |  | Sections |  | Scope |  |  |  | BL Start | BL Finish | [5 empty] | 0 | 0 | 0 | 0 | 363 | 999 | 1067 | 2541 | 3353 | 3495 | 3946 | 2983 | 1339 | 819
S No |  |  |  |  | STRUCTURE NAME |  | SCOPE |  |  |  | 2024-09-22 | 2025-07-06 | [5 empty] | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 1
1 |  |  |  |  | Limestone Crusher & Transport |  | 2222.1842 |  |  | 160 | 2024-10-02 | 2025-03-20 | [12 empty] | 444.4368 | 777.7645 | 666.6553 | 333.3276 |  |  |  | 1888.8566 | 0
2 |  |  |  |  | LimeStone Stockpile and Feeding |  | 2573.0756 |  |  | 45 | 2025-01-01 | 2025-07-06 | [10 empty] | 753 | 350 | 579 | 450 | 263 | 178.0756 |  |  |  | 1292 | 0
3 |  |  |  |  | Raw Material Hopper |  | 701.6303 |  |  | 140 | 2024-11-29 | 2025-05-24 | [12 empty] | 70.163 | 126.2934 | 168.3913 | 196.4565 | 140.3261 |  |  | 364.8477 | 0
4 |  |  |  |  | Raw Mill (Roller Press Building 1 & 2) |  | 966.0899 |  |  | 85 | 2024-10-02 | 2025-04-09 | [10 empty] | 51 | 72 | 68 | 162 | 219 | 183 | 144 | 67.0899 |  | 449 | 0
5 |  |  |  |  | Raw Mill Bag House |  |  |  |  | 30 | 2024-11-14 | 2025-03-01 | [19 empty] | 0 | 0
6 |  |  |  |  | Raw Meal Silo (Blending Silo) |  | 163.3662 |  |  | 80 | 2024-12-29 | 2025-03-03 | [14 empty] | 49 | 74 | 40.3662 |  |  | 0 | 0
7 |  |  |  |  | PreHeater |  | 4025.5819 |  |  | 160 | 2024-10-08 | 2025-06-28 | [9 empty] | 350 | 150 | 500 | 500 | 500 | 500 | 500 | 500 | 330 | 195.5819 | 1500 | 0
8 |  |  |  |  | Kiln |  | 103.1959 |  |  | 63 | 2024-09-27 | 2025-02-18 | [9 empty] | 13 | 20 | 20 | 20 | 20 |  |  | 10.1959 |  |  | 40 | 0
9 |  |  |  |  | Clinker Cooler |  | 459.3082 |  |  | 40 | 2024-10-17 | 2025-01-26 | [13 empty] | 120 | 210 | 129.3082 |  |  |  | 330 | 0
10 |  |  |  |  | Cooler ESP Building |  |  |  |  | 56 | 2024-10-04 | 2025-03-03 | [19 empty] | 0 | 0
11 |  |  |  |  | Reject Silo |  | 108.5416 |  |  | 115 | 2024-09-22 | 2025-02-03 | [12 empty] | 13 | 25 | 25 | 35 | 10.54 |  |  | 63 | 0.0016
12 |  |  |  |  | Clinker Loading Silos (3S 01, 02) |  | 233.1415 |  |  | 70 | 2024-10-07 | 2025-01-21 | [13 empty] | 52 | 58 | 63 | 60.1415 |  |  | 110 | 0
13 |  |  |  |  | Correctives Unloading and Transport |  | 741.6117 |  |  | 45 | 2025-03-17 | 2025-05-25 | [11 empty] | 23.3142 | 46.6283 | 55.954 | 51.2911 | 32.6398 | 531.7844 |  |  | 153.8734 | 0
14 |  |  |  |  | Correctives Storage and Transport |  | 1606.9216 |  |  | 105 | 2024-12-14 | 2025-06-07 | [12 empty] | 96.4095 | 133.4901 | 170.5707 | 155.7385 | 103.8256 | 946.8871 |  | 400.4703 | 0
15 |  |  |  |  | Receiving of Coal & Additives Transport |  | 2549.1073 |  |  | 73 | 2025-03-07 | 2025-06-04 | [15 empty] | 550 | 750 | 650 | 599.1073 | 0 | 0
16 |  |  |  |  | Coal Reclaming and Transport |  | 1995.7333 |  |  | 106 | 2024-12-19 | 2025-04-01 | [12 empty] | 450 | 370 | 200 | 470 | 505.7333 |  |  | 1020 | 0
17 |  |  |  |  | Fuel Grinding |  | 288.1255 |  |  | 136 | 2024-10-31 | 2025-06-17 | [10 empty] | 25 | 44 | 32 | 26 | 46 | 35 |  | 55 | 25.1255 | 104 | 0
18 |  |  |  |  | Cable Gallery - Erection |  | 2072.0768 |  |  | 91 | 2025-03-31 | 2025-06-28 | [13 empty] | 250 | 550 | 750 | 522.0768 |  |  | 800 | 0
19 |  |  |  |  | D33 - Compressed Air Station |  | 1.8 | [22 empty] | 1.8 |  | 0 | 0
20 |  |  |  |  | Substation Staircase |  | 35.8972 | [16 empty] | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 |  |  |  | 1.08 | 34.0972
21 |  |  |  |  | M32/53 - Combined/Fire Water Pump Station |  | 10.1209 | [22 empty] | 10.1209 |  | 0 | 0
22 |  |  |  |  | Process Water Piping System |  | 47.8 | [22 empty] | 47.8 |  | 0 | 0
0
[5 empty] | Total |  | 5076 |  |  | 685.161 | 594.271 | 326.022 | [5 empty] | 304.367 | [6 empty] | 2541 | 3353 | 3495 | 3946 | 2983 | 1339 | 819

## P&E
S No | Section | Department | Description | Sub Phase 1 | Particular | UOM |  |  | Scope | DRAWING RELESED | ACHIVED | DURATION | BL Start | BL Finish | Current Month Plan | Current Month Actual | Cummulative Planned | Cummulative completed | Balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | -0.2 | 0 | 0.09 | 368.206 | 367.7589 | 368.588 | 0.36 | HO
Structure Erection Plan for 3 month (Based on L5 schedule) with backlog | [23 empty] | 67 | 378 | 906 | 1419 | 1878 | 2257 | 3295 | 3778 | 3419 | 2442 | 1555 | 111
S No |  |  |  |  | Sections |  | Plate | Equipment | Scope |  |  |  | BL Start | BL Finish | [5 empty] | 21505.365 | 21505.365 | 21505.365 | 21505.365 | 67 | 378 | 906 | 1419 | 1878 | 2257 | 3295 | 3778 | 3419 | 2442 | 1555 | 111
S No |  |  |  |  | STRUCTURE |  | 10147.2 | 32863.53 | 43010.73 |  |  |  | 1958-11-16 08:46 | 2025-08-19 | [5 empty] | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01
1 |  |  |  |  | Limestone Crusher & Transport |  | 102 | 2128.111 | 2230.111 |  |  |  | 2024-09-25 | 2025-04-29 | [5 empty] | 2025-04-01: 229; 2025-05-01: 255; 2025-06-01: 508; 2025-07-01: 700; 2025-08-01: 538.111 | 992
2 |  |  |  |  | LimeStone Stockpile and Feeding |  | 19.2 | 676.242 | 695.442 |  |  |  | 2024-12-08 | 2025-07-06 | [5 empty] | 2025-03-01: 65; 2025-04-01: 96; 2025-05-01: 109.44; 2025-06-01: 99; 2025-07-01: 121; 2025-08-01: 205 | 304.44
3 |  |  |  |  | Raw Material Hopper |  | 168 | 272.0054 | 440.0054 |  |  |  | 2024-11-29 | 2025-05-27 | [5 empty] | 2025-04-01: 19; 2025-05-01: 54; 2025-06-01: 90; 2025-07-01: 62; 2025-08-01: 83; 2025-09-01: 97; 2025-10-01: 35.01 | 163
4 |  |  |  |  | Raw Mill (Roller Press Building 1 & 2) |  | 881.04 | 2219.298 | 3100.338 |  |  |  | 2024-10-07 | 2025-06-13 | [9 empty] | 67 | 318 | 539 | 530 | 403 | 559 | 295 | 169 | 85 | 79 | 56.338 |  | 1257
5 |  |  |  |  | Raw Mill Bag House |  | 368.16 | 946.2 | 1314.36 |  |  |  | 2024-12-28 | 2025-08-17 | [5 empty] | 2025-04-01: 44; 2025-05-01: 58; 2025-06-01: 205; 2025-07-01: 220; 2025-08-01: 120; 2025-09-01: 297; 2025-10-01: 259; 2025-11-01: 111.36 | 307
6 |  |  |  |  | Raw Meal Silo (Blending Silo) |  | 15 | 186.71 | 201.71 |  |  |  | 2024-11-18 | 2025-04-12 | [5 empty] | 2025-03-01: 4; 2025-04-01: 4; 2025-05-01: 10; 2025-06-01: 51; 2025-07-01: 58; 2025-08-01: 31; 2025-09-01: 27; 2025-10-01: 16.71 | 65
7 |  |  |  |  | PreHeater |  | 2440.5 | 788.862 | 3229.362 |  |  |  | 2024-10-05 | 2025-06-28 | [5 empty] | 2025-02-01: 208; 2025-03-01: 325; 2025-04-01: 388; 2025-05-01: 343.36; 2025-06-01: 332; 2025-07-01: 330; 2025-08-01: 401; 2025-09-01: 423; 2025-10-01: 479 | 1063.36
8 |  |  |  |  | Kiln |  | 234.5 | 1353.16 | 1587.66 |  |  |  | 2024-08-30 | 2025-04-08 | [5 empty] | 2025-04-01: 180; 2025-05-01: 50; 2025-06-01: 132; 2025-07-01: 632; 2025-08-01: 280; 2025-09-01: 280; 2025-10-01: 33.66 | 362
9 |  |  |  |  | Clinker Cooler |  | 260 | 972.76 | 1232.76 |  |  |  | 2024-12-22 | 2025-05-17 | [5 empty] | 2025-03-01: 100; 2025-04-01: 100; 2025-05-01: 200; 2025-06-01: 240; 2025-07-01: 243; 2025-08-01: 197; 2025-09-01: 85; 2025-10-01: 67.76 | 540
10 |  |  |  |  | Cooler ESP Building |  | 76 | 1075.09 | 1151.09 |  |  |  | 2024-11-03 | 2025-06-04 | [5 empty] | 2025-03-01: 132; 2025-04-01: 157; 2025-05-01: 248; 2025-06-01: 226; 2025-07-01: 198.09; 2025-08-01: 190 | 631
11 |  |  |  |  | Reject Silo |  | 22 | 328.17 | 350.17 |  |  |  | 2024-12-05 | 2025-04-09 | [5 empty] | 2025-05-01: 34; 2025-06-01: 66; 2025-07-01: 88; 2025-08-01: 88; 2025-09-01: 74.17 | 100
12 |  |  |  |  | Clinker Loading Silos (3S 01, 02) |  | 18 | 625.6292 | 643.6292 |  |  |  | 2024-11-20 | 2025-03-13 | [5 empty] | 2025-06-01: 44; 2025-07-01: 88; 2025-08-01: 148; 2025-09-01: 188; 2025-10-01: 175.63 | 44
13 |  |  |  |  | Correctives Unloading and Transport |  | 48 | 524.3532 | 572.3532 |  |  |  | 2024-12-28 | 2025-06-14 | [5 empty] | 2025-05-01: 66; 2025-06-01: 145; 2025-07-01: 167; 2025-08-01: 102; 2025-09-01: 92.35 | 211
14 |  |  |  |  | Correctives Storage and Transport |  | 35 | 623.664 | 658.664 |  |  |  | 2025-01-10 | 2025-08-04 | [5 empty] | 2025-02-01: 45; 2025-03-01: 87; 2025-04-01: 56; 2025-05-01: 157; 2025-06-01: 113; 2025-07-01: 63; 2025-08-01: 54; 2025-09-01: 83.66 | 326
15 |  |  |  |  | Receiving of Coal & Additives Transport |  | 44.5 | 1535.4413 | 1579.9413 |  |  |  | 2025-04-09 | 2025-07-09 | [5 empty] | 2025-06-01: 450; 2025-07-01: 357; 2025-08-01: 413; 2025-09-01: 239; 2025-10-01: 120.94 | 450
16 |  |  |  |  | Coal Reclaming and Transport |  |  | 1137.4839 | 1137.4839 |  |  |  | 2025-01-10 | 2025-08-19 | [5 empty] | 2025-06-01: 194; 2025-07-01: 202; 2025-08-01: 255; 2025-09-01: 266.4839; 2025-10-01: 220 | 194
17 |  |  |  |  | Fuel Grinding |  | 339.3 | 855.145 | 1194.445 |  |  |  | 2024-08-12 | 2025-07-14 | [10 empty] | 60 | 114 | 176 | 202 | 113 | 105 | 80 | 167 | 148 | 29.445 |  | 420
18 |  |  |  |  | Compressed Air Station and Pipeline Erection |  | 2.4 | 93.44 | 95.84 |  |  |  | 2025-04-19 | 2025-06-17 | [5 empty] | 2025-08-01: 398.1483; 2025-09-01: 398.1483; 2025-10-01: 398.1483 | 0
19 |  |  |  |  | WTP Readiness with Water Pipeline Erection |  |  | 90 | 90 |  |  |  | 2025-02-10 | 2025-05-10 | [5 empty] | 2025-08-01: 31.9467; 2025-09-01: 31.9467; 2025-10-01: 31.9467 | 0
[5 empty] | Total |  | 5073.6 | 16431.765 | 21505.365 |  |  |  | 21505.365 | 21505.365 | [5 empty] | 2024-08-01: 21505.365; 2024-09-01: 21505.365; 2024-10-01: 21505.365; 2024-11-01: 21505.365

## Manpower Trend - A
Department (P) | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Civil (P) | 663 | 1003 | 1000 | 1108 | 178 | 384 | 529 | 367 | 368 | 532 | 882 | 865 | 865 | 865
Mechanical(P) | 20 | 80 | 150 | 200 | 9 | 11 | 29 | 29 | 29 | 44 | 44 | 289 | 314 | 314
E&I(P)
Process(P)

## PLAN VS ACTUAL
Department (P) | Civil (P) | Mechanical(P) | E&I(P) | Process(P) | Department (A) | Civil (A) | Mechanical (A) | E&I(A) | Process(A) | TOTAL PLAN | TOTAL ACTUAL | MAX P | MAX A
2024-03-01 | 663 | 20 | 0 | 0 | 2024-03-01 | 663 | 20 | 0 | 0 | 683 | 683 | 1308 | 2808
2024-04-01 | 1003 | 80 | 0 | 0 | 2024-04-01 | 1003 | 80 | 0 | 0 | 1083 | 1083
2024-05-01 | 1000 | 150 | 0 | 0 | 2024-05-01 | 1000 | 150 | 0 | 0 | 1150 | 1150
2024-06-01 | 1108 | 200 | 0 | 0 | 2024-06-01 | 1108 | 200 | 0 | 0 | 1308 | 1308
2024-07-01 | 178 | 9 | 0 | 0 | 2024-07-01 | 663 | 20 | 0 | 0 | 187 | 683
2024-08-01 | 384 | 11 | 0 | 0 | 2024-08-01 | 1003 | 80 | 0 | 0 | 395 | 1083
2024-09-01 | 529 | 29 | 0 | 0 | 2024-09-01 | 1000 | 20 | 0 | 0 | 558 | 1020
2024-10-01 | 367 | 29 | 0 | 0 | 2024-10-01 | 708 | 20 | 0 | 0 | 396 | 728
2024-11-01 | 368 | 29 | 0 | 0 | 2024-11-01 | 708 | 20 | 0 | 0 | 397 | 728
2024-12-01 | 532 | 44 | 0 | 0 | 2024-12-01 | 708 | 20 | 0 | 0 | 576 | 728
2025-01-01 | 882 | 44 | 0 | 0 | 2025-01-01 | 1454 | 576 | 0 | 0 | 926 | 2030
2025-02-01 | 865 | 289 | 0 | 0 | 2025-02-01 | 708 | 643 | 0 | 0 | 1154 | 1351
2025-03-01 | 865 | 314 | 0 | 0 | 2025-03-01 | 1544 | 1140 | 0 | 0 | 1179 | 2684
2025-04-01 | 865 | 314 | 0 | 0 | 2025-04-01 | 1603 | 1205 | 0 | 0 | 1179 | 2808
2025-05-01 | 0 | 0 | 0 | 0 | 2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 0 | 0 | 2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 0 | 0 | 0 | 0 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-01 | 0 | 0 | 0 | 0 | 2025-08-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-01 | 0 | 0 | 0 | 0 | 2025-09-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 0 | 0 | 0 | 0 | 2025-10-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-01 | 0 | 0 | 0 | 0 | 2025-11-01 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 0 | 0 | 0 | 0 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Trend - P
Department (A) | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Civil (A) | 663 | 1003 | 1000 | 1108 | 663 | 1003 | 1000 | 708 | 708 | 708 | 1454 | 708 | 1544 | 1603
Mechanical (A) | 20 | 80 | 150 | 200 | 20 | 80 | 20 | 20 | 20 | 20 | 576 | 643 | 1140 | 1205
E&I(A)
Process(A)

## Land Status
S No | Description | Land Required (In Acre) | Land Procured (In Acre) | Khasara Numbers - To be procured | Khasara Numbers - Procured | Type of Land | Land Conversion (If Any) | Remarks
1 | Land For railway siding | 18 | 0 |  |  | Agriculture Land | Required | Currently under Proposal stage
2
3
4
5
6
7
8

## Critical Points
S No | Priority | Focus Points | Status & Action Plan | Open Date | Responsible | Target Date | Revised Target | Delay (In Days) | Status
A |  | Statutory Clearances
1 | CRITICAL | Drawing Approval by Director of Safety | In Progress |  | Sudhakar Pandey | 2024-07-31 |  |  | Open
2 | CRITICAL | EC of Mines ML1 | In Progress |  | Sudhakar Pandey | 2024-09-30 |  |  | Open
3 | CRITICAL | CTE for Mines ML1 | In Progress |  | Sudhakar Pandey | 2024-08-30 |  |  | Open
4 | MODERATE | Approval from Railways (FSR,IPA,DPR & ESP) | Pending at DRM/GM office at Secunderabad |  | Sudhakar Pandey | 2024-07-20 | 2024-07-31 | 11 | Open
5 | MODERATE | 220KV Work Start approval | In Progress |  | Sudhakar Pandey | 2024-07-31 |  |  | Open
B |  | Engineering & Procurement
6 | MINIMAL | Design Engineering for LS Crusher, OLBC & Stock Pile. | 30% Area Test Report awaited, New Soil Testing Agency engaged. |  | LNVT / TCDRI | 2024-07-31 |  |  | Open
C |  | Construction & Pre Project
7 | CRITICAL | Non availability of sufficient Manpower, Machineries & Drawings leading to delay in execution of project at Site. | Currently (144/ 865 Manpower available) AAA senior team visited Kathmandu and conducted meeting with LNVT/ TCDRI on dated 26/27-Jun-24 for expedite manpower & other required resources. |  | LNVT/TCDRI | 2024-07-31 |  |  | Open
8 | MINIMAL | Additional railway line with platform along with RUB is required for Manual unloading of raw material and emergency access from Colony to Plant | Estimation for the job provided to Railway team and is under approval |  | Bharat Chouhan | 2024-07-31 |  |  | Open
9 | MODERATE | Fabrication contractor not freeze and mobilized | LNVT informed that contractor Finalization by 23-Jul-24 & LOI will be issued by 24-Jul-24. |  | LNVT | 2024-07-24 | 2024-07-30 | 6 | Open
10 | MODERATE | In adequate resources for the excavation of the balance structures/Buildings | 3 Nos of additional Poclain Operators are being arranged by LNVT. |  | LNVT | 2024-07-31 |  |  | Open
11 | MODERATE | Inadequate Staging Material | LOI issued to M/s Vikash Scaffolding for 500 MT. Expected dispatch will start by 19-July-24. |  | LNVT | 2024-07-31 |  |  | Open
12 | CRITICAL | Inadequate LNVT Staff Civil Head, Safety Head, Mechanical Head, E&I Head, Quality team,& Planning Team not available. | LNVT Informed that - Planning Engineer will report by 20-Jul-24 & for balance position LNVT will confirm by 22-Jul-24 (Status Still pending from LNVT) |  | LNVT | 2024-07-31 |  |  | Open
13 | MODERATE | In adequate material (TMT) (Req 1500 MT ) | 640 MT TMT received at site against 1500 MT & further quantity is in process for dispatch. |  | LNVT | 2024-07-31 |  |  | Open
14 | MINIMAL | Leveling & Development of Fabrication Yard. Also additional resource required for compaction & leveling. | Expected completion for levelling by 25-Jul-24 subjected to Vibro Roller availability. |  | LNVT | 2024-07-25 |  |  | Open
15 | MINIMAL | Water Pipe Line from Vansadi Village to Transport Nagar | Drawing Finalized. PR done for construction PR done for materials |  | Sudhakar Pandey | 2024-12-30 |  |  | Open

## Packages
SN | Section | Sub Phase - 1 | Package Name | Vendor | Sub -Vendor | Planned Date | Order Finalization (LOI Confirmation) | Status | Remarks
1 | C | E&I packages | MV Switchboards | LNVT | Schneider | 2024-04-27 | 2024-12-11 | Closed | LOI/PO
2 | C | E&I packages | MV Drives | LNVT | Hitachi Hirel Power Electronics Private Limited, Sanand | 2024-04-27 | 2024-10-08 | Closed | Drawings Submitted
3 | C | E&I packages | LRS | LNVT | M/s. Ploneer Electrlcal Works | 2024-04-27 | 2024-08-22 | Closed | Inspection Finished
4 | C | E&I packages | MV Capacitors | LNVT | Hitachi Hirel Power Electronics Private Limited, Sanand | 2024-05-13 | 2024-11-21 | Closed | LOI/PO
5 | C | E&I packages | Transformers - Power And Distribution | LNVT | Schneider | 2024-05-13 | 2024-09-30 | Closed | Inspection Finished
6 | C | E&I packages | Lighting Power Transformer | LNVT |  | 2024-05-28 |  | Open | Technicacl Clarification
7 | C | E&I packages | LV Panels - PCC/ MCC / MLDB/ MPDB/ EPDB | LNVT | Danfoss | 2024-05-13 |  | Closed | LOI/PO
8 | C | E&I packages | LV Bus Duct | LNVT |  | 2024-06-12 |  | Open | Technicacl Clarification
9 | C | E&I packages | LV Capacitor Panels | LNVT | Intrelec | 2024-05-18 | 2024-09-16 | Closed | Drawings Submitted
10 | C | E&I packages | SPDB (Sub Main Distribution Board) | LNVT |  | 2024-05-28 |  | Open | RFQ Floated
11 | C | E&I packages | LV Drives | LNVT | Danfoss Industries Pvt. Ltd. | 2024-05-13 | 2024-12-09 | Closed | LOI/PO
12 | C | E&I packages | UPS / UPS DB / DCS DB | LNVT |  | 2024-05-28 |  | Open | RFQ Floated
13 | C | E&I packages | Battery / Battery Charger | LNVT |  | 2024-05-28 |  | Open | Technicacl Clarification
14 | C | E&I packages | Switches / Sockets/ Single Phase Receptacle/ Welding Socket Outlet/ Exit Sign Boards | LNVT |  | 2024-06-07 |  | Open | RFQ Floated
15 | C | E&I packages | Local Push Buttons /Panic Stop Push Buttons/ VCS | LNVT |  | 2024-06-07 |  | Open | RFQ Received
16 | C | E&I packages | Analog / Digital Junction Box Various Sizes 5TB To 200 TB | LNVT |  | 2024-06-07 |  | Open | RFQ Floated
17 | C | E&I packages | Magnetic Starter Panel/Power Junction Box | LNVT |  | 2024-06-17 |  | Open | RFQ not received
18 | C | E&I packages | Hooter And Flasher | LNVT |  | 2024-06-17 | 2024-09-16 | Closed | Inspection Finished
19 | C | E&I packages | Ligthing SLD With Timer | LNVT |  | 2024-06-17 |  | Open | Technicacl Clarification
20 | C | E&I packages | AAQMS (Ambient Air Quality Monitoring System) | LNVT | Thermo Fisher Scientific India Pvt Ltd | 2024-05-13 | 2024-10-08 | Closed | Mechanical Manufacturing
21 | C | E&I packages | Dust Monitors | LNVT | SICK INDIA Pvt. Ltd. | 2024-05-28 | 2024-09-16 | Closed | Drawings Submitted
22 | C | E&I packages | Temperature Transmitters | LNVT | Vaibhav Tech Solutions | 2024-06-27 | 2024-10-01 | Closed | Drawings Submitted
23 | C | E&I packages | Pressure Transmitters / DP Transmitters | LNVT | Vaibhav Tech Solutions | 2024-06-27 | 2024-10-01 | Closed | Drawings Submitted
24 | C | E&I packages | Radar Type Level Transmitter | LNVT | Vaibhav Tech Solutions | 2024-06-27 |  | Closed | RFQ not received
25 | C | E&I packages | Ultrasonic Level Transmitters | LNVT |  | 2024-06-27 |  | Open | RFQ not received
26 | C | E&I packages | Hopper Level Switch | LNVT |  | 2024-06-27 |  | Open | Technical Clarification
27 | C | E&I packages | Vibration Transmitters | LNVT |  | 2024-06-27 |  | Open | Technical Clarification
28 | C | E&I packages | RTD / Thermocouple | LNVT |  | 2024-06-27 |  | Open | Technical Clarification
29 | C | E&I packages | Plant DCS / PLC System / DCS System / Control Desk / Computers / Servers | LNVT | FLSmidth | 2024-05-28 | 2024-09-20 | Closed | LOI/PO
30 | C | E&I packages | Kiln Shell Scanner | LNVT | Thermo Tecknix | 2024-05-28 | 2025-02-17 | Closed | LOI/PO
31 | C | E&I packages | Fire Alarm System (For Load Centers) | LNVT | Vaibhav Tech Solutions | 2024-06-12 | 2025-02-17 | Closed | Technicacl Clarification
32 | C | E&I packages | CCTV Monitoring System | LNVT | Vaibhav Tech Solutions | 2024-06-07 | 2025-02-17 | Closed | Technicacl Clarification
33 | C | E&I packages | Energy Management System | LNVT |  | 2024-06-17 |  | Open | RFQ not received
34 | C | E&I packages | Telephone System | LNVT |  | 2024-06-07 |  | Open | RFQ not received
35 | C | E&I packages | PA System | LNVT |  | 2024-06-07 |  | Open | RFQ Floated
36 | C | E&I packages | Access Control System | LNVT | Vaibhav Tech Solutions | 2024-06-07 | 2025-02-17 | Closed | Technicacl Clarification
37 | C | E&I packages | MV Power Cables | LNVT | TORRENT | 2024-06-07 | 2024-12-19 | Closed | LOI/PO
38 | C | E&I packages | LV Power Cables | LNVT |  | 2024-06-27 |  | Open | Technical Clarification
39 | C | E&I packages | Control And Signal Cables | LNVT |  | 2024-06-27 |  | Open | RFQ Floated
40 | C | E&I packages | Lighting Cable Various Sizes | LNVT |  | 2024-06-27 |  | Open | RFQ not received
41 | C | E&I packages | Earthing Junction Box | LNVT |  | 2024-07-13 |  | Open | RFQ Floated
42 | C | E&I packages | Earthing Electrode | LNVT |  | 2024-07-13 |  | Open | RFQ Floated
43 | C | E&I packages | Earthing Flat / Wire - Different Sizes | LNVT | Raipur | 2024-07-13 | 2024-08-28 | Closed | First FOR site
44 | C | E&I packages | Outdoor Led Lamps/Fluorscent Led Lamp/Emergency Led Lamps With Battery Back-Up/Road / Street Lamps | LNVT | Bajaj | 2024-07-13 | 2025-03-06 | Closed | Technicacl Clarification
45 | C | E&I packages | High Mast | LNVT | M/s. Pyrotech Electronics Pvt Ltd.. | 2024-07-13 | 2024-08-30 | Closed | Inspection Finished
46 | C | E&I packages | Aviation And All Other Lighting Related Items | LNVT |  | 2024-07-13 |  | Open | RFQ not received
47 | C | E&I packages | Cable Glands And Lugs, Termination Kits | LNVT |  | 2024-07-13 |  | Open | RFQ Floated
48 | C | E&I packages | Safety And PPE Equipment Exit Sign Boards | LNVT |  | 2024-07-13 |  | Open | RFQ Received
49 | C | Mechanical Packages | Vertical Mill For Coal | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-03-01 | Closed | Last FOR site
50 | C | Mechanical Packages | Roller Press | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-04-09 | Closed | Last FOR site
51 | C | Mechanical Packages | Limestone Crusher (Double Impact Rotor Crusher/apron feeder/Spillage conveyor/Wobbler Feeder etc.) | LNVT | L&T | 2024-03-03 | 2024-04-11 | Closed | Inspection Finished
52 | C | Mechanical Packages | Sizer | LNVT | TAKRAF India Private Limited | 2024-05-04 | 2024-07-18 | Closed | Mechanical Manufacturing
53 | C | Mechanical Packages | Ultrahigh molecular weight polyethylene Liner | TCDRI | Tangyin New Eternal Wear Resistant Material Co. Ltd. | 2024-07-27 | 2024-08-09 | Closed | First FOR site
54 | C | Mechanical Packages | Wearable Liner | TCDRI | Weihai Hongsong | 2024-12-22 | 2024-07-18 | Closed | Mechanical Manufacturing
55 | C | Mechanical Packages | Wear resistant ceramic coating/Paster | TCDRI | SINOMA | 2024-11-09 | 2024-07-31 | Closed | First FOR site
56 | C | E&I packages | MV Motor | TCDRI | SHANGHAI ELECTRIC GROUP | 2024-04-09 | 2024-05-22 | Closed | Last FOR site
57 | C | Mechanical Packages | Lubricants | LNVT |  | 2024-11-27 |  | Open | RFQ not received
58 | C | Mechanical Packages | Magnetic Separator | TCDRI | FUSHUN LONGJI | 2024-05-30 | 2024-06-11 | Closed | First FOR site
59 | C | Mechanical Packages | Metal Detector | TCDRI | Minebea Intec | 2024-05-30 | 2024-05-23 | Closed | First FOR site
60 | C | Mechanical Packages | Cross Analyzer | LNVT |  | 2024-05-11 |  | Open | Technicacl Clarification
61 | C | Mechanical Packages | Sampler | TCDRI | XIANGFAN ZHENGGUANG | 2024-06-04 | 2024-04-18 | Closed | First FOR site
62 | C | Mechanical Packages | HT Sampler | TCDRI | ITECA | 2024-06-04 | 2024-04-28 | Closed | Inspection Finished
63 | C | Mechanical Packages | Local Fabrication - Preheater | LNVT | Site Fabrication | 2024-05-13 | 2024-05-13 | Closed | Raw Material Prepared
64 | C | Mechanical Packages | Local Fabrication - Kiln | LNVT | Invincible US Infrastructure Pvt Ltd., Hyderabad | 2024-05-27 | 2024-07-10 | Closed | Mechanical Manufacturing
65 | C | Mechanical Packages | Local Fabrication - Cooler | LNVT | Invincible Us Infrastructure,Secunderabad, Hyderabad | 2024-05-13 | 2024-07-22 | Closed | Mechanical Manufacturing
66 | C | Mechanical Packages | Local Fabrication - Coal Mill | LNVT | Diamond Engineering Pvt.Ltd | 2024-05-13 | 2024-07-10 | Closed | Mechanical Manufacturing
67 | C | Mechanical Packages | Local fabrication - Cyclone and bin for roller | LNVT | Site Fabrication | 2024-03-03 | 2024-05-13 | Closed | Raw Material Prepared
68 | C | Mechanical Packages | Local Fabrication - Bag House | LNVT | Maventek Industries | 2024-07-04 | 2024-09-17 | Closed | Mechanical Manufacturing
69 | C | Mechanical Packages | Local Fabrication - ESP | LNVT | Sai Industries | 2024-07-04 | 2024-09-09 | Closed | Mechanical Manufacturing
70 | C | Mechanical Packages | Local Fabrication - Bucket Elvator | LNVT | Diamond Engineering | 2024-06-11 | 2024-07-22 | Closed | Mechanical Manufacturing
71 | C | Mechanical Packages | Local fabrication - Process duct/pressure relief cone/weighing bin | LNVT |  | 2024-08-17 |  | Closed | Site Fabrication
72 | C | Mechanical Packages | Local fabrication - Steel structure (Bin/Cyclone/Hopper/Stack etc) | LNVT |  | 2024-08-17 | 2024-10-29 | Closed | Mechanical Manufacturing
73 | C | Mechanical Packages | Kiln (Including Damming Ring for locking brick) | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-04-09 | Closed | Last For Site
74 | C | Mechanical Packages | Preheater (Diptube, Expansion Joint, Valves) | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-04-09 | Closed | Last For Site
75 | C | Mechanical Packages | Grate Cooler | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-04-09 | Closed | First FOR site
76 | C | Mechanical Packages | Burner | TCDRI | SINOMA-TCDRI | 2024-03-03 | 2024-04-09 | Closed | First FOR site
77 | C | Mechanical Packages | Bucket Elevator (Preheater) | LNVT | Techno Industries Private Limited | 2024-03-03 | 2024-06-01 | Closed | Mechanical Manufacturing
78 | C | Mechanical Packages | Process Valve/Non Standard Valve | TCDRI | Yangzhou GaoBiao Machinery Co.,Ltd | 2024-06-30 | 2024-08-06 | Closed | Inspection Finished
79 | C | Mechanical Packages | Motorized Actuator | TCDRI | TIANJIN BAOHENG | 2024-07-08 | 2024-04-12 | Closed | Package Finished
80 | C | Mechanical Packages | Expansion Joint/Soft Joint | TCDRI | Nantong Animate Machinery Co., Ltd | 2024-06-30 | 2024-04-18 | Closed | last FOR site
81 | C | Process Packages | Wear Resistant Ceramic Elbow | TCDRI | Yixing Huguang | 2024-06-30 | 2024-10-23 | Closed | Inspection Finished
82 | C | Process Packages | Castable | LNVT |  | 2024-07-27 |  | Open | RFQ Floated
83 | C | Process Packages | Refractory bricks (Including Magnesia brick for kiln) | TCDRI | RHI Magnesita | 2024-07-15 | 2024-08-25 | Closed | Package Finished
84 | C | Process Packages | Refractory bricks (Including brick for preheater brick/TDA etc.) | LNVT |  | 2024-07-27 |  | Open | RFQ Floated
85 | C | Process Packages | Refractory bricks (Including Haning brick etc.) | LNVT |  | 2024-07-15 |  | Open | RFQ Floated
86 | C | Process Packages | Calcium Silicate | TCDRI | Zhengzhou Shengshi Jinding Insulation Refractory Co.,Ltd | 2024-07-15 | 2024-08-28 | Closed | Inspection Finished
87 | C | Process Packages | Ceramic Fibre/Nano Plate | TCDRI | Luoyang Sanhe Insulation Technology Co., LtdCo.,Ltd | 2024-07-15 | 2024-08-13 | Closed | Inspection Finished
88 | C | Process Packages | Refractory auxiliary material (Water glass) | LNVT |  | 2024-07-15 |  | Open | RFQ Floated
89 | C | Mechanical Packages | Water Treatment System | TCDRI | Jiangsu Jinyi Water Industry Equipment Co., ltd. | 2024-07-30 | 2024-07-31 | Closed | Inspection Finished
90 | C | Mechanical Packages | Water Spraying System | TCDRI | Nanjing Seagle | 2024-07-30 | 2024-05-29 | Closed | Inspection Finished
91 | C | Mechanical Packages | Cooling Tower/Filter | TCDRI | Jiangsu Jinyi Water Industry Equipment Co., ltd. | 2024-07-30 | 2024-07-31 | Closed | Inspection Finished
92 | C | Mechanical Packages | Water Pump/Fire pump/High pressure pump | TCDRI | Shandong Shuanglun | 2024-07-30 | 2024-08-06 | Closed | Painting
93 | C | Mechanical Packages | Water Valve | TCDRI |  | 2024-08-30 |  | Open | RFQ not received
94 | C | Mechanical Packages | Water Instrument | TCDRI |  | 2024-08-30 |  | Open | RFQ not received
95 | C | Mechanical Packages | Pipes And Parts | LNVT |  | 2024-06-21 |  | Open | RFQ Received
96 | C | Mechanical Packages | Stacker And Reclaimer | LNVT | TAKRAF India Private Limited | 2024-04-17 | 2024-05-17 | Closed | Package Finished
97 | C | Mechanical Packages | Belt Bucket Elevator | TCDRI | BEUMER Machinery (Shanghai) Co. Ltd. | 2024-03-03 | 2024-01-24 | Closed | Last FOR Site
98 | C | Mechanical Packages | Chain Bucket Elevator | TCDRI | Hangzhou Boyu Machinery Co.,Ltd | 2024-03-03 | 2024-01-26 | Closed | Last FOR Site
99 | C | Mechanical Packages | Motorized Ball Valve | TCDRI | Yangzhou GaoBiao Machinery Co.,Ltd | 2024-06-30 | 2024-04-09 | Closed | First FOR site
100 | C | Mechanical Packages | Manhole/Measure Hole |  |  | 2024-06-30 | 2024-11-24 | Closed | Inspection Finished
101 | C | Mechanical Packages | Belt Conveyor | LNVT | Hengyang Conveying Machinery Co.,Ltd | 2024-06-30 | 2024-07-15 | Closed | Inspection Finished
102 | C | Mechanical Packages | OLBC - Belt Conveyor | TCDRI | Anhui Kezhong Technology Co. Ltd | 2024-05-05 | 2024-07-10 | Closed | Raw Material Prepared
103 | C | Mechanical Packages | Pan Conveyor (DPC) | TCDRI | SINOMA-TCDRI | 2024-04-14 | 2024-04-10 | Closed | Package Finished
104 | C | Mechanical Packages | Air Slide | TCDRI | Nantong Animate Machinery Co., Ltd | 2024-05-25 | 2024-04-10 | Closed | Inspection Finished
105 | C | Mechanical Packages | Screw Conveyor | TCDRI | Botou Maite Cement Machinery Co.,Ltd | 2024-05-15 | 2024-04-10 | Closed | First FOR Site
106 | C | Mechanical Packages | FU Conveyor (Chain Conveyor) | TCDRI | Botou Maite Cement Machinery Co.,Ltd | 2024-05-25 | 2024-04-10 | Closed | First FOR Site
107 | C | Mechanical Packages | Surface Feeder | TCDRI | SINOMA-TCDRI | 2024-03-21 | 2024-01-29 | Closed | Inspection Finished
108 | C | Mechanical Packages | Pulverized Coal Weigh Feeder (European part/China part) | TCDRI | Schenck Process (Tianjin) Industrial Technology Co. Ltd. | 2024-03-03 | 2024-03-01 | Closed | Inspection Finished
109 | C | Mechanical Packages | Raw Meal Weigh Feeder | TCDRI | Schenck Process (Tianjin) Industrial Technology Co. Ltd. | 2024-04-29 | 2024-04-07 | Closed | Package Finished
110 | C | Mechanical Packages | Apron Weighing Feeder/Belt Scale/Weighing Feeder/Impact Flow Scale | LNVT | Schenck Process India Private Co.,Ltd | 2024-05-20 | 2024-07-15 | Closed | LOI/PO
111 | C | E&I packages | Load Cell | LNVT | Schenck Process India Private Co.,Ltd | 2024-05-28 | 2024-07-15 | Closed | Raw Material Prepared
112 | C | E&I packages | Weigh Bridge | LNVT | Rice Lake Weighing Systems India Limited | 2024-04-26 | 2024-04-26 | Closed | Inspection Finished
113 | C | Mechanical Packages | Control Valve For Raw Meal Silo/Kiln Feeding System Valve | TCDRI | Zhejiang HENT Electromechanic Engineering Co.,Ltd | 2024-06-30 | 2024-04-10 | Closed | first FOR site
114 | C | Mechanical Packages | Wagon Bulk Loader | TCDRI | Jiangsu Green Mechanical Co., Ltd | 2024-04-04 | 2024-01-22 | Closed | first FOR site
115 | C | Mechanical Packages | Truck Bulk Loader | TCDRI | Jiangsu Green Mechanical Co., Ltd | 2024-03-03 | 2024-01-22 | Closed | first FOR site
116 | C | Mechanical Packages | Wagon Tippler | LNVT | Rice Lake Weighing Systems India Limited | 2024-04-27 | 2024-05-23 | Closed | Mechanical Manufacturing
117 | C | Mechanical Packages | Truck Tippler | LNVT | Perfect Hydrotech | 2024-04-27 | 2024-05-16 | Closed | Mechanical Manufacturing
118 | C | Mechanical Packages | Process Bag House | TCDRI | SINOMA-TCDRI | 2024-04-14 | 2024-04-22 | Closed | Package Finished
119 | C | Mechanical Packages | Nuisance Bag Filter | LNVT | Thermax | 2024-07-27 | 2024-08-13 | Closed | Drawings Submitted
120 | C | Mechanical Packages | Grate Cooler Fan | LNVT | Reitz | 2024-05-11 | 2024-06-27 | Closed | Raw Material Prepared
121 | C | Mechanical Packages | Process Fan | LNVT | Howden Air and Gas India Private Limited | 2024-05-11 | 2024-05-06 | Closed | Mechanical Manufacturing
122 | C | Mechanical Packages | Small Fan | LNVT |  | 2024-07-27 | 2024-08-20 | Closed | Drawings Submitted
123 | C | Mechanical Packages | Roots Blower | TCDRI | Shandong Tomorrow | 2024-06-29 | 2024-05-22 | Closed | first FOR site
124 | C | Mechanical Packages | Air Compressor | TCDRI | Atlas Copco (SHANGHAI) | 2024-06-14 | 2024-06-04 | Closed | Package Finished
125 | C | Mechanical Packages | Air Cannon | TCDRI | NanjingHerman Technical Co., Ltd | 2024-05-05 | 2024-04-18 | Closed | Inspection Finished
126 | C | Mechanical Packages | Air Tank | TCDRI | Tianjin Lanxing Oil and Gas Equipment Manufacturing Co., Ltd. | 2024-06-14 | 2024-06-04 | Closed | First FOR Site
127 | C | Mechanical Packages | Air Conditioner | LNVT |  | 2024-08-26 |  | Open | Technical Clarification
128 | C | Mechanical Packages | Ventilation System | TCDRI |  | 2024-08-26 |  | Closed | LOI/PO
129 | C | Process Packages | Insulation Material | LNVT |  | 2024-10-28 | 2025-02-19 | Open | RFQ received
130 | C | Process Packages | Insulation Auxiliary Material (Steel Plate/Bolts Etc.) | LNVT |  | 2024-10-28 |  | Open | RFQ received
131 | C | Mechanical Packages | Fire Equipment (Extinguisher/Outdoor Fire Hydrant) | LNVT | Singhania System Technologists Pvt. Ltd. | 2024-10-28 | 2024-06-04 | Closed | Mechanical Manufacturing
132 | C | Mechanical Packages | Electrical Hoist | LNVT | Century Crane Engineers (P) Ltd | 2024-08-11 | 2024-11-26 | Closed | Drawings Submitted
133 | C | Mechanical Packages | Double/Single Crane | LNVT | Century Crane Engineers (P) Ltd | 2024-08-11 | 2024-11-26 | Closed | Drawings Submitted
134 | C | E&I packages | LV Motors | TCDRI | Shandong Lijiu | 2024-04-27 | 2024-05-22 | Closed | Inspection Finished
135 | C | E&I packages | Fiber Optic Cables / Ethernet Cable | LNVT |  | 2024-06-17 |  | Open | RFQ Floated
136 | C | E&I packages | Cable Trays Various Sizes | LNVT |  | 2024-06-17 |  | Open | RFQ Floated
137 | C | Mechanical Packages | Steel Engineering outsourcing/Tekla（1） | TCDRI | Nanjing Suyue Steel Structure Technology Consulting Co., Ltd | 2024-04-14 | 2024-04-30 | Closed | Drawings Submitted
138 | C | Mechanical Packages | Steel Engineering outsourcing/Tekla（2） | TCDRI | Luoyang Renli Construction Technology Co., Ltd | 2024-04-14 | 2024-04-30 | Closed | Drawings Submitted
139 | C | E&I packages | ETAP Study | TCDRI | Power Consultants LLP | 2024-03-03 | 2024-07-24 | Closed | LOI/PO
140 | C | E&I packages | E&I Engineering outsourcing | LNVT | Excel consultancy | 2024-03-03 | 2024-03-19 | Closed | Drawings Submitted

## Statutory Approvals
Sr No | Category | Activity Name | Authority | Responsibility | Plan Date | Expected/ Actual Date | Remarks | Status
1 | C | CGWA clearance / Permission to extract ground water | Member Secretary, Central Ground Water Authority, New Delhi or to the Regional Director, Central Ground Water Board of concerned State | Sudhakar Pandey | 2024-03-30 | 2024-03-30 |  | Achieved
2 | C | MoEF / SIEAA clearance | MoEF / SIEAA | Sudhakar Pandey | 2024-03-30 | 2024-03-30 |  | Achieved
3 | C | Consent to Establish | State Pollution Control Board | Sudhakar Pandey | 2024-03-30 | 2024-03-30 |  | Achieved
4 | C | Consent to operate | State Pollution Control Board | Sudhakar Pandey | 2025-08-30 | 2025-08-30 | Required before commissioning | Balance
5 | C | Silos and packing plant certification | Weights & Measures Dept | Sudhakar Pandey | 2025-08-30 | 2025-08-30 | Required before commissioning | Balance
6 | C | Construction drawing approval as per factories act | Chief Inspector of Factories | Sudhakar Pandey | 2024-07-31 | 2024-07-31 |  | Balance
7 | C | MoEF / SIEAA clearance for Mines | MoEF / SIEAA | Sudhakar Pandey | 2024-08-30 | 2024-08-30 |  | Balance
8 | C | Consent to Establish for Mines | State Pollution Control Board | Sudhakar Pandey | 2024-09-30 | 2024-09-30 |  | Balance
9 | C | Consent to Operate mines | State Pollution Control Board | Sudhakar Pandey | 2024-08-30 | 2024-08-30 |  | Balance
10 | C | Fire Clearance | Divisional Fire Officer | Sudhakar Pandey | 2025-05-31 | 2025-05-31 | Required before commissioning | Balance
11 | C | Approval from Railways (FSR, IPA, DPR & ESP) | DRM/GM Railways | Sudhakar Pandey | 2024-07-20 | 2024-07-30 | DPR & ESP completed date on 05-Jul-24 Pending at DRM/GM office at Secunderabad | Balance
12 | C | CTE for Batching Plant | State Pollution Control Board | Sudhakar Pandey | 2024-03-30 | 2024-03-30 |  | Achieved
13 | C | CTO for Batching Plant | State Pollution Control Board | Sudhakar Pandey | 2024-03-30 | 2024-03-30 |  | Achieved
14 | C | 220KV Work Start approval | State Electrical Board | Sudhakar Pandey | 2024-07-30 | 2024-07-30 | In Progress | Balance

## Safety Statistics
Summary | Statistics
Total Mhr | 247369
LTI | NIL
Man Hr/LTI | NIL

## Information Icon
S No | Description | Data
1 | Project Name | Maratha CU
2 | Plant Capacity | 10000 TPD
3 | Project Partners | Image Attached
4 | Project Overview | Maratha Project is Brown Field Expansion Project Located in a City of Korpana, Maharastra. The closest railway station to Ambuja Maratha Cement Works is Chandrapur Railway Station.For air travel, you can use the Nearest Airport is Nagpur, which is approximately 150 KM away from the cement works.
5 | Overall Progress | This page will provide a brief summary of Project
6 | Procurement Status | This page will provide a detail status of Procurement and Ordering
7 | Engineering | This page will provide a detail progress of Engineering (Mech, Process and Civil design)
8 | Construction | This page will provide a detail phases of construction with Critical structures
9 | Delivery | This page will provide a Status of Workshop fabrication, Equipment and Consumables availability
10 | Commissioning | This page will provide brief on when the production can start
11 | SPI | The Schedule Performance Index (SPI) is a measure of schedule efficiency, expressed as the ratio of earned value to planned value. If the value of SPI less than 1 (project behind schedule), of 1 (project on schedule), or greater than 1 (project ahead of schedule).
12 | Project Partners | Technology Suppliers Crusher – TCDRI/L&T Stacker Reclaimer – TCDRI/Takraf Raw Mill – TCDRI Coal Mill – TCDRI Kiln – TCDRI Cooler – TCDRI Wagon Tippler – TCDRI/L&T E&I – Under Ordering Engineering Consultant HOLTEC Engineering TCDRI BOE (Value Engineering) Service Providers Civil – TCDRI/LNVT Mechanical – TCDRI/LNVT E&I – TCDRI/LNVT PMC Consultant BOE Consulting

## SPI
Date | SPI
2024-03-01 | 1
2024-04-01 | 1
2024-05-01 | 1
2024-06-01 | 1
2024-07-01 | 1
2024-08-01 | 0.91
2024-09-01 | 0.91
2024-10-01 | 0.91
2024-11-01 | 0.9
2024-12-01 | 0.88
2025-01-01 | 1
2025-02-01 | 0.94
2025-03-01 | 0.90157
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01

## Delivery - Critical
S No | Department | Sub Phase 1 | Item Description | Equipment No | Target Date | Expected Date | Vendor Name | Overdue (In Days) | Impact Project End Date | Status | Annotations
1 | Mechanical | Equipments
2 | Mechanical | Equipments
3 | Mechanical | Equipments
4 | Mechanical | Equipments
5 | Mechanical | Equipments
6 | Mechanical | Equipments
7 | Mechanical | Equipments
8 | Mechanical | Equipments
9 | Mechanical | Equipments
10 | Mechanical | Equipments
11 | Mechanical | Equipments
12 | Mechanical | Equipments
13 | Mechanical | Equipments
14 | Mechanical | Equipments
15 | Mechanical | Equipments
16 | Mechanical | Equipments
17 | Mechanical | Equipments
18 | Mechanical | Equipments
19 | Mechanical | Equipments
20 | Mechanical | Equipments
21 | Mechanical | Equipments
22 | Mechanical | Equipments
23 | Mechanical | Equipments
24 | Mechanical | Equipments
25 | Mechanical | Equipments
26 | Mechanical | Equipments
27 | Mechanical | Equipments
28 | Mechanical | Equipments
29 | Mechanical | Equipments
30 | Mechanical | Equipments
31 | Mechanical | Equipments
32 | Mechanical | Equipments
33 | Mechanical | Equipments
34 | Mechanical | Equipments
35 | Mechanical | Equipments
36 | Mechanical | Equipments
37 | Mechanical | Equipments
38 | Mechanical | Equipments
39 | Mechanical | Equipments
40 | Mechanical | Equipments
41 | Mechanical | Equipments
42 | Mechanical | Equipments
43 | Mechanical | Equipments
44 | Mechanical | Equipments
45 | Mechanical | Equipments
46 | Mechanical | Equipments
47 | Mechanical | Equipments
48 | Mechanical | Equipments
49 | Mechanical | Equipments
50 | Mechanical | Equipments
51 | Mechanical | Equipments
52 | Mechanical | Equipments
53 | Mechanical | Equipments
54 | Mechanical | Equipments
55 | Mechanical | Equipments
56 | Mechanical | Equipments
57 | Mechanical | Equipments
58 | Mechanical | Equipments
59 | Mechanical | Equipments
60 | Mechanical | Equipments
61 | Mechanical | Equipments
62 | Mechanical | Equipments
63 | Mechanical | Equipments
64 | Mechanical | Equipments
65 | Mechanical | Equipments
66 | Mechanical | Equipments
67 | Mechanical | Equipments
68 | Mechanical | Equipments
69 | Mechanical | Equipments
70 | Mechanical | Equipments
71 | Mechanical | Equipments
72 | Mechanical | Equipments
73 | Mechanical | Equipments
74 | Mechanical | Equipments
75 | Mechanical | Equipments
76 | Mechanical | Equipments
77 | Mechanical | Equipments
78 | Mechanical | Equipments
79 | Mechanical | Equipments
80 | Mechanical | Equipments
81 | Mechanical | Equipments
82 | Mechanical | Equipments
83 | Mechanical | Equipments
84 | Mechanical | Equipments
85 | Mechanical | Equipments
86 | Mechanical | Equipments
87 | Mechanical | Equipments
88 | Mechanical | Equipments
89 | Mechanical | Equipments
90 | Mechanical | Equipments
91 | Mechanical | Equipments
92 | Mechanical | Equipments
93 | Mechanical | Equipments
94 | Mechanical | Equipments
95 | Mechanical | Equipments
96 | Mechanical | Equipments
97 | Mechanical | Equipments
98 | Mechanical | Equipments
99 | Mechanical | Equipments
100 | Mechanical | Equipments
101 | Mechanical | Equipments
102 | Mechanical | Equipments
103 | Mechanical | Equipments
104 | Mechanical | Equipments
105 | Mechanical | Equipments
106 | Mechanical | Equipments
107 | Mechanical | Equipments
108 | Mechanical | Equipments
109 | Mechanical | Equipments
110 | Mechanical | Equipments
111 | Mechanical | Equipments
112 | Mechanical | Equipments
113 | Mechanical | Equipments
114 | Mechanical | Equipments
115 | Mechanical | Equipments
116 | Mechanical | Equipments
117 | Mechanical | Equipments
118 | Mechanical | Equipments
119 | Mechanical | Equipments
120 | Mechanical | Equipments
121 | Mechanical | Equipments
122 | Mechanical | Equipments
123 | Mechanical | Equipments
124 | Mechanical | Equipments
125 | Mechanical | Equipments
126 | Mechanical | Equipments
127 | Mechanical | Equipments
128 | Mechanical | Equipments
129 | Mechanical | Equipments
130 | Mechanical | Equipments
131 | Mechanical | Equipments
132 | Mechanical | Equipments
133 | Mechanical | Equipments
134 | Mechanical | Equipments
135 | Mechanical | Equipments
136 | Mechanical | Equipments
137 | Mechanical | Equipments
138 | Mechanical | Equipments
139 | Mechanical | Equipments
140 | Mechanical | Equipments
141 | Mechanical | Equipments
142 | Mechanical | Equipments
143 | Mechanical | Equipments
144 | Mechanical | Equipments
145 | Mechanical | Equipments
146 | Mechanical | Equipments
147 | Mechanical | Equipments
148 | Mechanical | Equipments
149 | Mechanical | Equipments
150 | Mechanical | Equipments
151 | Mechanical | Equipments
152 | Mechanical | Equipments
153 | Mechanical | Equipments
154 | Mechanical | Equipments
155 | Mechanical | Equipments
156 | Mechanical | Equipments
157 | Mechanical | Equipments
158 | Mechanical | Equipments
159 | Mechanical | Equipments
160 | Mechanical | Equipments
161 | Mechanical | Equipments
162 | Mechanical | Equipments
163 | Mechanical | Equipments
164 | Mechanical | Equipments
165 | Mechanical | Equipments
166 | Mechanical | Equipments
167 | Mechanical | Equipments
168 | Mechanical | Equipments
169 | Mechanical | Equipments
170 | Mechanical | Equipments
171 | Mechanical | Equipments
172 | Mechanical | Equipments
173 | Mechanical | Equipments
174 | Mechanical | Equipments
175 | Mechanical | Equipments
176 | Mechanical | Equipments
177 | Mechanical | Equipments
178 | Mechanical | Equipments
179 | Mechanical | Equipments
180 | Mechanical | Equipments
181 | Mechanical | Equipments
182 | Mechanical | Equipments
183 | Mechanical | Equipments
184 | Mechanical | Equipments
185 | Mechanical | Equipments
186 | Mechanical | Equipments
187 | Mechanical | Equipments
188 | Mechanical | Equipments
189 | Mechanical | Equipments
190 | Mechanical | Equipments
191 | Mechanical | Equipments
192 | Mechanical | Equipments
193 | Mechanical | Equipments
194 | Mechanical | Equipments
195 | Mechanical | Equipments
196 | Mechanical | Equipments
197 | Mechanical | Equipments
198 | Mechanical | Equipments
199 | Mechanical | Equipments
200 | Mechanical | Equipments
201 | Mechanical | Equipments
202 | Mechanical | Equipments
203 | Mechanical | Equipments
204 | Mechanical | Equipments
205 | Mechanical | Equipments
206 | Mechanical | Equipments
207 | Mechanical | Equipments
208 | Mechanical | Equipments
209 | Mechanical | Equipments
210 | Mechanical | Equipments
211 | Mechanical | Equipments
212 | Mechanical | Equipments
213 | E&I | Electrial Items | HT Cables
214 | E&I | Electrial Items | LT Cables
215 | E&I | Electrial Items | Signal Cables
216 | E&I | Electrial Items | LT Motors
217 | E&I | Electrial Items | HT Motors
218 | E&I | Electrial Items | Panels
219 | E&I | Electrial Items | Transformers
220 | E&I | Electrial Items | Cable Tray
221 | E&I | Electrial Items | Weigh Bridge

## Engg Drill page
Sr No | Department | Sub Phase 1 | Sub Phase 2 | Description | Plan Date | Actual Date | Status
1 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | 3D MODEL - MT002-TDIC-GA10-2120000-0000 | 2024-06-15 | 2024-06-15 | Closed
2 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN LAYOUT - MT002-TDIC-GA10-2120000-0001 | 2024-02-06 | 2024-02-06 | Closed
3 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | SECTION 1-1 - MT002-TDIC-GA10-2120000-0002 | 2024-02-06 | 2024-02-06 | Closed
4 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | SECTION 2-2, 3-3, 4-4 - MT002-TDIC-GA10-2120000-0003 | 2024-02-06 | 2024-02-06 | Closed
5 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN -5.000, 0.000, 4.000, 5.000-6.787, 5.000-7.437, 8.395, 19.800, 24.000 - MT002-TDIC-GA10-2120000-0004 | 2024-02-06 | 2024-02-06 | Closed
6 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN VIEW -5.000 - MT002-TDIC-GA10-2120000-0005 | 2024-02-06 | 2024-03-04 | Closed
7 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN VIEW -9.000 - MT002-TDIC-GA10-2120000-0006 | 2024-02-06 | 2024-03-04 | Closed
8 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN FOUNDATION -5.000, 0.000, 4.000, 5.000-6.787, 5.000-7.437, 6.600, 8.359 - MT002-TDIC-GA11-2120000-0001 | 2024-03-04 | 2024-02-06 | Closed
9 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PLAN FOUNDATION 14.715, 19.800,24.000 - MT002-TDIC-GA11-2120000-0002 | 2024-03-04 | 2024-02-06 | Closed
10 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | APRON FEEDER EQUIPMENT DRAWING - MT002-TDIC-ME12-212AF01-0001 | 2024-05-14 | 2024-08-14 | Closed
11 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | WOBBLER FEEDER EQUIPMENT DRAWING - MT002-TDIC-ME12-212WQ01-0001 | 2024-05-14 | 2024-08-14 | Closed
12 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | FLOW SHEET - MT002-TDIC-ME01-2120000-0001 | 2024-02-06 | 2024-02-06 | Closed
13 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-2120000-0001 | 2024-02-06 | 2024-02-06 | Closed
14 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | LIMESTONE CRUSHING SPRAY DUST SUPPRESSIONG SYSTEM 1 | 2024-10-24 | 2024-08-14 | Closed
15 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | LIMESTONE CRUSHING SPRAY DUST SUPPRESSIONG SYSTEM 2 | 2024-10-24 | 2024-08-14 | Closed
16 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | EQUIPMENT DRAWING - MT002-TDIC-ME12-2120000-0001 | 2024-10-24 | 2024-08-14 | Closed
17 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | EQUIPMENT DRAWING - MT002-TDIC-ME12-2120000-0002 | 2024-10-24 | 2024-08-14 | Closed
18 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | EQUIPMENT DRAWING - MT002-TDIC-ME12-2120000-0003 | 2024-10-24 | 2024-08-14 | Closed
19 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | APRON FEEDER EQUIPMENT DRAWING | 2024-10-24 | 2024-08-14 | Closed
20 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | WOBBLER FEEDER EQUIPMENT DRAWING | 2024-10-24 | 2024-08-14 | Closed
21 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | EQUIPMENT DRAWING - MT002-TDIC-ME12-2120000-0008 | 2024-10-24 | 2024-09-21 | Closed
22 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | EQUIPMENT DRAWING - MT002-TDIC-ME12-2120000-0009 | 2024-10-24 | 2024-09-21 | Closed
23 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | AIR COMPRESSOR equipment drawing | 2024-10-24 | 2024-08-16 | Closed
24 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | AIR COMPRESSOR equipment data sheet | 2024-10-24 | 2024-08-16 | Closed
25 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PUMP STATION ASSLY FOR APRON, IMPACTOR | 2024-10-24 | 2024-09-05 | Closed
26 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | PUMP STATION ASSLY FOR WOBBLER | 2024-10-24 | 2024-09-05 | Closed
27 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | BAG FILTER Equipment drawing | 2024-10-24 | 2024-09-18 | Closed
28 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | LIMESTONE CRUSHING SPRAY DUST SUPPRESSIONG SYSTEM 1 - MT002-TDIC-ME12-212IJ01-0001 | 2024-10-24 | 2024-06-08 | Closed
29 | Mechanical | Mechanical & Process | 212 - LIMESTONE CRUSHER | LIMESTONE CRUSHING SPRAY DUST SUPPRESSIONG SYSTEM 2 - MT002-TDIC-ME12-212IJ01-0002 | 2024-10-24 | 2024-06-08 | Closed
30 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | LAYOUT - MT002-TDIC-GA01-2920000-0001 | 2024-02-22 | 2024-02-22 | Closed
31 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | LAYOUT - MT002-TDIC-GA01-2920000-0002 | 2024-02-22 | 2024-02-22 | Closed
32 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PLAN LAYOUT - MT002-TDIC-GA10-2920000-0001 | 2024-02-22 | 2024-02-22 | Closed
33 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PLAN 3.000, 3.500, 6.000, 6.500, 15.500, 22.500, SECTION 1-1 - MT002-TDIC-GA10-2920000-0002 | 2024-02-22 | 2024-02-22 | Closed
34 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | VERTICAL SECTION OF NO.2 BELT CONVEYOR - MT002-TDIC-GA10-2920000-0101 | 2024-02-22 | 2024-02-22 | Closed
35 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | VERTICAL SECTION OF NO.3 BELT CONVEYOR - MT002-TDIC-GA10-2920000-0201 | 2024-02-22 | 2024-02-22 | Closed
36 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | VERTICAL SECTION OF NO.4 BELT CONVEYOR - MT002-TDIC-GA10-2920000-0301 | 2024-02-22 | 2024-02-22 | Closed
37 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FOUNDATION DRAWING - MT002-TDIC-GA11-2920000-0101 | 2024-05-11 |  | Open
38 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FOUNDATION DRAWING - MT002-TDIC-GA11-2920000-0201 | 2024-05-11 |  | Open
39 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FOUNDATION DRAWING - MT002-TDIC-GA11-2920000-0301 | 2024-05-11 |  | Open
40 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FOUNDATION DRAWING - MT002-TDIC-GA11-2920000-0401 | 2024-05-11 |  | Open
41 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FOUNDATION DRAWING - MT002-TDIC-GA11-2920000-0501 | 2024-05-11 |  | Open
42 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FLOW SHEET - MT002-TDIC-ME01-2920000-0001 | 2024-02-22 | 2024-02-22 | Closed
43 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FLOW SHEET - MT002-TDIC-ME01-2920000-0101 | 2024-02-22 | 2024-02-22 | Closed
44 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FLOW SHEET - MT002-TDIC-ME01-2920000-0201 | 2024-02-22 | 2024-02-22 | Closed
45 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | FLOW SHEET - MT002-TDIC-ME01-2920000-0301 | 2024-02-22 | 2024-02-22 | Closed
46 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-2920000-0001 | 2024-02-22 | 2024-02-22 | Closed
47 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-2920000-0101 | 2024-02-22 | 2024-02-22 | Closed
48 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-2920000-0201 | 2024-02-22 | 2024-02-22 | Closed
49 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-2920000-0301 | 2024-02-22 | 2024-02-22 | Closed
50 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | BELT WEIGHER equipment drawing - MT002-TDIC-ME12-292BW01-0001 | 2024-05-11 | 2024-08-06 | Closed
51 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | LOAD CELL equipment drawing - MT002-TDIC-ME12-292LC01-0001 | 2024-07-23 | 2024-08-09 | Closed
52 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | BELT CONVEYOR 2nd batch equipment drawing - MT002-TDIC-ME12-292BC04-0001 | 2024-07-23 | 2024-08-15 | Closed
53 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0004 | 2024-07-23 |  | Open
54 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0005 | 2024-07-23 |  | Open
55 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0006 | 2024-12-24 |  | Open
56 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0007 | 2024-12-24 |  | Open
57 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0008 | 2024-12-24 |  | Open
58 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0009 | 2024-12-24 |  | Open
59 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0010 | 2024-12-24 |  | Open
60 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0011 | 2024-12-24 |  | Open
61 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0012 | 2024-12-24 |  | Open
62 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0013 | 2024-12-24 |  | Open
63 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0014 | 2024-12-24 |  | Open
64 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0015 | 2024-12-24 |  | Open
65 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0016 | 2024-12-24 |  | Open
66 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | EQUIPMENT DRAWING - MT002-TDIC-ME12-2920000-0017 | 2024-12-24 |  | Open
67 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | METAL SEPARATOR DATA SHEET - MT002-TDIC-ME10-292MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
68 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-292MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
69 | Mechanical | Mechanical & Process | 292 - LIMESTONE TRANSPORT TO STORAGE | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-312MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
70 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | PLAN LAYOUT - MT002-TDIC-GA10-3120000-0001 | 2024-05-11 | 2024-07-24 | Closed
71 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | SECTION 1-1 - MT002-TDIC-GA10-3120000-0002 | 2024-05-11 | 2024-07-24 | Closed
72 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | SECTION 2-2 - MT002-TDIC-GA10-3120000-0003 | 2024-05-11 | 2024-07-24 | Closed
73 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | SECTION 3-3 - MT002-TDIC-GA10-3120000-0004 | 2024-05-11 | 2024-07-24 | Closed
74 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | SECTION C-C,D-D,PLAN FOUNDATION ±0.000,4.000 - MT002-TDIC-GA10-3120000-0005 | 2024-05-11 | 2024-07-24 | Closed
75 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | PLAN XXX；SECTION 5-5，6-6 - MT002-TDIC-GA10-3120000-0006 | 2024-05-11 |  | Open
76 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | PLANFOUNDATION XXX - MT002-TDIC-GA11-3120000-0001 | 2024-05-11 | 2024-07-28 | Closed
77 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | PLANFOUNDATION XXX - MT002-TDIC-GA11-3120000-0002 | 2024-05-11 | 2024-09-28 | Closed
78 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | FLOW SHEET - MT002-TDIC-ME01-3120000-0001 | 2024-05-11 | 2024-07-24 | Closed
79 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-3120000-0001 | 2024-05-11 | 2024-07-24 | Closed
80 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | 3D MODELING - MT002-TDIC-GA10-3120000-0000 | 2024-05-11 | 2024-07-24 | Closed
81 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-3120000-0001 | 2024-05-11 |  | Open
82 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | Piping- Bill of quantities - MT002-TDIC-ME51-3120000-0001 | 2024-05-11 |  | Open
83 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | GA DRAWING FOR LUFFING STACKER - MT002-TDIC-ME12-292ST01-0001 | 2024-05-11 | 2024-06-23 | Closed
84 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | GA DRAWING FOR LUFFING STACKER - MT002-TDIC-ME12-292ST01-0002 | 2024-05-11 | 2024-06-23 | Closed
85 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | STOCKPILE LAYOUT FOR LIMESTONE SYSTEM(292ST01&312RE01) - MT002-TDIC-ME12-292ST01-0003 | 2024-05-11 | 2024-06-23 | Closed
86 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | STOCKPILE LAYOUT FOR LIMESTONE SYSTEM(292ST01&312RE01) - MT002-TDIC-ME12-292ST01-0004 | 2024-05-11 | 2024-06-23 | Closed
87 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | WHEEL LOAD DATA FOR LUFFING STACKER - MT002-TDIC-ME12-292ST01-0005 | 2024-05-11 | 2024-06-23 | Closed
88 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR LUFFING STACKER (292ST01) | 2024-05-11 | 2024-07-02 | Closed
89 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR LUFFING STACKER (292ST01) | 2024-05-11 | 2024-07-02 | Closed
90 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR LUFFING STACKER (292ST01) | 2024-05-11 | 2024-07-02 | Closed
91 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR LUFFING STACKER (292ST01) BUFFER TG-514 | 2024-05-11 | 2024-07-02 | Closed
92 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | GA DRAWING FOR BRIDGE RECLAIMER - MT002-TDIC-ME12-312RE01-0001 | 2024-05-11 | 2024-06-23 | Closed
93 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | WHEEL LOAD DATA OF BRIDGE RECLAIMER - MT002-TDIC-ME12-312RE01-0002 | 2024-05-11 | 2024-06-23 | Closed
94 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER (312RE01) | 2024-05-11 | 2024-07-02 | Closed
95 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER (312RE01) | 2024-05-11 | 2024-07-02 | Closed
96 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER (312RE01) | 2024-05-11 | 2024-07-02 | Closed
97 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | RAIL FIXING AND FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER (312RE01) BUFFER TG-514 | 2024-05-11 | 2024-07-02 | Closed
98 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | DATA SHEET OF STACKER & RECLAIMER - MT002-TDIC-ME10-292ST01-0001 | 2024-11-13 |  | Open
99 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BELT SCALE 293BW01 - MT002-TDIC-ME12-292BW01-0001 | 2024-05-11 |  | Open
100 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BELT SCALE 313BW01 - MT002-TDIC-ME12-312BW01-0001 | 2024-05-11 |  | Open
101 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BUTTERFLY DAMPER 294BV01 - MT002-TDIC-ME12-292BV01-0001 | 2024-10-11 |  | Open
102 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BUTTERFLY DAMPER 294BV02 - MT002-TDIC-ME12-292BV02-0001 | 2024-10-11 |  | Open
103 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | TWO-WAY VALVE 294MW01 - MT002-TDIC-ME12-292MW01-0001 | 2024-10-11 |  | Open
104 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | TWO-WAY VALVE 294MW02 - MT002-TDIC-ME12-292MW02-0001 | 2024-10-11 |  | Open
105 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | NEEDLE GATE 312NG01 - MT002-TDIC-ME12-312NG01-0001 | 2024-10-11 |  | Open
106 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | NEEDLE GATE 312NG02 - MT002-TDIC-ME12-312NG02-0001 | 2024-10-11 |  | Open
107 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BAG FILTER 294BF01 - MT002-TDIC-ME12-292BF01-0001 | 2024-10-11 | 2024-09-02 | Closed
108 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BAG FILTER 294BF02 - MT002-TDIC-ME12-292BF02-0001 | 2024-10-11 | 2024-09-02 | Closed
109 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | BAG FILTER 312BF01 - MT002-TDIC-ME12-312BF01-0001 | 2024-10-11 | 2024-09-02 | Closed
110 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | FAN 294FN01 - MT002-TDIC-ME12-292 FN01-0001 | 2024-10-11 | 2024-09-02 | Closed
111 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | FAN 294FN02 - MT002-TDIC-ME12-292 FN02-0001 | 2024-10-11 | 2024-09-02 | Closed
112 | Mechanical | Mechanical & Process | 312-1-LIMESTONE TRANSPORT AND STORAGE | FAN 312FN01 - MT002-TDIC-ME12-312 FN01-0001 | 2024-10-11 | 2024-08-30 | Closed
113 | Mechanical | Mechanical & Process | 312-2- LIMESTONE CONVEYING TO EIXSTING LINE | PLAN LAYOUT - MT002-TDIC-GA10-3120000-0101 | 2024-05-11 |  | Open
114 | Mechanical | Mechanical & Process | 312-2- LIMESTONE CONVEYING TO EIXSTING LINE | SECTION 1-1 - MT002-TDIC-GA10-3120000-0102 | 2024-05-11 |  | Open
115 | Mechanical | Mechanical & Process | 312-2- LIMESTONE CONVEYING TO EIXSTING LINE | SECTION 2-2 - MT002-TDIC-GA10-3120000-0103 | 2024-05-11 |  | Open
116 | Mechanical | Mechanical & Process | 312-2- LIMESTONE CONVEYING TO EIXSTING LINE | PLAN FOUNDATION XXX - MT002-TDIC-GA11-3120000-0101 | 2024-05-11 |  | Open
117 | Mechanical | Mechanical & Process | 312-2- LIMESTONE CONVEYING TO EIXSTING LINE | Belt Conveyor 312BC03 - MT002-TDIC-ME12-312BC03-0001 | 2024-10-11 | 2024-09-29 | Closed
118 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | 3D MODELING - MT002-TDIC-GA10-3320000-0000 | 2024-05-25 | 2024-05-25 | Closed
119 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN LAYOUT(1) - MT002-TDIC-GA10-3320000-0001 | 2024-05-25 | 2024-05-25 | Closed
120 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | SECTION 1-1 - MT002-TDIC-GA10-3320000-0002 | 2024-05-25 | 2024-05-25 | Closed
121 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | SECTION 2-2,3-3 - MT002-TDIC-GA10-3320000-0003 | 2024-05-25 | 2024-05-25 | Closed
122 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | SECTION 4-4 - MT002-TDIC-GA10-3320000-0004 | 2024-05-25 | 2024-05-25 | Closed
123 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN ±0.00,4.700,10.800,23.000,26.300,29.500,33.700 - MT002-TDIC-GA10-3320000-0005 | 2024-05-25 | 2024-05-25 | Closed
124 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN LAYOUT/PLAN LAYOUT(2) - MT002-TDIC-GA10-3320000-0101 | 2024-04-20 | 2024-02-06 | Closed
125 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | SECTION 1-1、SECTION 5-5 - MT002-TDIC-GA10-3320000-0102 | 2024-04-20 | 2024-02-06 | Closed
126 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | SECTION 2-2、SECTION 6-6 - MT002-TDIC-GA10-3320000-0103 | 2024-04-20 | 2024-02-06 | Closed
127 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN 21.000-30.600, 25.000-34.000, PLAN 28.100,33.500, 43.800 - MT002-TDIC-GA10-3320000-0104 | 2024-04-20 | 2024-02-06 | Closed
128 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN FOUNDATION 4.700,8.000,11.200,16.000 - MT002-TDIC-GA11-3320000-0001 | 2024-05-25 | 2024-05-25 | Closed
129 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN FOUNDATION19.000,22.200,23.000,26.300,28.700,29.500,33.700 - MT002-TDIC-GA11-3320000-0002 | 2024-05-25 | 2024-05-25 | Closed
130 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN ±0.000-14.500,11.000-41.700,DETAIL D1-D5 - MT002-TDIC-GA11-3320000-0003 | 2024-05-25 | 2024-05-25 | Closed
131 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN FOUNDATION 28.100,33.500, 41.100,43.800,51.000,DETAIL D6-D7 - MT002-TDIC-GA11-3320000-0101 | 2024-04-20 | 2024-05-24 | Closed
132 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PLAN FOUNDATION 21.000-30.600,25.000-34.000 - MT002-TDIC-GA11-3320000-0102 | 2024-04-20 | 2024-05-24 | Closed
133 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | FLOW SHEET - MT002-TDIC-ME01-3320000-0001 | 2024-04-20 | 2024-02-06 | Closed
134 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-3320000-0001 | 2024-04-20 | 2024-02-06 | Closed
135 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | 3D MODELING - MT002-TDIC-GA10-3320000-0100 | 2024-04-20 | 2024-05-24 | Closed
136 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | PROCESS PIPING DRAWING - MT002-TDIC-ME50-3320000-0001 | 2024-11-13 |  | Open
137 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | LIST OF PROCESS PIPING MATERIAL - MT002-TDIC-ME51-3320000-0001 | 2024-11-13 |  | Open
138 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Load Cell 313LC01-03 - MT002-TDIC-ME12-313LC01-0001 | 2024-10-11 |  | Open
139 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Load Cell X92LC01-03 - MT002-TDIC-ME12-X92LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
140 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Load Cell X92LC04-06 - MT002-TDIC-ME12-X92LC04-0001 | 2024-10-11 | 2024-08-09 | Closed
141 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Needle Gate 332NG01 - MT002-TDIC-ME12-332NG01-0001 | 2024-10-11 | 2024-08-18 | Closed
142 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Needle Gate 332NG02 - MT002-TDIC-ME12-332NG02-0001 | 2024-10-11 | 2024-08-18 | Closed
143 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Needle Gate 332NG03 - MT002-TDIC-ME12-332NG03-0001 | 2024-10-11 | 2024-08-18 | Closed
144 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Weigh feeder 332WF01 - MT002-TDIC-ME12-332WF01-0001 | 2024-10-11 | 2024-08-27 | Closed
145 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Weigh feeder 332WF02 - MT002-TDIC-ME12-332WF02-0001 | 2024-10-11 | 2024-08-27 | Closed
146 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Weigh feeder 332WF03 - MT002-TDIC-ME12-332WF03-0001 | 2024-10-11 | 2024-08-27 | Closed
147 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Load Cell 332LC01-03 - MT002-TDIC-ME12-332LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
148 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Load Cell 332LC04-06 - MT002-TDIC-ME12-332LC04-0001 | 2024-10-11 | 2024-08-09 | Closed
149 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Needle Gate 332NG05 - MT002-TDIC-ME12-332NG05-0001 | 2024-10-11 | 2024-08-18 | Closed
150 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Needle Gate 332NG06 - MT002-TDIC-ME12-332NG06-0001 | 2024-10-11 |  | Open
151 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Weigh feeder 332WF05 - MT002-TDIC-ME12-332WF05-0001 | 2024-10-11 |  | Open
152 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Weigh feeder 332WF06 - MT002-TDIC-ME12-332WF06-0001 | 2024-10-11 |  | Open
153 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF01 - MT002-TDIC-ME12-332BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
154 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN01 - MT002-TDIC-ME12-332FN01-0001 | 2024-10-11 | 2024-09-30 | Closed
155 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF02 - MT002-TDIC-ME12-332BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
156 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN02 - MT002-TDIC-ME12-332FN02-0001 | 2024-10-11 | 2024-09-30 | Closed
157 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF03 - MT002-TDIC-ME12-332BF03-0001 | 2024-10-11 | 2024-08-28 | Closed
158 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN03 - MT002-TDIC-ME12-332FN03-0001 | 2024-10-11 | 2024-09-30 | Closed
159 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF04 - MT002-TDIC-ME12-332BF04-0001 | 2024-10-11 | 2024-08-28 | Closed
160 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN04 - MT002-TDIC-ME12-332FN04-0001 | 2024-10-11 | 2024-09-30 | Closed
161 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF05 - MT002-TDIC-ME12-332BF05-0001 | 2024-10-11 | 2024-08-28 | Closed
162 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN05 - MT002-TDIC-ME12-332FN05-0001 | 2024-10-11 | 2024-09-30 | Closed
163 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Bag Filter 332BF06 - MT002-TDIC-ME12-332BF06-0001 | 2024-10-11 | 2024-08-28 | Closed
164 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Fan 332FN06 - MT002-TDIC-ME12-332FN06-0001 | 2024-10-11 | 2024-09-30 | Closed
165 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Conveyor 332BC01 - MT002-TDIC-ME12-332BC01-0001 | 2024-10-11 | 2024-08-08 | Closed
166 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Conveyor 332BC02 - MT002-TDIC-ME12-332BC02-0001 | 2024-10-11 | 2024-08-08 | Closed
167 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Conveyor 332BC03 - MT002-TDIC-ME12-332BC03-0001 | 2024-10-11 | 2024-08-08 | Closed
168 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Belt Conveyor 332BC04 - MT002-TDIC-ME12-332BC04-0001 | 2024-10-11 | 2024-08-08 | Closed
169 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-332MS01-0001 | 2024-10-11 | 2024-06-23 | Closed
170 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Pneumatic Arc Gate 332CM01 - MT002-TDIC-ME12-332CM01-0001 | 2024-10-11 | 2024-08-18 | Closed
171 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Pneumatic Arc Gate 332CM02 - MT002-TDIC-ME12-332CM02-0001 | 2024-10-11 | 2024-08-18 | Closed
172 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Electric Hoist 332EH01 - MT002-TDIC-ME12-332EH01-0001 | 2024-10-11 |  | Open
173 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Manual Monorail Trolley 332EH02 - MT002-TDIC-ME12-332EH02-0001 | 2024-10-11 |  | Open
174 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Manual Monorail Trolley 332EH03 - MT002-TDIC-ME12-332EH03-0001 | 2024-10-11 |  | Open
175 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Pneumatic Butterfly Damper 332BV01 - MT002-TDIC-ME12-332BV01-0001 | 2024-10-11 | 2024-08-18 | Closed
176 | Mechanical | Mechanical & Process | 332-1 RAW MILL HOPPER | Pneumatic Butterfly Damper 332BV02 - MT002-TDIC-ME12-332BV02-0001 | 2024-10-11 | 2024-08-18 | Closed
177 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | PLAN LAYOUT - MT002-TDIC-GA10-3320000-0101 | 2024-03-07 | 2024-02-05 | Closed
178 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | SECTION 1-1 - MT002-TDIC-GA10-3320000-0102 | 2024-03-07 | 2024-02-05 | Closed
179 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | SECTION 2-2 - MT002-TDIC-GA10-3320000-0103 | 2024-03-07 | 2024-02-05 | Closed
180 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | PLAN 21.000-30.600,25.000-34.000 PLAN 28.100,33.500,43.800 - MT002-TDIC-GA10-3320000-0104 | 2024-03-07 | 2024-02-05 | Closed
181 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | PLAN FOUNDATION 21.000-30.600,25.000-34.000 PLAN FOUNDATION 28.100,33.500,43.800 - MT002-TDIC-GA10-3320000-0105 | 2024-03-07 |  | Open
182 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | 3D MODELING - MT002-TDIC-GA10-3320000-0100 | 2024-03-07 |  | Open
183 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Needle Gate 332NG01 - MT002-TDIC-ME12-332NG01-0001 | 2024-10-11 | 2024-08-18 | Open
184 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Load Cell 332LC04-06 - MT002-TDIC-ME12-332LC04-0001 | 2024-10-11 |  | Open
185 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Needle Gate 332NG05 - MT002-TDIC-ME12-332NG05-0001 | 2024-10-11 |  | Open
186 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Needle Gate 332NG06 - MT002-TDIC-ME12-332NG06-0001 | 2024-10-11 |  | Open
187 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Belt Weigh feeder 332WF05 - MT002-TDIC-ME12-332WF05-0001 | 2024-10-11 | 2024-08-27 | Closed
188 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Belt Weigh feeder 332WF06 - MT002-TDIC-ME12-332WF06-0001 | 2024-10-11 | 2024-08-27 | Closed
189 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Bag Filter 332BF04 - MT002-TDIC-ME12-332BF04-0001 | 2024-10-11 | 2024-08-28 | Closed
190 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Fan 332FN04 - MT002-TDIC-ME12-332FN04-0001 | 2024-10-11 |  | Open
191 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Bag Filter 332BF05 - MT002-TDIC-ME12-332BF05-0001 | 2024-10-11 | 2024-08-28 | Closed
192 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Fan 332FN05 - MT002-TDIC-ME12-332FN05-0001 | 2024-10-11 |  | Open
193 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Bag Filter 332BF06 - MT002-TDIC-ME12-332BF06-0001 | 2024-10-11 | 2024-08-28 | Closed
194 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Fan 332FN06 - MT002-TDIC-ME12-332FN06-0001 | 2024-10-11 |  | Open
195 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Belt Conveyor 332BC03 - MT002-TDIC-ME12-332BC03-0001 | 2024-10-11 | 2024-08-08 | Closed
196 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Belt Conveyor 332BC04 - MT002-TDIC-ME12-332BC04-0001 | 2024-10-11 | 2024-08-08 | Closed
197 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Pneumatic Arc Gate 332CM01 - MT002-TDIC-ME12-332CM01-0001 | 2024-10-11 | 2024-08-18 | Closed
198 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Pneumatic Arc Gate 332CM02 - MT002-TDIC-ME12-332CM02-0001 | 2024-10-11 | 2024-08-18 | Closed
199 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Manual Monorail Trolley 332EH03 - MT002-TDIC-ME12-332EH03-0001 | 2024-10-11 |  | Open
200 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Pneumatic Butterfly Damper 332BV01 - MT002-TDIC-ME12-332BV01-0001 | 2024-10-11 | 2024-08-18 | Closed
201 | Mechanical | Mechanical & Process | 332-2 RAW MILL FEEDING | Pneumatic Butterfly Damper 332BV02 - MT002-TDIC-ME12-332BV02-0001 | 2024-10-11 |  | Open
202 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | GENERAL PLAN - MT002-TDIC-GA10-3620000-0001 | 2024-03-07 | 2024-01-08 | Closed
203 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 1-1,3-3 - MT002-TDIC-GA10-3620000-0002 | 2024-03-07 | 2024-01-08 | Closed
204 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 2-2 - MT002-TDIC-GA10-3620000-0003 | 2024-03-07 | 2024-01-08 | Closed
205 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 4-4,5-5 - MT002-TDIC-GA10-3620000-0004 | 2024-03-07 | 2024-01-08 | Closed
206 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 6-6,7-7.12-12 - MT002-TDIC-GA10-3620000-0005 | 2024-03-07 | 2024-01-08 | Closed
207 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 8-8,9-9 - MT002-TDIC-GA10-3620000-0006 | 2024-03-07 | 2024-01-08 | Closed
208 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 10-10,13-13 - MT002-TDIC-GA10-3620000-0007 | 2024-03-07 | 2024-01-08 | Closed
209 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SECTION 11-11 - MT002-TDIC-GA10-3620000-0008 | 2024-03-07 | 2024-01-08 | Closed
210 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN ±0.000 - MT002-TDIC-GA10-3620000-0009 | 2024-03-07 | 2024-01-08 | Closed
211 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN -3.150,6.500,7.000 - MT002-TDIC-GA10-3620000-0010 | 2024-03-07 | 2024-01-08 | Closed
212 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN 2.500-10.500,6.500,7.000,9.000 - MT002-TDIC-GA10-3620000-0011 | 2024-03-07 | 2024-01-08 | Closed
213 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN 13.300,16.500,16.310 - MT002-TDIC-GA10-3620000-0012 | 2024-03-07 | 2024-01-08 | Closed
214 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN 17.500,20.212,20.500,22.000,29.400 - MT002-TDIC-GA10-3620000-0013 | 2024-03-07 | 2024-01-08 | Closed
215 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION -3.150,±0.000,4.300 - MT002-TDIC-GA11-3620000-0001 | 2024-04-07 | 2024-03-22 | Closed
216 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 6.500,7.000,13.300,16.500,16.310,16.000-17.500 - MT002-TDIC-GA11-3620000-0002 | 2024-04-07 | 2024-03-22 | Closed
217 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 2.500-10.500,9.000.12.600-18.000 - MT002-TDIC-GA11-3620000-0003 | 2024-04-07 | 2024-03-22 | Closed
218 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 17.500,20.212,20.500,22.000 - MT002-TDIC-GA11-3620000-0004 | 2024-04-07 | 2024-03-22 | Closed
219 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 23.000,26.500,31.900,32.100,35.100,43.400,45.000 - MT002-TDIC-GA11-3620000-0005 | 2024-04-07 | 2024-03-22 | Closed
220 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 4.500-7.000,6.500,7.000,10.000,12.700 - MT002-TDIC-GA11-3620000-0006 | 2024-04-07 | 2024-03-22 | Closed
221 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PLAN FOUNDATION 34.000,37.400,38.900,42.900 - MT002-TDIC-GA11-3620000-0007 | 2024-04-07 | 2024-03-22 | Closed
222 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | FLOW SHEET:RAW MILL GRINDING 3# - MT002-TDIC-ME01-3620000-0001 | 2024-04-07 | 2024-01-08 | Closed
223 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | FLOW SHEET:RAW MILL GRINDING 4# - MT002-TDIC-ME01-3630000-0001 | 2024-04-07 | 2024-01-08 | Closed
224 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | FLOW SHEET:RAW MEAL CONVEYING TO SILO - MT002-TDIC-ME01-3920000-0001 | 2024-04-07 | 2024-01-08 | Closed
225 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | FLOW SHEET:DEDUSTING OF KILN SYSTEM - MT002-TDIC-ME01-4220000-0001 | 2024-04-07 | 2024-01-08 | Closed
226 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | HEAT BALANCE - MT002-TDIC-ME03-362RP01-0001 | 2024-05-28 | 2024-05-28 | Closed
227 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PROCESS EQUIPMENT LIST:RAW MILL GRINDING 3# - MT002-TDIC-ME04-3620000-0001 | 2024-04-07 | 2024-01-08 | Closed
228 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PROCESS EQUIPMENT LIST:RAW MILL GRINDING 4# - MT002-TDIC-ME04-3630000-0001 | 2024-04-07 | 2024-01-08 | Closed
229 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PROCESS EQUIPMENT LIST:RAW MEAL CONVEYING TO SILO - MT002-TDIC-ME04-3920000-0001 | 2024-04-07 | 2024-01-08 | Closed
230 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PROCESS EQUIPMENT LIST:DEDUSTING OF KILN SYSTEM - MT002-TDIC-ME04-4220000-0001 | 2024-04-07 | 2024-01-08 | Closed
231 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | MT002-TDIC-ME04-3620000-0101 | 2024-04-07 | 2024-07-12 | Closed
232 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | PROCESS PIPING DRAWING - MT002-TDIC-ME50-3620000-0001 | 2024-10-11 |  | Open
233 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | LIST OF PROCESS PIPING MATERIAL - MT002-TDIC-ME51-3620000-0001 | 2024-10-11 |  | Open
234 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bucket Elevator 363BE01 - MT002-TDIC-ME12-363BE01-0001 | 2024-04-07 | 2024-03-12 | Closed
235 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bucket Elevator 363BE02 - MT002-TDIC-ME12-363BE02-0001 | 2024-04-07 | 2024-03-12 | Closed
236 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bucket Elevator 362BE01 - MT002-TDIC-ME12-362BE01-0001 | 2024-04-07 | 2024-03-12 | Closed
237 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bucket Elevator 362BE02 - MT002-TDIC-ME12-362BE02-0001 | 2024-04-07 | 2024-03-12 | Closed
238 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Bucket Elevator 363BE01 - MT002-TDIC-ME10-363BE01-0001 | 2024-04-07 | 2024-03-12 | Closed
239 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Bucket Elevator 363BE02 - MT002-TDIC-ME10-363BE02-0001 | 2024-04-07 | 2024-03-12 | Closed
240 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Bucket Elevator 362BE01 - MT002-TDIC-ME10-362BE01-0001 | 2024-04-07 | 2024-03-12 | Closed
241 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Bucket Elevator 362BE02 - MT002-TDIC-ME10-362BE02-0001 | 2024-04-07 | 2024-03-12 | Closed
242 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | 2-Φ6800 Cyclone 363CN01 - MT002-TDIC-ME12-363CN01-0001 | 2024-04-07 | 2024-03-27 | Closed
243 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | 2-Φ6800 Cyclone 362CN01 - MT002-TDIC-ME12-362CN01-0001 | 2024-04-07 | 2024-03-27 | Closed
244 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Cyclone 362CN01 - MT002-TDIC-ME10-362CN01-0001 | 2024-04-07 | 2024-03-27 | Closed
245 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Cyclone 363CN01 - MT002-TDIC-ME10-363CN01-0001 | 2024-04-07 | 2024-03-27 | Closed
246 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | EQUIPMENT DRAWING - MT002-TDIC-ME12-362FN01-0001 | 2024-04-07 | 2024-05-24 | Closed
247 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | EQUIPMENT DRAWING - MT002-TDIC-ME12-363FN01-0001 | 2024-04-07 | 2024-05-24 | Closed
248 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Process Fan 363FN01 - MT002-TDIC-ME10-362FN01-0001 | 2024-04-07 | 2024-05-28 | Closed
249 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Process Fan 362FN01 - MT002-TDIC-ME10-362FN01-0001 | 2024-04-07 | 2024-05-28 | Closed
250 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180:NEEDLE GATE - MT002-TDIC-ME12-362NG01-0001 | 2024-10-11 | 2024-03-12 | Closed
251 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180:NEEDLE GATE - MT002-TDIC-ME12-363NG01-0001 | 2024-10-11 | 2024-03-12 | Closed
252 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180: ELECTRO-HYDRAULIC ROD VALVES - MT002-TDIC-ME12-362NG04-0001 | 2024-10-11 | 2024-03-12 | Closed
253 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180: ELECTRO-HYDRAULIC ROD VALVES - MT002-TDIC-ME12-363NG04-0001 | 2024-10-11 | 2024-03-12 | Closed
254 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180:ROLLER PRESS - MT002-TDIC-ME12-363RP01-0001 | 2024-04-07 | 2024-03-12 | Closed
255 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180:ROLLER PRESS - MT002-TDIC-ME12-362RP01-0001 | 2024-04-07 | 2024-03-12 | Closed
256 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TASr-540Combined Separator 363SR01 - MT002-TDIC-ME12-363SR01-0001 | 2024-04-07 | 2024-03-12 | Closed
257 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TASr-540Combined Separator 362SR01 - MT002-TDIC-ME12-362SR01-0001 | 2024-04-07 | 2024-03-12 | Closed
258 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | HYDRAULIC SYSTEM DIAGRAM - MT002-TDIC-ME12-363HS01-0001 | 2024-04-15 | 2024-04-15 | Closed
259 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATA SHEET - MT002-TDIC-ME10-363RP01-0001 | 2024-04-04 | 2024-04-04 | Closed
260 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Separator 362SR01 - MT002-TDIC-ME10-362SR01-0001 | 2024-04-07 | 2024-03-27 | Closed
261 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TDM-512/2×7 BAG FILTER - MT002-TDIC-ME12-422BF01-0001 | 2024-04-07 | 2024-04-27 | Closed
262 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TECHNOLOGICAL PARAMETER, ELECTRICAL MATERIAL FOR EACH DUSTCOLLECTOR - MT002-TDIC-ME12-422BF01-0002 | 2024-04-07 | 2024-04-27 | Closed
263 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | BAG FILTER FOUNDATION DRAWING - MT002-TDIC-ME12-422BF01-0003 | 2024-04-07 | 2024-04-27 | Closed
264 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DRAG CHAIN FOUNDATION DRAWING - MT002-TDIC-ME12-422BF01-0004 | 2024-04-07 | 2024-04-27 | Closed
265 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Process Bag house 422BH01 - MT002-TDIC-ME10-422BH01-0001 | 2024-04-07 | 2024-04-30 | Closed
266 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | EQUIPMENT DRAWING - MT002-TDIC-ME12-422FN01-0001 | 2024-04-07 | 2024-05-24 | Closed
267 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Process Fan 422FN01 - MT002-TDIC-ME10-422FN01-0001 | 2024-04-07 | 2024-05-28 | Closed
268 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180 WEIGHT HOPPER - MT002-TDIC-ME12-3633B01-0001 | 2024-04-07 | 2024-03-12 | Closed
269 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | TRP220-180 WEIGHT HOPPER - MT002-TDIC-ME12-3623B01-0001 | 2024-04-07 | 2024-03-12 | Closed
270 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | CHUTE METAL SEPARATOR 363MS01 - MT002-TDIC-ME12-362MS01-0001 | 2024-10-11 | 2024-06-23 | Closed
271 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 363BF01 - MT002-TDIC-ME12-362BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
272 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 363BF02 - MT002-TDIC-ME12-362BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
273 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 362BF01 - MT002-TDIC-ME12-362BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
274 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 362BF02 - MT002-TDIC-ME12-362BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
275 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 393BF01 - MT002-TDIC-ME12-392BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
276 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter 393BF02 - MT002-TDIC-ME12-392BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
277 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 363FN03 - MT002-TDIC-ME12-362FN03-0001 | 2024-10-11 |  | Open
278 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 363FN02 - MT002-TDIC-ME12-362FN02-0001 | 2024-10-11 |  | Open
279 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 362FN03 - MT002-TDIC-ME12-362FN03-0001 | 2024-10-11 |  | Open
280 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 362FN02 - MT002-TDIC-ME12-362FN02-0001 | 2024-10-11 |  | Open
281 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 393FN01 - MT002-TDIC-ME12-392FN01-0001 | 2024-10-11 |  | Open
282 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Bag Filter Fan 393FN02 - MT002-TDIC-ME12-392FN02-0001 | 2024-10-11 |  | Open
283 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA01 - MT002-TDIC-ME12-392FA01-0001 | 2024-10-11 |  | Open
284 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA02 - MT002-TDIC-ME12-392FA02-0001 | 2024-10-11 |  | Open
285 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA03 - MT002-TDIC-ME12-392FA03-0001 | 2024-10-11 |  | Open
286 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA04 - MT002-TDIC-ME12-392FA04-0001 | 2024-10-11 |  | Open
287 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA05 - MT002-TDIC-ME12-392FA05-0001 | 2024-10-11 |  | Open
288 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA06 - MT002-TDIC-ME12-392FA06-0001 | 2024-10-11 |  | Open
289 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA07 - MT002-TDIC-ME12-392FA07-0001 | 2024-10-11 |  | Open
290 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide Fan 393FA08 - MT002-TDIC-ME12-392FA08-0001 | 2024-10-11 |  | Open
291 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | MT600×25000mm CHAIN CONVEYOR - MT002-TDIC-ME12-422CV03-0001 | 2024-10-11 | 2024-04-17 | Closed
292 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | MT600×21000mm CHAIN CONVEYOR - MT002-TDIC-ME12-422CV04-0001 | 2024-10-11 | 2024-04-17 | Closed
293 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | MT500×8500mm CHAIN CONVEYOR - MT002-TDIC-ME12-422CV05-0001 | 2024-10-11 | 2024-04-17 | Closed
294 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Chain conveyor 422CV03 - MT002-TDIC-ME10-422CV03-0001 | 2024-10-11 | 2024-04-17 | Closed
295 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Chain conveyor 422CV04 - MT002-TDIC-ME10-422CV04-0001 | 2024-10-11 | 2024-04-17 | Closed
296 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATASHEET of Chain conveyor 422CV05 - MT002-TDIC-ME10-422CV05-0001 | 2024-10-11 | 2024-04-17 | Closed
297 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SAMPLER - MT002-TDIC-ME12-392SM01-0001 | 2024-10-11 | 2024-04-19 | Closed
298 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SAMPLER - MT002-TDIC-ME12-392SM02-0001 | 2024-10-11 | 2024-04-19 | Closed
299 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SAMPLER - MT002-TDIC-ME12-392SM03-0001 | 2024-10-11 | 2024-04-19 | Closed
300 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | DATA SHEET - MT002-TDIC-ME10-392SM01-0001 | 2024-10-11 | 2024-04-19 | Closed
301 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SAMPLER - MT002-TDIC-ME12-422SM01-0001 | 2024-10-11 | 2024-04-19 | Closed
302 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | SAMPLER - MT002-TDIC-ME12-432SM01-0001 | 2024-10-11 | 2024-04-19 | Closed
303 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ01-0001 | 2024-11-11 | 2024-06-08 | Closed
304 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ02-0001 | 2024-11-11 | 2024-06-08 | Closed
305 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ03-0001 | 2024-11-11 | 2024-06-08 | Closed
306 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ04-0001 | 2024-11-11 | 2024-06-08 | Closed
307 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ06-0001 | 2024-11-11 | 2024-06-08 | Closed
308 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ08-0001 | 2024-11-11 | 2024-06-08 | Closed
309 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-363EJ09-0001 | 2024-11-11 | 2024-06-08 | Closed
310 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-422EJ01-0001 | 2024-11-11 | 2024-06-08 | Closed
311 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-422EJ04-0001 | 2024-11-11 | 2024-06-08 | Closed
312 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-422EJ05-0001 | 2024-11-11 | 2024-06-08 | Closed
313 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-422EJ06-0001 | 2024-11-11 | 2024-06-08 | Closed
314 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-422EJ07-0001 | 2024-11-11 | 2024-06-08 | Closed
315 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide 393AS01 - MT002-TDIC-ME12-392AS01-0001 | 2024-10-11 | 2024-04-25 | Closed
316 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide 393AS12 - MT002-TDIC-ME12-392AS12-0001 | 2024-10-11 | 2024-04-25 | Closed
317 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Air Slide 393AS13 - MT002-TDIC-ME12-392AS13-0001 | 2024-10-11 | 2024-04-25 | Closed
318 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | METAL SEPARATOR DATA SHEET - MT002-TDIC-ME10-362MS01-0001 | 2024-10-11 | 2024-06-23 | Closed
319 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Belt Conveyor 363BC02 - MT002-TDIC-ME12-362BC02-0001 | 2024-10-11 | 2024-08-08 | Closed
320 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Belt Conveyor 362BC02 - MT002-TDIC-ME12-362BC02-0001 | 2024-10-11 | 2024-08-08 | Closed
321 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Load Cell 363LC01~363LC03 - MT002-TDIC-ME12-362LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
322 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Load Cell 363LC04~363LC06 - MT002-TDIC-ME12-362LC04-0001 | 2024-10-11 | 2024-08-09 | Closed
323 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Load Cell 362LC01~362LC03 - MT002-TDIC-ME12-362LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
324 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Load Cell 362LC04~362LC06 - MT002-TDIC-ME12-362LC04-0001 | 2024-10-11 | 2024-08-09 | Closed
325 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Butterfly Damper 363BV01 - MT002-TDIC-ME12-362BV01-0001 | 2024-11-11 | 2024-08-18 | Closed
326 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 363LD01 - MT002-TDIC-ME12-362LD01-0001 | 2024-11-11 | 2024-08-18 | Closed
327 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 363LD02 - MT002-TDIC-ME12-362LD02-0001 | 2024-11-11 | 2024-08-18 | Closed
328 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 363LD03 - MT002-TDIC-ME12-362LD03-0001 | 2024-11-11 | 2024-08-18 | Closed
329 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Two-way Valve 363MW01 - MT002-TDIC-ME12-362MW01-0001 | 2024-11-11 | 2024-08-18 | Closed
330 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Two-way Valve 363MW02 - MT002-TDIC-ME12-362MW02-0001 | 2024-11-11 | 2024-08-18 | Closed
331 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Needle Gate 363NG02 - MT002-TDIC-ME12-362NG02-0001 | 2024-11-11 | 2024-08-18 | Closed
332 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Needle Gate 363NG03 - MT002-TDIC-ME12-362NG03-0001 | 2024-11-11 | 2024-08-18 | Closed
333 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 363PG02 - MT002-TDIC-ME12-362PG02-0001 | 2024-11-11 | 2024-08-18 | Closed
334 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 363PG03 - MT002-TDIC-ME12-362PG03-0001 | 2024-11-11 | 2024-08-18 | Closed
335 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 363PG04 - MT002-TDIC-ME12-362PG04-0001 | 2024-11-11 | 2024-08-18 | Closed
336 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 363PG05 - MT002-TDIC-ME12-362PG05-0001 | 2024-11-11 | 2024-08-18 | Closed
337 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Rotary Airlock 363RF03 - MT002-TDIC-ME12-362RF03-0001 | 2024-11-11 | 2024-08-18 | Closed
338 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Rotary Airlock 363RF04 - MT002-TDIC-ME12-362RF04-0001 | 2024-11-11 |  | Open
339 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Moterized Guilotine Damper 363SD01 - MT002-TDIC-ME12-362SD01-0001 | 2024-11-11 | 2024-08-18 | Closed
340 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Moterized Guilotine Damper 363SD02 - MT002-TDIC-ME12-362SD02-0001 | 2024-11-11 | 2024-08-18 | Closed
341 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 363SG03 - MT002-TDIC-ME12-362SG03-0001 | 2024-11-11 | 2024-08-18 | Closed
342 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 363SG04 - MT002-TDIC-ME12-362SG04-0001 | 2024-11-11 |  | Open
343 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 363SG06 - MT002-TDIC-ME12-362SG06-0001 | 2024-11-11 | 2024-08-18 | Closed
344 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Butterfly Damper 362BV01 - MT002-TDIC-ME12-362BV01-0001 | 2024-11-11 |  | Open
345 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 362LD01 - MT002-TDIC-ME12-362LD01-0001 | 2024-11-11 |  | Open
346 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 362LD02 - MT002-TDIC-ME12-362LD02-0001 | 2024-11-11 |  | Open
347 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 362LD03 - MT002-TDIC-ME12-362LD03-0001 | 2024-11-11 |  | Open
348 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Two-way Valve 362MW01 - MT002-TDIC-ME12-362MW01-0001 | 2024-11-11 | 2024-08-18 | Closed
349 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Two-way Valve 362MW02 - MT002-TDIC-ME12-362MW02-0001 | 2024-11-11 | 2024-08-18 | Closed
350 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Needle Gate 362NG02 - MT002-TDIC-ME12-362NG02-0001 | 2024-11-11 |  | Open
351 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Needle Gate 362NG03 - MT002-TDIC-ME12-362NG03-0001 | 2024-11-11 |  | Open
352 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 362PG02 - MT002-TDIC-ME12-362PG02-0001 | 2024-11-11 |  | Open
353 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 362PG03 - MT002-TDIC-ME12-362PG03-0001 | 2024-11-11 |  | Open
354 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 362PG04 - MT002-TDIC-ME12-362PG04-0001 | 2024-11-11 |  | Open
355 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Pneumatic Slide Gate 362PG05 - MT002-TDIC-ME12-362PG05-0001 | 2024-11-11 |  | Open
356 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Rotary Airlock 362RF03 - MT002-TDIC-ME12-362RF03-0001 | 2024-11-11 |  | Open
357 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Rotary Airlock 362RF04 - MT002-TDIC-ME12-362RF04-0001 | 2024-11-11 |  | Open
358 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Moterized Guilotine Damper 362SD01 - MT002-TDIC-ME12-362SD01-0001 | 2024-11-11 |  | Open
359 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Moterized Guilotine Damper 362SD02 - MT002-TDIC-ME12-362SD02-0001 | 2024-11-11 |  | Open
360 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 362SG03 - MT002-TDIC-ME12-362SG03-0001 | 2024-11-11 |  | Open
361 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 362SG04 - MT002-TDIC-ME12-362SG04-0001 | 2024-11-11 |  | Open
362 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 362SG06 - MT002-TDIC-ME12-362SG06-0001 | 2024-11-11 |  | Open
363 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Butterfly Damper 422BV01 - MT002-TDIC-ME12-422BV01-0001 | 2024-11-11 | 2024-08-18 | Closed
364 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Butterfly Damper 422BV02 - MT002-TDIC-ME12-422BV02-0001 | 2024-11-11 | 2024-08-18 | Closed
365 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Louver Damper 422LD01 - MT002-TDIC-ME12-422LD01-0001 | 2024-11-11 | 2024-08-18 | Closed
366 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Slide Gate 422SG15 - MT002-TDIC-ME12-422SG15-0001 | 2024-11-11 | 2024-08-18 | Closed
367 | Mechanical | Mechanical & Process | 362 - RAW MILL GRINDING | Rotary Airlock 422RF15 - MT002-TDIC-ME12-422RF15-0001 | 2024-11-11 | 2024-08-18 | Closed
368 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | GENERAL PLAN - MT002-TDIC-GA10-3920000-0001 | 2024-03-07 | 2024-01-08 | Closed
369 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | SECTION 1-1 - MT002-TDIC-GA10-3920000-0002 | 2024-03-07 | 2024-01-08 | Closed
370 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | SECTION 2-2,3-3，4-4 - MT002-TDIC-GA10-3920000-0003 | 2024-03-07 | 2024-01-08 | Closed
371 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PLAN 63.500,71.100 - MT002-TDIC-GA10-3920000-0004 | 2024-03-07 | 2024-01-08 | Closed
372 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PLAN 11.100,FOUNDATION INSIDE SILO - MT002-TDIC-GA10-3920000-0005 | 2024-03-07 | 2024-01-08 | Closed
373 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PLAN FOUNDATION ±0.000,11.100 - MT002-TDIC-GA11-3920000-0001 | 2024-03-07 |  | Open
374 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PLAN FOUNDATION 63.500,66.000-67.100,71.100,DETAIL D15 - MT002-TDIC-GA11-3920000-0002 | 2024-03-07 |  | Open
375 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PLAN OF SILO BOTTOM,DETAIL D16 - MT002-TDIC-GA11-3920000-0003 | 2024-03-07 |  | Open
376 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | DETAIL D1-D14 - MT002-TDIC-GA11-3920000-0004 | 2024-03-07 |  | Open
377 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | FLOW SHEET - MT002-TDIC-ME01-4120000-0001 | 2024-03-07 | 2024-01-08 | Closed
378 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4120000-0001 | 2024-03-07 | 2024-01-08 | Closed
379 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | 3D MODELING - MT002-TDIC-GA10-3920000-0000 | 2024-03-07 |  | Open
380 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-3920000-0001 | 2024-08-25 |  | Open
381 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Piping- Bill of quantities - MT002-TDIC-ME51-3920000-0001 | 2024-08-25 |  | Open
382 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Bucket Elevator EQUIPMENT DRAWING - MT002-TDIC-ME12-392BE01-0001 | 2024-03-07 | 2024-03-11 | Closed
383 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Bucket Elevator DATASHEET - MT002-TDIC-ME10-392BE01-0001 | 2024-03-07 | 2024-03-11 | Closed
384 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | HGBW-HCA 1100×71000 - MT002-TDIC-ME12-392BE02-0001 | 2024-04-25 | 2024-04-25 | Closed
385 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | DATA SHEET - MT002-TDIC-ME10-392BE02-0001 | 2024-04-25 | 2024-04-25 | Closed
386 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Bag Filter - MT002-TDIC-ME12-392BF03-0001 | 2024-10-11 |  | Open
387 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-392FN03-0001 | 2024-10-11 |  | Open
388 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Air Slide - MT002-TDIC-ME12-392AS03-0001 | 2024-10-11 | 2024-04-25 | Closed
389 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Air Slide - MT002-TDIC-ME12-392DB01-0001 | 2024-10-11 | 2024-04-25 | Closed
390 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Air Slide - MT002-TDIC-ME12-412AE01-0001 | 2024-10-11 | 2024-04-25 | Closed
391 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Air Slide - MT002-TDIC-ME12-412AS01-0001 | 2024-10-11 | 2024-04-25 | Closed
392 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Air Slide - MT002-TDIC-ME12-412AS10-0001 | 2024-10-11 | 2024-04-25 | Closed
393 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-392FA09-0001 | 2024-10-11 |  | Open
394 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-392FA10-0001 | 2024-10-11 |  | Open
395 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-392FA11-0001 | 2024-10-11 |  | Open
396 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-392FA12-0001 | 2024-10-11 |  | Open
397 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-412FA01-0001 | 2024-10-11 |  | Open
398 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-412FA02-0001 | 2024-10-11 |  | Open
399 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-412FA03-0001 | 2024-10-11 |  | Open
400 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Fan - MT002-TDIC-ME12-412FA04-0001 | 2024-10-11 |  | Open
401 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | ELECTRIC FLOW CONTROL VALVE B630 - MT002-TDIC-ME12-412PG01-0001 | 2024-11-11 | 2024-04-14 | Closed
402 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | MANUAL GATE VALVE B630 - MT002-TDIC-ME12-412SG01-0001 | 2024-11-11 | 2024-04-14 | Closed
403 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | HREE-WAY VALVE ASSEMBLY DIAGRAM B630 - MT002-TDIC-ME12-412SG01-0002 | 2024-04-14 | 2024-04-14 | Closed
404 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | PNEUMATIC GATE VALVE B630 - MT002-TDIC-ME12-412SV01-0001 | 2024-11-11 | 2024-04-14 | Closed
405 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | DATA SHEET - MT002-TDIC-ME10-412BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
406 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | DATA SHEET - MT002-TDIC-ME10-412BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
407 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Blower - MT002-TDIC-ME12-412BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
408 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Blower - MT002-TDIC-ME12-412BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
409 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Penumatic Butterfly Damper - MT002-TDIC-ME12-392BV01-0001 | 2024-11-11 | 2024-08-18 | Closed
410 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Penumatic Butterfly Damper - MT002-TDIC-ME12-392BV02-0001 | 2024-11-11 | 2024-08-18 | Closed
411 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Vent Valve - MT002-TDIC-ME12-392VE01-0001 | 2024-11-11 |  | Open
412 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Equipment drawing of 412BV01 - MT002-TDIC-ME12-412BV01-0001 | 2024-11-11 | 2024-05-05 | Closed
413 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | Equipment drawing of 412BV11 - MT002-TDIC-ME12-412BV11-0001 | 2024-05-05 | 2024-05-05 | Closed
414 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | DATA SHEET - MT002-TDIC-ME10-432BE01-0001 | 2024-03-11 | 2024-03-11 | Closed
415 | Mechanical | Mechanical & Process | 392 -RAW MEAL SILO | HGBW-HC 900×158500 - MT002-TDIC-ME12-432BE01-0001 | 2024-03-11 | 2024-03-11 | Closed
416 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN ±0.000 - MT002-TDIC-GA10-4420000-0001 | 2024-03-07 | 2024-01-08 | Closed
417 | Mechanical | Mechanical & Process | 442 - PREHEATING | SECTION 1-1,3-3,4-4 - MT002-TDIC-GA10-4420000-0002 | 2024-03-07 | 2024-01-08 | Closed
418 | Mechanical | Mechanical & Process | 442 - PREHEATING | SECTION 2-2,5-5 - MT002-TDIC-GA10-4420000-0003 | 2024-03-07 | 2024-01-08 | Closed
419 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 10.140,26.490 - MT002-TDIC-GA10-4420000-0004 | 2024-03-07 | 2024-01-08 | Closed
420 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 46.340,68.740 - MT002-TDIC-GA10-4420000-0005 | 2024-03-07 | 2024-01-08 | Closed
421 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 90.340,109.190 - MT002-TDIC-GA10-4420000-0006 | 2024-03-07 | 2024-01-08 | Closed
422 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 128.040,142.740 - MT002-TDIC-GA10-4420000-0007 | 2024-03-07 | 2024-01-08 | Closed
423 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 14.800,17.800,18.300,21.440,23.490,61.140,61.800,62.340,66.340 - MT002-TDIC-GA10-4420000-0008 | 2024-03-07 | 2024-03-24 | Closed
424 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 37.800,51.900,52.590,56.800,59.300,145.800,147.700 - MT002-TDIC-GA10-4420000-0009 | 2024-03-07 | 2024-03-24 | Closed
425 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN 81.440,82.220,100.340,102.320,119.600,121.170 - MT002-TDIC-GA10-4420000-0010 | 2024-03-07 | 2024-03-24 | Closed
426 | Mechanical | Mechanical & Process | 442 - PREHEATING | SECTION 6-6；PLAN 138.000,23.440 - MT002-TDIC-GA10-4420000-0011 | 2024-03-07 | 2024-03-24 | Closed
427 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION ±0.000 - MT002-TDIC-GA11-4420000-0001 | 2024-03-07 |  | Open
428 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION 10.140,26.490 - MT002-TDIC-GA11-4420000-0002 | 2024-03-07 |  | Open
429 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION 46.340,68.740 - MT002-TDIC-GA11-4420000-0003 | 2024-03-07 |  | Open
430 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION 90.340,109.190 - MT002-TDIC-GA11-4420000-0004 | 2024-03-07 |  | Open
431 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION 128.040,142.740 - MT002-TDIC-GA11-4420000-0005 | 2024-03-07 |  | Open
432 | Mechanical | Mechanical & Process | 442 - PREHEATING | PLAN FOUNDATION 5.400-3.700,5.000,16.300, 31.740,145.800,147.700,154.500,159.300,151.740-150.500-148.300 - MT002-TDIC-GA11-4420000-0006 | 2024-03-07 | 2024-03-24 | Closed
433 | Mechanical | Mechanical & Process | 442 - PREHEATING | DETAIL D4,D5,D7,D9 - MT002-TDIC-GA11-4420000-0007 | 2024-03-07 | 2024-03-24 | Closed
434 | Mechanical | Mechanical & Process | 442 - PREHEATING | DETAIL D1-D3,D6,D8 - MT002-TDIC-GA11-4420000-0008 | 2024-03-07 | 2024-03-24 | Closed
435 | Mechanical | Mechanical & Process | 442 - PREHEATING | FLOW SHEET - MT002-TDIC-ME01-4320000-0001 | 2024-03-07 | 2024-01-08 | Closed
436 | Mechanical | Mechanical & Process | 442 - PREHEATING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4320000-0001 | 2024-03-07 | 2024-01-08 | Closed
437 | Mechanical | Mechanical & Process | 442 - PREHEATING | FLOW SHEET - MT002-TDIC-ME01-4420000-0001 | 2024-03-07 | 2024-01-08 | Closed
438 | Mechanical | Mechanical & Process | 442 - PREHEATING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4420000-0001 | 2024-03-07 | 2024-01-08 | Closed
439 | Mechanical | Mechanical & Process | 442 - PREHEATING | 3D MODELING - MT002-TDIC-GA10-4420000-0000 | 2024-03-07 | 2024-09-27 | Closed
440 | Mechanical | Mechanical & Process | 442 - PREHEATING | PROCESS PIPING DRAWING - MT002-TDIC-ME50-4420000-0001 | 2024-08-25 |  | Open
441 | Mechanical | Mechanical & Process | 442 - PREHEATING | LIST OF PROCESS PIPING MATERIAL - MT002-TDIC-ME51-4420000-0001 | 2024-08-25 |  | Open
442 | Mechanical | Mechanical & Process | 442 - PREHEATING | TGD1250×30150mm - MT002-TDIC-ME12-412BE01-0001 | 2024-03-07 | 2024-03-12 | Closed
443 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-412BE01-0001 | 2024-03-07 | 2024-04-09 | Closed
444 | Mechanical | Mechanical & Process | 442 - PREHEATING | Bucket Elevator 432BE01 - MT002-TDIC-ME12-432BE01-0001 | 2024-03-07 | 2024-03-11 | Closed
445 | Mechanical | Mechanical & Process | 442 - PREHEATING | HEAT BALANCE - MT002-TDIC-ME03-442PH01-0001 | 2024-05-28 | 2024-05-28 | Closed
446 | Mechanical | Mechanical & Process | 442 - PREHEATING | PREHEATER 442PH01 DATASHEET - MT002-TDIC-ME10-442PH01-0001 | 2024-03-15 | 2024-03-13 | Closed
447 | Mechanical | Mechanical & Process | 442 - PREHEATING | 11000TPD PREHEATER SYSTEM - MT002-TDIC-ME12-442PH01-0001 | 2024-03-15 | 2024-03-13 | Closed
448 | Mechanical | Mechanical & Process | 442 - PREHEATING | 11000TPD PREHEATER SYSTEM - MT002-TDIC-ME12-442PH01-0002 | 2024-03-15 | 2024-03-13 | Closed
449 | Mechanical | Mechanical & Process | 442 - PREHEATING | 11000TPD PREHEATER SYSTEM - MT002-TDIC-ME12-442PH01-0003 | 2024-03-15 | 2024-03-13 | Closed
450 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-452PR01-0001 | 2024-03-15 | 2024-03-13 | Closed
451 | Mechanical | Mechanical & Process | 442 - PREHEATING | EQUIPMENT DRAWING - MT002-TDIC-ME12-442FN01-0001 | 2024-05-15 | 2024-05-24 | Closed
452 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATASHEET of PROCESS FAN 442FN01 - MT002-TDIC-ME10-442FN01-0001 | 2024-05-15 |  | Open
453 | Mechanical | Mechanical & Process | 442 - PREHEATING | MULTICOR S1250 WITH B500 - MT002-TDIC-ME12-432PF01-0001 | 2024-05-15 | 2024-04-14 | Closed
454 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATASHEET of Coriolis powder Feeding system 432PF01 - MT002-TDIC-ME10-432PF01-0001 | 2024-05-15 | 2024-04-15 | Closed
455 | Mechanical | Mechanical & Process | 442 - PREHEATING | Impact Flow Meter 432FM01 - MT002-TDIC-ME12-432FM01-0001 | 2024-05-15 | 2024-08-18 | Closed
456 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATASHEET of Impact Flow Meter 432FM01 - MT002-TDIC-ME10-432FM01-0001 | 2024-05-15 |  | Open
457 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
458 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
459 | Mechanical | Mechanical & Process | 442 - PREHEATING | Roots Blower 432BL01 - MT002-TDIC-ME12-432BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
460 | Mechanical | Mechanical & Process | 442 - PREHEATING | Roots Blower 432BL02 - MT002-TDIC-ME12-432BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
461 | Mechanical | Mechanical & Process | 442 - PREHEATING | Load Cell 412LC01~412LC03 - MT002-TDIC-ME12-412LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
462 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV03 - MT002-TDIC-ME12-432BV03-0001 | 2024-10-11 | 2024-08-27 | Closed
463 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV04 - MT002-TDIC-ME12-432BV04-0001 | 2024-10-11 |  | Open
464 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV05 - MT002-TDIC-ME12-432BV05-0001 | 2024-10-11 |  | Open
465 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV06 - MT002-TDIC-ME12-432BV06-0001 | 2024-10-11 | 2024-08-27 | Closed
466 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV07 - MT002-TDIC-ME12-432BV07-0001 | 2024-10-11 |  | Open
467 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic butterfly Damper 432BV08 - MT002-TDIC-ME12-432BV08-0001 | 2024-10-11 |  | Open
468 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic Shut-off Gate 432SG05 - MT002-TDIC-ME12-432SG05-0001 | 2024-10-11 |  | Open
469 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic Shut-off Gate 432SG06 - MT002-TDIC-ME12-432SG06-0001 | 2024-10-11 | 2024-08-18 | Closed
470 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic Ball Valve 432BV01 - MT002-TDIC-ME12-432BV01-0001 | 2024-10-11 | 2024-05-05 | Closed
471 | Mechanical | Mechanical & Process | 442 - PREHEATING | Pneumatic Ball Valve 432BV02 - MT002-TDIC-ME12-432BV02-0001 | 2024-10-11 |  | Open
472 | Mechanical | Mechanical & Process | 442 - PREHEATING | Hot meal Sampler 442SM01 - MT002-TDIC-ME12-442SM01-0001 | 2024-08-11 | 2024-05-15 | Closed
473 | Mechanical | Mechanical & Process | 442 - PREHEATING | Hot meal Sampler 442SM02 - MT002-TDIC-ME12-442SM02-0001 | 2024-08-11 |  | Open
474 | Mechanical | Mechanical & Process | 442 - PREHEATING | PNEUMATIC GATE VALVE B630 - MT002-TDIC-ME12-432SV01-0001 | 2024-10-11 | 2024-04-14 | Closed
475 | Mechanical | Mechanical & Process | 442 - PREHEATING | MANUAL GATE VALVE B630 - MT002-TDIC-ME12-432SG01-0001 | 2024-10-11 | 2024-04-14 | Closed
476 | Mechanical | Mechanical & Process | 442 - PREHEATING | THREE-WAY VALVE ASSEMBLY DIAGRAM B630 - MT002-TDIC-ME12-432SG01-0002 | 2024-10-11 | 2024-04-14 | Closed
477 | Mechanical | Mechanical & Process | 442 - PREHEATING | PNEUMATIC FLOW CONTROL VALVE B630 - MT002-TDIC-ME12-432PG01-0001 | 2024-10-11 | 2024-04-14 | Closed
478 | Mechanical | Mechanical & Process | 442 - PREHEATING | PNEUMATIC GATE VALVE 650*650 - MT002-TDIC-ME12-432SG0A-0001 | 2024-10-11 | 2024-04-14 | Closed
479 | Mechanical | Mechanical & Process | 442 - PREHEATING | HIGH TEMPERATURE ROTARY AIR LOCK VALVE 800*1000 - MT002-TDIC-ME12-432RF0A-0001 | 2024-10-11 | 2024-04-14 | Closed
480 | Mechanical | Mechanical & Process | 442 - PREHEATING | ELECTRIC DISTRIBUTOR VALVE, EDV Φ1200-B800/B630, SCHEME DIAGRAM - MT002-TDIC-ME12-432MW01-0001 | 2024-10-11 | 2024-04-14 | Closed
481 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-412PG01-0001 | 2024-10-11 | 2024-04-14 | Closed
482 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-412SG01-0001 | 2024-10-11 | 2024-04-14 | Closed
483 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-412SV01-0001 | 2024-10-11 | 2024-04-14 | Closed
484 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432MW01-0001 | 2024-10-11 | 2024-04-14 | Closed
485 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432PG01-0001 | 2024-10-11 | 2024-04-14 | Closed
486 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432RF0A-0001 | 2024-10-11 | 2024-04-14 | Closed
487 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432SG0A-0001 | 2024-10-11 | 2024-04-14 | Closed
488 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432SG01-0001 | 2024-10-11 | 2024-04-14 | Closed
489 | Mechanical | Mechanical & Process | 442 - PREHEATING | DATA SHEET - MT002-TDIC-ME10-432SV01-0001 | 2024-10-11 | 2024-04-14 | Closed
490 | Mechanical | Mechanical & Process | 442 - PREHEATING | METAL EXPANSION JOINT - MT002-TDIC-ME12-442EJ01-0001 | 2024-11-11 | 2024-06-08 | Closed
491 | Mechanical | Mechanical & Process | 442 - PREHEATING | METAL EXPANSION JOINT - MT002-TDIC-ME12-442EJ09-0001 | 2024-11-11 | 2024-06-08 | Closed
492 | Mechanical | Mechanical & Process | 442 - PREHEATING | METAL EXPANSION JOINT - MT002-TDIC-ME12-442EJ11-0001 | 2024-11-11 | 2024-06-08 | Closed
493 | Mechanical | Mechanical & Process | 442 - PREHEATING | METAL EXPANSION JOINT - MT002-TDIC-ME12-442EJ12-0001 | 2024-11-11 | 2024-06-08 | Closed
494 | Mechanical | Mechanical & Process | 442 - PREHEATING | FLOW SHEET - MT002-TDIC-ME10-442AB01-0001 | 2024-11-11 | 2024-06-07 | Closed
495 | Mechanical | Mechanical & Process | 442 - PREHEATING | OUTLINE DIMENSION DRAWING - MT002-TDIC-ME12-442AB01-0001 | 2024-11-11 | 2024-06-07 | Closed
496 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR BLASTER SYSTEM DIAGRAM - MT002-TDIC-ME12-442AB01-0002 | 2024-11-11 | 2024-06-07 | Closed
497 | Mechanical | Mechanical & Process | 442 - PREHEATING | INSTALLATION LAYOUT DIAGRAM - MT002-TDIC-ME12-442AB01-0003 | 2024-11-11 | 2024-06-07 | Closed
498 | Mechanical | Mechanical & Process | 442 - PREHEATING | DN100 FLAT NOZZLE ASSEMBLY - MT002-TDIC-ME12-442AB01-0004 | 2024-11-11 | 2024-06-07 | Closed
499 | Mechanical | Mechanical & Process | 442 - PREHEATING | Bag Filter 412BF01 - MT002-TDIC-ME12-412BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
500 | Mechanical | Mechanical & Process | 442 - PREHEATING | Bag Filter 432BF01 - MT002-TDIC-ME12-432BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
501 | Mechanical | Mechanical & Process | 442 - PREHEATING | FAN 412FN01 - MT002-TDIC-ME12-412FN01-0001 | 2024-10-11 | 2024-09-30 | Closed
502 | Mechanical | Mechanical & Process | 442 - PREHEATING | FAN 432FN01 - MT002-TDIC-ME12-432FN01-0001 | 2024-10-11 |  | Open
503 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE FAN 432FA05 - MT002-TDIC-ME12-432FA05-0001 | 2024-10-11 |  | Open
504 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE FAN 412FA05~06 - MT002-TDIC-ME12-412FA05-0001 | 2024-10-11 |  | Open
505 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE FAN 432FA01~02 - MT002-TDIC-ME12-432FA01-0001 | 2024-10-11 |  | Open
506 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE FAN 432FA03~04 - MT002-TDIC-ME12-432FA03-0001 | 2024-10-11 |  | Open
507 | Mechanical | Mechanical & Process | 442 - PREHEATING | Open Air Slides 412AE02 - MT002-TDIC-ME12-412AE02-0001 | 2024-11-11 | 2024-04-25 | Closed
508 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE 432AS01~04 - MT002-TDIC-ME12-432AS01-0001 | 2024-11-11 | 2024-04-25 | Closed
509 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE 432AS06 - MT002-TDIC-ME12-432AS06-0001 | 2024-11-11 | 2024-04-25 | Closed
510 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE 412AS11 - MT002-TDIC-ME12-412AS11-0001 | 2024-11-11 | 2024-04-25 | Closed
511 | Mechanical | Mechanical & Process | 442 - PREHEATING | AIR SLIDE 432AS05 - MT002-TDIC-ME12-432AS05-0001 | 2024-11-11 | 2024-04-25 | Closed
512 | Mechanical | Mechanical & Process | 442 - PREHEATING | EQUIPMENT DRAWINGS - MT002-TDIC-ME21-442PH01-0001 | 2024-11-11 | 2024-05-20 | Closed
513 | Mechanical | Mechanical & Process | 462 - KILN | PLAN LAYOUT - MT002-TDIC-GA10-4620000-0001 | 2024-03-07 | 2024-01-08 | Closed
514 | Mechanical | Mechanical & Process | 462 - KILN | SECTION 1-1 - MT002-TDIC-GA10-4620000-0002 | 2024-03-07 | 2024-01-08 | Closed
515 | Mechanical | Mechanical & Process | 462 - KILN | SECTION 2-2,3-3,4-4 - MT002-TDIC-GA10-4620000-0003 | 2024-03-07 | 2024-01-08 | Closed
516 | Mechanical | Mechanical & Process | 462 - KILN | SECTION 5-5,6-6,7-7 - MT002-TDIC-GA10-4620000-0004 | 2024-03-07 | 2024-01-08 | Closed
517 | Mechanical | Mechanical & Process | 462 - KILN | PLAN FOUNDATION OF KILN；PLAN FOUNDATION OF 6.900, 8.000, 9.200, 11.000 - MT002-TDIC-GA11-4620000-0001 | 2024-03-07 | 2024-03-22 | Closed
518 | Mechanical | Mechanical & Process | 462 - KILN | DETAIL D1-D2 - MT002-TDIC-GA11-4620000-0002 | 2024-03-07 | 2024-03-22 | Closed
519 | Mechanical | Mechanical & Process | 462 - KILN | DETAIL D3-D4 - MT002-TDIC-GA11-4620000-0003 | 2024-03-07 | 2024-03-22 | Closed
520 | Mechanical | Mechanical & Process | 462 - KILN | FLOW SHEET - MT002-TDIC-ME01-4620000-0001 | 2024-03-07 | 2024-01-08 | Closed
521 | Mechanical | Mechanical & Process | 462 - KILN | Process Equipment List - MT002-TDIC-ME04-4620000-0001 | 2024-03-07 | 2024-01-08 | Closed
522 | Mechanical | Mechanical & Process | 462 - KILN | 3D model - MT002-TDIC-GA10-4620000-0000 | 2024-03-07 |  | Open
523 | Mechanical | Mechanical & Process | 462 - KILN | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-4620000-0001 | 2024-07-26 |  | Open
524 | Mechanical | Mechanical & Process | 462 - KILN | Piping- Bill of quantities - MT002-TDIC-ME51-4620000-0001 | 2024-07-26 |  | Open
525 | Mechanical | Mechanical & Process | 462 - KILN | Outside and foundation Drawing of Kiln Hood - MT002-TDIC-ME12-462KH01-0001 | 2024-03-15 | 2024-03-06 | Closed
526 | Mechanical | Mechanical & Process | 462 - KILN | Φ5.8*86 Outside Drawing of Rotarykiln - MT002-TDIC-ME12-462KL01-0001 | 2024-03-15 | 2024-02-23 | Closed
527 | Mechanical | Mechanical & Process | 462 - KILN | Φ5.8*86 Outside Drawing of Rotarykiln - MT002-TDIC-ME12-462KL01-0002 | 2024-03-15 | 2024-02-23 | Closed
528 | Mechanical | Mechanical & Process | 462 - KILN | Φ5.8*86 Foundation Drawing of Rotarykiln - MT002-TDIC-ME12-462KL01-0003 | 2024-03-15 | 2024-02-23 | Closed
529 | Mechanical | Mechanical & Process | 462 - KILN | Φ5.8*86 Load Diagram of Rotarykiln - MT002-TDIC-ME12-462KL01-0004 | 2024-03-15 | 2024-02-23 | Closed
530 | Mechanical | Mechanical & Process | 462 - KILN | Electric Wiring and Control Diagram of Φ5.8*86 Rotarykiln - MT002-TDIC-ME12-462KL01-0005 | 2024-03-15 | 2024-02-23 | Closed
531 | Mechanical | Mechanical & Process | 462 - KILN | DATASHEET of 462KL01 - MT002-TDIC-ME10-462KL01-0001 | 2024-03-15 | 2024-02-23 | Closed
532 | Mechanical | Mechanical & Process | 462 - KILN | Foundation Drawing of TA Duct(1) - MT002-TDIC-ME12-452DU01-0001 | 2024-03-15 | 2024-03-13 | Closed
533 | Mechanical | Mechanical & Process | 462 - KILN | Foundation Drawing of TA Duct(2) - MT002-TDIC-ME12-452DU01-0002 | 2024-03-15 | 2024-03-13 | Closed
534 | Mechanical | Mechanical & Process | 462 - KILN | TERTIARY AIR DUCT EQUIPMENT DRAWING - MT002-TDIC-ME21-452DU01-0001 | 2024-05-28 | 2024-05-22 | Closed
535 | Mechanical | Mechanical & Process | 462 - KILN | FAN 462FA01 - MT002-TDIC-ME12-462FA01-0001 | 2024-10-11 |  | Open
536 | Mechanical | Mechanical & Process | 462 - KILN | FAN 462FA02 - MT002-TDIC-ME12-462FA02-0001 | 2024-10-11 |  | Open
537 | Mechanical | Mechanical & Process | 462 - KILN | FAN 462FA03 - MT002-TDIC-ME12-462FA03-0001 | 2024-10-11 |  | Open
538 | Mechanical | Mechanical & Process | 462 - KILN | FAN 462FA04 - MT002-TDIC-ME12-462FA04-0001 | 2024-10-11 |  | Open
539 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN LAYOUT - MT002-TDIC-GA10-4720000-0001 | 2024-03-07 | 2024-01-08 | Closed
540 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | SECTION 1-1 - MT002-TDIC-GA10-4720000-0002 | 2024-03-07 | 2024-01-08 | Closed
541 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | SECTION 2-2,3-3,4-4,5-5,6-6 - MT002-TDIC-GA10-4720000-0003 | 2024-03-07 | 2024-01-08 | Closed
542 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | SECTION 7-7,8-8 - MT002-TDIC-GA10-4720000-0004 | 2024-03-07 | 2024-01-08 | Closed
543 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN ±0.000,2.800 - MT002-TDIC-GA10-4720000-0005 | 2024-03-07 | 2024-01-08 | Closed
544 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | SECTION9-9,10-10,11-11,12-12,13-13 - MT002-TDIC-GA10-4720000-0006 | 2024-03-07 | 2024-01-08 | Closed
545 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | SECTION 14-14 - MT002-TDIC-GA10-4720000-0007 | 2024-03-07 | 2024-03-25 | Closed
546 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN FOUNDATION -6.500 - 28.800,-2.000,±0.000,2.000,2.800 - MT002-TDIC-GA11-4720000-0001 | 2024-03-07 | 2024-03-25 | Closed
547 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN FOUNDATION 7.500,7.600,7.800,11.000 - MT002-TDIC-GA11-4720000-0002 | 2024-03-07 | 2024-03-25 | Closed
548 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN FOUNDATION -4.100，,5.100 - MT002-TDIC-GA11-4720000-0003 | 2024-03-07 | 2024-03-25 | Closed
549 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PLAN FOUNDATION OF DUCT - MT002-TDIC-GA11-4720000-0004 | 2024-03-07 | 2024-03-25 | Closed
550 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | FLOW SHEET (1/2) - MT002-TDIC-ME01-4720000-0001 | 2024-03-07 | 2024-01-08 | Closed
551 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | FLOW SHEET (2/2) - MT002-TDIC-ME01-4720000-0002 | 2024-03-07 | 2024-01-08 | Closed
552 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4720000-0001 | 2024-03-07 | 2024-01-08 | Closed
553 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | 3D model - MT002-TDIC-GA10-4720000-0000 | 2024-03-07 | 2024-03-25 | Closed
554 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-4720000-0001 | 2024-03-11 |  | Open
555 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Piping- Bill of quantities - MT002-TDIC-ME51-4720000-0001 | 2024-03-11 |  | Open
556 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | EQUIPMENT DRAWING - MT002-TDIC-ME12-472FN01-0001 | 2024-03-15 | 2024-05-24 | Closed
557 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Fan 472FN01 - MT002-TDIC-ME10-472FN01-0001 | 2024-03-15 |  | Open
558 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | 2×31/15/4×9/0.45 EP - MT002-TDIC-ME12-472EP01-0001 | 2024-03-15 | 2024-05-05 | Closed
559 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | TECHNICAL REQUIREMENTS - MT002-TDIC-ME12-472EP01-0002 | 2024-03-15 | 2024-05-05 | Closed
560 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | LOADS - MT002-TDIC-ME12-472EP01-0003 | 2024-03-15 | 2024-05-05 | Closed
561 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DRAG CHAIN FOUNDATION DRAWING - MT002-TDIC-ME12-472EP01-0004 | 2024-03-15 | 2024-05-05 | Closed
562 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Electrostatic Precipitator 472EP01 - MT002-TDIC-ME10-472EP01-0001 | 2024-03-15 | 2024-07-05 | Closed
563 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA01 - MT002-TDIC-ME12-472FA01-0001 | 2024-03-15 | 2024-07-26 | Closed
564 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA02 - MT002-TDIC-ME12-472FA02-0001 | 2024-03-15 | 2024-07-26 | Closed
565 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA03 - MT002-TDIC-ME12-472FA03-0001 | 2024-03-15 | 2024-07-26 | Closed
566 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA04 - MT002-TDIC-ME12-472FA04-0001 | 2024-03-15 | 2024-07-26 | Closed
567 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA05 - MT002-TDIC-ME12-472FA05-0001 | 2024-03-15 | 2024-07-26 | Closed
568 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA06 - MT002-TDIC-ME12-472FA06-0001 | 2024-03-15 | 2024-07-26 | Closed
569 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA07 - MT002-TDIC-ME12-472FA07-0001 | 2024-03-15 | 2024-07-26 | Closed
570 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA08 - MT002-TDIC-ME12-472FA08-0001 | 2024-03-15 | 2024-07-26 | Closed
571 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA09 - MT002-TDIC-ME12-472FA09-0001 | 2024-03-15 | 2024-07-26 | Closed
572 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA10 - MT002-TDIC-ME12-472FA10-0001 | 2024-03-15 | 2024-07-26 | Closed
573 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA11 - MT002-TDIC-ME12-472FA11-0001 | 2024-03-15 | 2024-07-26 | Closed
574 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA12 - MT002-TDIC-ME12-472FA12-0001 | 2024-03-15 | 2024-07-26 | Closed
575 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA13 - MT002-TDIC-ME12-472FA13-0001 | 2024-03-15 | 2024-07-26 | Closed
576 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA14 - MT002-TDIC-ME12-472FA14-0001 | 2024-03-15 | 2024-07-26 | Closed
577 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA15 - MT002-TDIC-ME12-472FA15-0001 | 2024-03-15 | 2024-07-26 | Closed
578 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Cooler Fan 472FA16 - MT002-TDIC-ME12-472FA16-0001 | 2024-03-15 | 2024-07-26 | Closed
579 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Fan 472FA17 - MT002-TDIC-ME12-472FA17-0001 | 2024-03-15 |  | Open
580 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Fan 472FA18 - MT002-TDIC-ME12-472FA18-0001 | 2024-03-15 |  | Open
581 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA01 - MT002-TDIC-ME10-472FA01-0001 | 2024-03-15 |  | Open
582 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA02 - MT002-TDIC-ME10-472FA02-0001 | 2024-03-15 |  | Open
583 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA03 - MT002-TDIC-ME10-472FA03-0001 | 2024-03-15 |  | Open
584 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA04 - MT002-TDIC-ME10-472FA04-0001 | 2024-03-15 |  | Open
585 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA05 - MT002-TDIC-ME10-472FA05-0001 | 2024-03-15 |  | Open
586 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA06 - MT002-TDIC-ME10-472FA06-0001 | 2024-03-15 |  | Open
587 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA07 - MT002-TDIC-ME10-472FA07-0001 | 2024-03-15 |  | Open
588 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA08 - MT002-TDIC-ME10-472FA08-0001 | 2024-03-15 |  | Open
589 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA09 - MT002-TDIC-ME10-472FA09-0001 | 2024-03-15 |  | Open
590 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA10 - MT002-TDIC-ME10-472FA10-0001 | 2024-03-15 |  | Open
591 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA11 - MT002-TDIC-ME10-472FA11-0001 | 2024-03-15 |  | Open
592 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA12 - MT002-TDIC-ME10-472FA12-0001 | 2024-03-15 |  | Open
593 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA13 - MT002-TDIC-ME10-472FA13-0001 | 2024-03-15 |  | Open
594 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA14 - MT002-TDIC-ME10-472FA14-0001 | 2024-03-15 |  | Open
595 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA15 - MT002-TDIC-ME10-472FA15-0001 | 2024-03-15 |  | Open
596 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Cooler Fan 472FA16 - MT002-TDIC-ME10-472FA16-0001 | 2024-03-15 |  | Open
597 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | CLINKER COOLER DRAWINGS - MT002-TDIC-ME12-472GQ01-0001 | 2024-03-07 | 2024-03-01 | Closed
598 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0002 | 2024-03-07 |  | Open
599 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0003 | 2024-03-07 |  | Open
600 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0004 | 2024-03-07 |  | Open
601 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0005 | 2024-03-07 |  | Open
602 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0006 | 2024-03-07 |  | Open
603 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0007 | 2024-03-07 |  | Open
604 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME12-472GQ01-0008 | 2024-03-07 |  | Open
605 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATASHEET of Grate Clinker Cooler 472GQ01 - MT002-TDIC-ME10-472GQ01-0001 | 2024-03-07 | 2024-03-01 | Closed
606 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Single Girder Electirc Crane 472CA01 - MT002-TDIC-ME12-472CA01-0001 | 2024-11-07 |  | Open
607 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | MT500×20000mm CHAIN CONVEYOR - MT002-TDIC-ME12-492CV05-0001 | 2024-08-07 | 2024-04-17 | Closed
608 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | MT400×13000mm CHAIN CONVEYOR - MT002-TDIC-ME12-492CV06-0001 | 2024-08-07 | 2024-04-17 | Closed
609 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATA SHEET - MT002-TDIC-ME10-492CV05-0001 | 2024-08-07 | 2024-04-17 | Closed
610 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Bag Filter 492BF01 - MT002-TDIC-ME12-492BF01-0001 | 2024-10-11 | 2024-08-30 | Closed
611 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Fan 492FA01 - MT002-TDIC-ME12-492FA01-0001 | 2024-10-11 |  | Open
612 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Auto Sampler 472SM01 - MT002-TDIC-ME12-472SM01-0001 | 2024-08-11 | 2024-05-15 | Closed
613 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | WATER SPRAYING SYSTEM FOR CLINKER COOLER - MT002-TDIC-ME12-472IJ01-0001 | 2024-08-11 | 2024-06-08 | Closed
614 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD01 - MT002-TDIC-ME12-472LD01-0001 | 2024-10-11 | 2024-08-18 | Closed
615 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD02 - MT002-TDIC-ME12-472LD02-0001 | 2024-10-11 | 2024-08-18 | Closed
616 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD03 - MT002-TDIC-ME12-472LD03-0001 | 2024-10-11 | 2024-08-18 | Closed
617 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD04 - MT002-TDIC-ME12-472LD04-0001 | 2024-10-11 | 2024-08-18 | Closed
618 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD05 - MT002-TDIC-ME12-472LD05-0001 | 2024-10-11 |  | Open
619 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD06 - MT002-TDIC-ME12-472LD06-0001 | 2024-10-11 |  | Open
620 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD07 - MT002-TDIC-ME12-472LD07-0001 | 2024-10-11 |  | Open
621 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD08 - MT002-TDIC-ME12-472LD08-0001 | 2024-10-11 |  | Open
622 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD09 - MT002-TDIC-ME12-472LD09-0001 | 2024-10-11 |  | Open
623 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD10 - MT002-TDIC-ME12-472LD10-0001 | 2024-10-11 |  | Open
624 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD12 - MT002-TDIC-ME12-472LD12-0001 | 2024-10-11 | 2024-08-18 | Closed
625 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD13 - MT002-TDIC-ME12-472LD13-0001 | 2024-10-11 |  | Open
626 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD14 - MT002-TDIC-ME12-472LD14-0001 | 2024-10-11 |  | Open
627 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD15 - MT002-TDIC-ME12-472LD15-0001 | 2024-10-11 |  | Open
628 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD16 - MT002-TDIC-ME12-472LD16-0001 | 2024-10-11 |  | Open
629 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD17 - MT002-TDIC-ME12-472LD17-0001 | 2024-10-11 |  | Open
630 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD18 - MT002-TDIC-ME12-472LD18-0001 | 2024-10-11 |  | Open
631 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD19 - MT002-TDIC-ME12-472LD19-0001 | 2024-10-11 |  | Open
632 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD20 - MT002-TDIC-ME12-472LD20-0001 | 2024-10-11 |  | Open
633 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD21 - MT002-TDIC-ME12-472LD21-0001 | 2024-10-11 | 2024-08-18 | Closed
634 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD22 - MT002-TDIC-ME12-472LD22-0001 | 2024-10-11 |  | Open
635 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD23 - MT002-TDIC-ME12-472LD23-0001 | 2024-10-11 |  | Open
636 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Louver Damper 472LD24 - MT002-TDIC-ME12-472LD24-0001 | 2024-10-11 |  | Open
637 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Moterized Butterfly Damper 472BV09 - MT002-TDIC-ME12-472BV09-0001 | 2024-10-11 | 2024-08-18 | Closed
638 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Hoist 472EH01 - MT002-TDIC-ME12-472EH01-0001 | 2024-10-11 |  | Open
639 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Hoist 472EH02 - MT002-TDIC-ME12-472EH02-0001 | 2024-10-11 |  | Open
640 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Electric Hoist 472EH04 - MT002-TDIC-ME12-472EH04-0001 | 2024-10-11 |  | Open
641 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Clinker conveyor 492CA01 - MT002-TDIC-ME12-492CA01-0001 | 2024-10-11 |  | Open
642 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATA SHEET - MT002-TDIC-ME10-482BL03-0001 | 2024-05-11 | 2024-05-27 | Closed
643 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | DATA SHEET - MT002-TDIC-ME10-482BL04-0001 | 2024-05-11 | 2024-05-27 | Closed
644 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Roots Blower 482BL03 - MT002-TDIC-ME12-482BL03-0001 | 2024-05-11 | 2024-05-27 | Closed
645 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Roots Blower 482BL04 - MT002-TDIC-ME12-482BL04-0001 | 2024-05-11 | 2024-05-27 | Closed
646 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | KILN MAIN BURNER DATA SHEET - MT002-TDIC-ME10-482BU01-0001 | 2024-03-15 | 2024-02-29 | Closed
647 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | KILN MAIN BURNER EQUIPMENT DRAWINGS - MT002-TDIC-ME12-482BU01-0001 | 2024-03-15 | 2024-02-29 | Closed
648 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Burner 482BU01 - MT002-TDIC-ME12-482BU01-0002 | 2024-03-15 |  | Open
649 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Burner 482BU01 - MT002-TDIC-ME12-482BU01-0003 | 2024-03-15 |  | Open
650 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Pneumatic Knife gate valve 482SD02 - MT002-TDIC-ME12-482SD02-0001 | 2024-10-11 | 2024-08-18 | Closed
651 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Pneumatic Knife gate valve 482SD03 - MT002-TDIC-ME12-482SD03-0001 | 2024-10-11 | 2024-08-18 | Closed
652 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Moterized Butterfly Damper 492BV01 - MT002-TDIC-ME12-492BV01-0001 | 2024-10-11 | 2024-08-18 | Closed
653 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Motorized arc gate 492CM01 - MT002-TDIC-ME12-492CM01-0001 | 2024-10-11 | 2024-08-18 | Closed
654 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | Needle Gate 492NG01 - MT002-TDIC-ME12-492NG01-0001 | 2024-10-11 | 2024-08-18 | Closed
655 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | FLOW SHEET - MT002-TDIC-ME10-472AB01-0001 | 2024-10-11 | 2024-06-07 | Closed
656 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | OUTLINE DIMENSION DRAWING - MT002-TDIC-ME12-472AB01-0001 | 2024-10-11 | 2024-06-07 | Closed
657 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | AIR BLASTER SYSTEM DIAGRAM - MT002-TDIC-ME12-472AB01-0002 | 2024-10-11 | 2024-06-07 | Closed
658 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | INSTALLATION LAYOUT DIAGRAM - MT002-TDIC-ME12-472AB01-0003 | 2024-10-11 | 2024-06-07 | Closed
659 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | FAN-SHAPED NOZZLE ASSEMBLY - MT002-TDIC-ME12-472AB01-0004 | 2024-10-11 | 2024-06-07 | Closed
660 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ01-0001 | 2024-10-11 | 2024-06-08 | Closed
661 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ02-0001 | 2024-10-11 | 2024-06-08 | Closed
662 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ03-0001 | 2024-10-11 | 2024-06-08 | Closed
663 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ04-0001 | 2024-10-11 | 2024-06-08 | Closed
664 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ05-0001 | 2024-10-11 | 2024-06-08 | Closed
665 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ11-0001 | 2024-10-11 | 2024-06-08 | Closed
666 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ12-0001 | 2024-10-11 | 2024-06-08 | Closed
667 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ13-0001 | 2024-10-11 | 2024-06-08 | Closed
668 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ14-0001 | 2024-10-11 | 2024-06-08 | Closed
669 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ15-0001 | 2024-10-11 | 2024-06-08 | Closed
670 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ16-0001 | 2024-10-11 | 2024-06-08 | Closed
671 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ17-0001 | 2024-10-11 | 2024-06-08 | Closed
672 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ18-0001 | 2024-10-11 | 2024-06-08 | Closed
673 | Mechanical | Mechanical & Process | 472 - CLINKER COOLING | METAL EXPANSION JOINT - MT002-TDIC-ME12-473EJ19-0001 | 2024-10-11 | 2024-06-08 | Closed
674 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN LAYOUT - MT002-TDIC-GA10-4920000-0001 | 2024-03-17 | 2024-02-09 | Closed
675 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | SECTION 1-1,2-2 - MT002-TDIC-GA10-4920000-0002 | 2024-03-17 | 2024-02-09 | Closed
676 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | SECTION 3-3 - MT002-TDIC-GA10-4920000-0003 | 2024-03-17 | 2024-03-25 | Closed
677 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | SECTION 4-4,5-5 - MT002-TDIC-GA10-4920000-0004 | 2024-05-07 | 2024-05-07 | Closed
678 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN 6.000,24.000,34.500 - MT002-TDIC-GA10-4920000-0005 | 2024-05-07 | 2024-05-07 | Closed
679 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION 6.000,29.800,34.500 - MT002-TDIC-GA10-4920000-0006 | 2024-05-07 | 2024-05-07 | Closed
680 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION 24.000-40.190,46.100 - MT002-TDIC-GA10-4920000-0007 | 2024-05-07 | 2024-05-07 | Closed
681 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION XXXX - MT002-TDIC-GA11-4920000-0001 | 2024-04-19 | 2024-05-07 | Closed
682 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION XXX - MT002-TDIC-GA11-4920000-0002 | 2024-04-19 | 2024-05-07 | Closed
683 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION XXX - MT002-TDIC-GA11-4920000-0003 | 2024-04-19 | 2024-05-07 | Closed
684 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PLAN FOUNDATION XXX - MT002-TDIC-GA11-4920000-0004 | 2024-04-19 | 2024-05-07 | Closed
685 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | 3D MODELING - MT002-TDIC-GA10-4920000-0000 | 2024-03-17 | 2024-03-25 | Closed
686 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | FLOW SHEET - MT002-TDIC-ME01-4920000-0001 | 2024-03-17 | 2024-03-25 | Closed
687 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4920000-0001 | 2024-03-17 | 2024-03-25 | Closed
688 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-4920000-0001 | 2024-09-08 |  | Open
689 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | Piping- Bill of quantities - MT002-TDIC-ME51-4920000-0001 | 2024-09-08 |  | Open
690 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | SCD1600×115144mm PAN CONVEYOR - MT002-TDIC-ME12-492AC01-0001 | 2024-05-07 | 2024-04-19 | Closed
691 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | DATASHEET of PAN CONVEYOR 492AC01 - MT002-TDIC-ME10-492AC02-0001 | 2024-05-07 | 2024-04-19 | Closed
692 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | SCD1600×63340mm PAN CONVEYOR - MT002-TDIC-ME12-492AC02-0001 | 2024-05-07 | 2024-04-19 | Closed
693 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | DATASHEET of PAN CONVEYOR 492AC02 - MT002-TDIC-ME10-492AC01-0001 | 2024-05-07 | 2024-04-19 | Closed
694 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | WAGON LOADER: PLAN VIEW AND SECTION VIEW - MT002-TDIC-ME12-6K2LA01-0001 | 2024-05-07 | 2024-03-05 | Closed
695 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | DATA SHEET - MT002-TDIC-ME10-6K2LA01-0001 | 2024-05-07 | 2024-03-05 | Closed
696 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | DATA SHEET - MT002-TDIC-ME10-6K2TC01-0001 | 2024-05-07 | 2024-03-05 | Closed
697 | Mechanical | Mechanical & Process | 492 - CLINKER TRANSPORT & STORAGE | CLINKER TRAIN BULK EQUIPMENT: PLAN VIEW AND SECTION VIEW - MT002-TDIC-ME12-6K2TC01-0001 | 2024-05-07 | 2024-03-05 | Closed
698 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | PLAN 34.000,39.400 - MT002-TDIC-GA10-6K20000-0001 | 2024-03-17 | 2024-01-28 | Closed
699 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | PLAN 7.400,10.200 - MT002-TDIC-GA10-6K20000-0002 | 2024-03-17 | 2024-01-28 | Closed
700 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | SECTION 1-1 - MT002-TDIC-GA10-6K20000-0003 | 2024-03-17 | 2024-01-28 | Closed
701 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | SECTION 2-2,3-3 - MT002-TDIC-GA10-6K20000-0004 | 2024-03-17 | 2024-01-28 | Closed
702 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | FLOW SHEET - MT002-TDIC-ME01-6K20000-0001 | 2024-03-17 | 2024-01-28 | Closed
703 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | Equipment List - MT002-TDIC-ME04-6K20000-0001 | 2024-03-17 | 2024-01-28 | Closed
704 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | 3D MODELING - MT002-TDIC-GA10-6K20000-0100 | 2024-03-17 |  | Open
705 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-6K20000-0001 | 2024-08-25 |  | Open
706 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | Piping- Bill of quantities - MT002-TDIC-ME51-6K20000-0001 | 2024-08-25 |  | Open
707 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | SCD1200×116635mm PAN CONVEYOR - MT002-TDIC-ME12-6K2AC01-0001 | 2024-05-07 | 2024-04-19 | Closed
708 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | DATASHEET of PAN CONVEYOR 6K2AC01 - MT002-TDIC-ME10-6K2AC02-0001 | 2024-05-07 | 2024-04-19 | Closed
709 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | SCD1200×132535mm PAN CONVEYOR - MT002-TDIC-ME12-6K2AC02-0001 | 2024-05-07 | 2024-04-19 | Closed
710 | Mechanical | Mechanical & Process | 6K2 -1 CLINKER CONVEYING TO LOADING SYSTEM | DATASHEET of PAN CONVEYOR 6K2AC02 - MT002-TDIC-ME10-6K2AC01-0001 | 2024-05-07 | 2024-04-19 | Closed
711 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | PLAN 34.000,39.400 - MT002-TDIC-GA10-6K20000-0001 | 2024-03-07 | 2024-01-30 | Closed
712 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | PLAN 7.400,10.200,15.950 - MT002-TDIC-GA10-6K20000-0002 | 2024-03-07 | 2024-01-30 | Closed
713 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | SECTION 1-1 - MT002-TDIC-GA10-6K20000-0003 | 2024-03-07 | 2024-01-30 | Closed
714 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | SECTION 2-2,3-3 - MT002-TDIC-GA10-6K20000-0004 | 2024-03-07 | 2024-01-30 | Closed
715 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | FLOW SHEET - MT002-TDIC-ME01-6K20000-0002 | 2024-03-07 | 2024-01-30 | Closed
716 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | Equipment List - MT002-TDIC-ME04-6K20000-0002 | 2024-03-07 | 2024-01-30 | Closed
717 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | 3D MODELING - MT002-TDIC-GA10-6K20000-0000 | 2024-03-07 |  | Open
718 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | BULK LOADER 6K2TC01 - MT002-TDIC-ME12-6K2TC01-0001 | 2024-05-07 | 2024-04-04 | Closed
719 | Mechanical | Mechanical & Process | 6K2-2 - CLINKER WAGON LOADING SYSTEM | DATASHEET of BULK LOADER 6K2TC01 - MT002-TDIC-ME10-6K2TC02-0001 | 2024-05-07 | 2024-04-04 | Closed
720 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | PLAN XXX - MT002-TDIC-GA10-L120000-0001 | 2024-05-21 |  | Open
721 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | PLAN XXX - MT002-TDIC-GA10-L120000-0002 | 2024-05-21 |  | Open
722 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | SECTION 1-1 - MT002-TDIC-GA10-L120000-0003 | 2024-05-21 |  | Open
723 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | SECTION 2-2,3-3 - MT002-TDIC-GA10-L120000-0004 | 2024-05-21 |  | Open
724 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | FLOW SHEET - MT002-TDIC-ME01-L120000-0001 | 2024-05-21 |  | Open
725 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | Equipment List - MT002-TDIC-ME04-L120000-0001 | 2024-05-21 |  | Open
726 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA AND LOAD DATA OF WAGON TIPPLER COMPLEX - MT002-TDIC-GA10-L12TI01-0001 | 2024-06-23 | 2024-06-23 | Closed
727 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GENERAL LAYOUT - MT002-TDIC-GA10-L12TI01-0004 | 2024-06-23 | 2024-06-23 | Closed
728 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | LOAD DATA AND FOUNDATION DETAILS OF SIDE ARM CHARGER - MT002-TDIC-GA11-L12SC01-0001 | 2024-06-23 | 2024-06-23 | Closed
729 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | LOAD DATA AND FOUNDATION DETAILS OF TRANSFER CAR AND EJECTOR - MT002-TDIC-GA11-L12SH01-0001 | 2024-06-23 | 2024-06-23 | Closed
730 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | LOAD DATA AND FOUNDATION DETAILS OF WAGON TIPPLER - MT002-TDIC-GA11-L12TI01-0001 | 2024-06-23 | 2024-06-23 | Closed
731 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | METAL SEPARATOR DATA SHEET - MT002-TDIC-ME10-L12MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
732 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-L12MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
733 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA AND LOAD DATA OF APRON CONVEYOR - MT002-TDIC-ME12-L12AF01-0001 | 2024-06-23 | 2024-06-23 | Closed
734 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA OF ROTASIDE SIDE ARM CHARGER - MT002-TDIC-ME12-L12SC01-0001 | 2024-06-23 | 2024-06-23 | Closed
735 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA OF TRANSFER CAR AND EJECTOR - MT002-TDIC-ME12-L12SH01-0001 | 2024-06-23 | 2024-06-23 | Closed
736 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA OF TRANSFER CAR AND EJECTOR - MT002-TDIC-ME12-L12SH01-0002 | 2024-06-23 | 2024-06-23 | Closed
737 | Mechanical | Mechanical & Process | L12-1 - COAL UNLOADING WAGON TIPPLER | GA OF ROTA-SIDE WAGON TIPPLER - MT002-TDIC-ME12-L12TI01-0001 | 2024-06-23 | 2024-06-23 | Closed
738 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | PLAN XXX - MT002-TDIC-GA10-L120000-0101 | 2024-05-21 |  | Open
739 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | PLAN XXX - MT002-TDIC-GA10-L120000-0102 | 2024-05-21 |  | Open
740 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | SECTION 1-1 - MT002-TDIC-GA10-L120000-0103 | 2024-05-21 |  | Open
741 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | SECTION 2-2,3-3 - MT002-TDIC-GA10-L120000-0104 | 2024-05-21 |  | Open
742 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | FLOW SHEET - MT002-TDIC-ME01-L120000-0002 | 2024-05-21 | 2024-10-09 | Closed
743 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | Equipment List - MT002-TDIC-ME04-L120000-0002 | 2024-05-21 | 2024-10-09 | Open
744 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | 3D MODELING - MT002-TDIC-GA10-L120000-0000 | 2024-05-21 |  | Open
745 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-L120000-0001 | 2024-12-15 |  | Open
746 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | Piping- Bill of quantities - MT002-TDIC-ME51-L120000-0001 | 2024-12-15 |  | Open
747 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | STACKER & RECLAIMER - MT002-TDIC-ME12-L12ST01-0001 | 2024-05-21 | 2024-06-23 | Closed
748 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | GENERAL ARRANGEMENT DRAWING FOR LUFFING STACKER ( L12ST01) - MT002-TDIC-ME12-L12ST01-0002 | 2024-05-21 | 2024-06-23 | Closed
749 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | STOCKPILE LAYOUT FOR COAL SYSTEM (L12ST01, L22RE01 & L23RE01) - MT002-TDIC-ME12-L12ST01-0003 | 2024-05-21 | 2024-06-23 | Closed
750 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | STOCKPILE LAYOUT FOR COAL SYSTEM (L12ST01, L22RE01 & L23RE01) - MT002-TDIC-ME12-L12ST01-0004 | 2024-05-21 | 2024-06-23 | Closed
751 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | WHEEL LOAD DATA FOR LUFFING STACKER ( L12ST01) - MT002-TDIC-ME12-L12ST01-0005 | 2024-05-21 | 2024-06-23 | Closed
752 | Mechanical | Mechanical & Process | L12-2 - COAL TRANSPORT TO STORAGE | DATASHEET of STACKER & RECLAIMER - MT002-TDIC-ME10-L12ST01-0001 | 2024-05-21 |  | Open
753 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | PLAN XXX - MT002-TDIC-GA10-L120000-0201 | 2024-05-21 |  | Open
754 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | PLAN XXX - MT002-TDIC-GA10-L120000-0202 | 2024-05-21 |  | Open
755 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | SECTION 1-1 - MT002-TDIC-GA10-L120000-0203 | 2024-05-21 |  | Open
756 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | SECTION 2-2,3-3 - MT002-TDIC-GA10-L120000-0204 | 2024-05-21 |  | Open
757 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | SIZER - MT002-TDIC-ME12-L12RC01-0001 | 2024-05-21 | 2024-07-28 | Closed
758 | Mechanical | Mechanical & Process | L12-3 - COAL CRUSHING SYSTEM | DATASHEET of SIZER - MT002-TDIC-ME10-L12RC01-0001 | 2024-05-21 | 2024-07-31 | Closed
759 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | PLAN LAYOUT - MT002-TDIC-GA10-L220000-0001 | 2024-05-11 | 2024-07-24 | Closed
760 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | SECTION 1-1，4-4 - MT002-TDIC-GA10-L220000-0002 | 2024-05-11 | 2024-07-24 | Closed
761 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | SECTION 2-2 - MT002-TDIC-GA10-L220000-0003 | 2024-05-11 | 2024-07-24 | Closed
762 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | SECTION 3-3 - MT002-TDIC-GA10-L220000-0004 | 2024-05-11 | 2024-07-24 | Closed
763 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | SECTION 5-5；PLAN 14.000 - MT002-TDIC-GA10-L220000-0003 | 2024-05-11 | 2024-07-24 | Closed
764 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | PLAN FOUNDATION ±0.000-3.000,±0.000-11.000 - MT002-TDIC-GA11-L220000-0001 | 2024-06-13 | 2024-07-24 | Closed
765 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | PLAN FOUNDATION 8.000-44.034；DETAIL D1-D5 - MT002-TDIC-GA11-L220000-0004 | 2024-06-13 |  | Open
766 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | FLOW SHEET - MT002-TDIC-ME01-L220000-0001 | 2024-05-11 | 2024-07-24 | Closed
767 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Equipment List - MT002-TDIC-ME04-L220000-0001 | 2024-05-11 | 2024-07-24 | Closed
768 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | 3D MODELING - MT002-TDIC-GA10-L220000-0000 | 2024-05-24 | 2024-07-24 | Closed
769 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-L220000-0001 | 2024-11-13 |  | Open
770 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Piping- Bill of quantities - MT002-TDIC-ME51-L220000-0001 | 2024-11-13 |  | Open
771 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | STOCK PILE LAYOUT FOR COAL & PETCOKE SYSTEM - MT002-TDIC-ME12-L22ST01-0001 | 2024-06-13 | 2024-06-23 | Closed
772 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | STOCK PILE LAYOUT FOR COAL & PETCOKE SYSTEM - MT002-TDIC-ME12-L22ST01-0002 | 2024-06-13 | 2024-06-23 | Closed
773 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | GENERAL ARRANGEMENT DRAWING FOR BRIDGE RECLAIMER (L22RE01) - MT002-TDIC-ME12-L22RE01-0001 | 2024-06-13 | 2024-06-23 | Closed
774 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER (COAL & PETCOKE HANDLING) (L22RE01 & L22RE02) - MT002-TDIC-ME12-L22RE01-0003 | 2024-06-13 | 2024-07-02 | Closed
775 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | WHEEL LOAD DATA OF BRIDGE RECLAIMER FOR COAL HANDLING(L22RE01) - MT002-TDIC-ME12-L22RE01-0002 | 2024-06-13 | 2024-06-23 | Closed
776 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | METAL SEPARATOR DATA SHEET - MT002-TDIC-ME10-L22MS01-0001 | 2024-06-13 | 2024-06-23 | Closed
777 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-L22MS01-0001 | 2024-06-13 | 2024-06-23 | Closed
778 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER (COAL & PETCOKE HANDLING) (L22RE01 & L22RE02) - MT002-TDIC-ME12-L22RE01-0004 | 2024-06-13 | 2024-07-02 | Closed
779 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER (COAL & PETCOKE HANDLING) (L22RE01 & L22RE02) - MT002-TDIC-ME12-L22RE01-0005 | 2024-06-13 | 2024-07-02 | Closed
780 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER (COAL & PETCOKE HANDLING) (L22RE01) - MT002-TDIC-ME12-L22RE01-0006 | 2024-06-13 | 2024-07-02 | Closed
781 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER (COAL & PETCOKE HANDLING) (L22RE02) - MT002-TDIC-ME12-L22RE01-0007 | 2024-06-13 | 2024-07-02 | Closed
782 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | RAIL FIXING & FOUNDATION ARRANGEMENT FOR BRIDGE RECLAIMER & SIDE SCRAPER RECLAIMER BUFFER TG-514 (COAL & PETCOKE HANDLING) (L22RE01 & L22RE02) - MT002-TDIC-ME12-L22RE01-0008 | 2024-06-13 | 2024-07-02 | Closed
783 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER PETCOKE HANDLING SYSTEM (L22RE02) - MT002-TDIC-ME12-L22RE02-0001 | 2024-06-13 |  | Open
784 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER PETCOKE HANDLING SYSTEM (L22RE02) - MT002-TDIC-ME12-L22RE02-0002 | 2024-06-13 |  | Open
785 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER PETCOKE HANDLING SYSTEM (L22RE02) - MT002-TDIC-ME12-L22RE02-0003 | 2024-06-13 |  | Open
786 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Needle Gate L22NG01 - MT002-TDIC-ME12-L22NG01-0001 | 2024-11-11 | 2024-08-18 | Closed
787 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Needle Gate L22NG02 - MT002-TDIC-ME12-L22NG02-0001 | 2024-11-11 | 2024-08-18 | Closed
788 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Belt Conveyor L22BC01 - MT002-TDIC-ME12-L22BC01-0001 | 2024-05-11 | 2024-08-15 | Closed
789 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Belt Conveyor L22BC02 - MT002-TDIC-ME12-L22BC02-0001 | 2024-05-11 | 2024-08-15 | Closed
790 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Belt Conveyor L22BC03 - MT002-TDIC-ME12-L22BC03-0001 | 2024-05-11 | 2024-08-15 | Closed
791 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | BMP Belt Scale L22BW01 - MT002-TDIC-ME12-L22BW01-0001 | 2024-05-11 | 2024-08-06 | Closed
792 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Bag Filter L22BF01 - MT002-TDIC-ME12-L22BF01-0001 | 2024-06-13 | 2024-06-13 | Closed
793 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Bag Filter L22BF02 - MT002-TDIC-ME12-L22BF02-0001 | 2024-06-13 | 2024-06-13 | Closed
794 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | FAN L22FN01 - MT002-TDIC-ME12-L22FN01-0001 | 2024-06-13 | 2024-09-30 | Closed
795 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | FAN L22FN02 - MT002-TDIC-ME12-L22FN02-0001 | 2024-06-13 | 2024-09-30 | Closed
796 | Mechanical | Mechanical & Process | L22-1 - COAL RECLAIMING AND STORAGE | Metal Detector L22MY01 - MT002-TDIC-ME12-L22MY01-0001 | 2024-06-13 |  | Open
797 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | PLAN LAYOUT - MT002-TDIC-GA10-L220000-0101 | 2024-05-11 |  | Open
798 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | SECTION 1-1，4-4 - MT002-TDIC-GA10-L220000-0102 | 2024-05-11 |  | Open
799 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | SECTION 2-2 - MT002-TDIC-GA10-L220000-0103 | 2024-05-11 |  | Open
800 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | SECTION 3-3 - MT002-TDIC-GA10-L220000-0104 | 2024-05-11 |  | Open
801 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | SECTION 5-5；PLAN 14.000 - MT002-TDIC-GA10-L220000-0103 | 2024-05-11 |  | Open
802 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | PLAN FOUNDATION ±0.000-3.000,±0.000-11.000 - MT002-TDIC-GA11-L220000-0101 | 2024-06-13 |  | Open
803 | Mechanical | Mechanical & Process | L22-2 - COAL CONVEYING TO NEW LINE | PLAN FOUNDATION 8.000-44.034；DETAIL D1-D5 - MT002-TDIC-GA11-L220000-0102 | 2024-06-13 |  | Open
804 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | PLAN LAYOUT - MT002-TDIC-GA10-L220000-0201 | 2024-05-11 |  | Open
805 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | SECTION 1-1，4-4 - MT002-TDIC-GA10-L220000-0202 | 2024-05-11 |  | Open
806 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | SECTION 2-2 - MT002-TDIC-GA10-L220000-0203 | 2024-05-11 |  | Open
807 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | SECTION 3-3 - MT002-TDIC-GA10-L220000-0204 | 2024-05-11 |  | Open
808 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | SECTION 5-5；PLAN 14.000 - MT002-TDIC-GA10-L220000-0205 | 2024-05-11 |  | Open
809 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | PLAN FOUNDATION ±0.000-3.000,±0.000-11.000 - MT002-TDIC-GA11-L220000-0201 | 2024-06-13 |  | Open
810 | Mechanical | Mechanical & Process | L22-3 - COAL CONVEYING TO EXSITNG LINE | PLAN FOUNDATION 8.000-44.034；DETAIL D1-D5 - MT002-TDIC-GA11-L220000-0202 | 2024-06-13 |  | Open
811 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | PLAN LAYOUT - MT002-TDIC-GA10-L230000-0001 | 2024-05-11 |  | Open
812 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | SECTION 1-1，4-4 - MT002-TDIC-GA10-L230000-0002 | 2024-05-11 |  | Open
813 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | SECTION 2-2 - MT002-TDIC-GA10-L230000-0003 | 2024-05-11 |  | Open
814 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | SECTION 3-3 - MT002-TDIC-GA10-L230000-0004 | 2024-05-11 |  | Open
815 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | PLAN XX - MT002-TDIC-GA10-L230000-0005 | 2024-05-11 |  | Open
816 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | PLAN FOUNDATION XXX - MT002-TDIC-GA11-L230000-0001 | 2024-06-13 |  | Open
817 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | PLAN FOUNDATION XXX - MT002-TDIC-GA11-L230000-0002 | 2024-06-13 |  | Open
818 | Mechanical | Mechanical & Process | L23-1 - COAL RECLAIMING AND TRANSPORT | 3D MODELING - MT002-TDIC-GA10-L230000-0000 | 2024-05-11 |  | Open
819 | Mechanical | Mechanical & Process | L23-5 - COAL RECLAIMING AND TRANSPORT | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-L230000-0001 | 2024-03-11 |  | Open
820 | Mechanical | Mechanical & Process | L23-5 - COAL RECLAIMING AND TRANSPORT | Piping- Bill of quantities - MT002-TDIC-ME51-L230000-0001 | 2024-03-11 |  | Open
821 | Mechanical | Mechanical & Process | L23-2 - COAL RECLAIMING AND TRANSPORT | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-L23MS01-0001 | 2024-06-23 | 2024-06-23 | Closed
822 | Mechanical | Mechanical & Process | L23-2 - COAL RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER (L23RE01) - MT002-TDIC-ME12-L23RE01-0001 | 2024-06-23 | 2024-06-23 | Closed
823 | Mechanical | Mechanical & Process | L23-2 - COAL RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER (L23RE01) - MT002-TDIC-ME12-L23RE01-0002 | 2024-06-23 | 2024-06-23 | Closed
824 | Mechanical | Mechanical & Process | L23-2 - COAL RECLAIMING AND TRANSPORT | WHEEL LOAD DATA FOR SIDE SCRAPER RECLAIMER (L23RE01) - MT002-TDIC-ME12-L23RE01-0003 | 2024-06-23 | 2024-06-23 | Closed
825 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | PLAN LAYOUT - MT002-TDIC-GA10-L230000-0101 | 2024-05-11 |  | Open
826 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | SECTION 1-1 - MT002-TDIC-GA10-L230000-0102 | 2024-05-11 |  | Open
827 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | SECTION 2-2 - MT002-TDIC-GA10-L230000-0103 | 2024-05-11 |  | Open
828 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | SECTION 3-3 - MT002-TDIC-GA10-L230000-0104 | 2024-05-11 |  | Open
829 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | PLAN XX - MT002-TDIC-GA10-L230000-0105 | 2024-05-11 |  | Open
830 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | PLAN FOUNDATION XXX - MT002-TDIC-GA11-L230000-0101 | 2024-06-13 |  | Open
831 | Mechanical | Mechanical & Process | L23-2 - COAL TRANSPORT TO EXISTING CPP | PLAN FOUNDATION XXX - MT002-TDIC-GA11-L230000-0102 | 2024-06-13 |  | Open
832 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN LAYOUT - MT002-TDIC-GA10-L620000-0001 | 2024-03-07 | 2024-02-09 | Closed
833 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 1-1 - MT002-TDIC-GA10-L620000-0002 | 2024-03-07 | 2024-02-09 | Closed
834 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 2-2 - MT002-TDIC-GA10-L620000-0003 | 2024-03-07 | 2024-02-09 | Closed
835 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 3-3,4-4,5-5 - MT002-TDIC-GA10-L620000-0004 | 2024-03-07 | 2024-02-09 | Closed
836 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 6-6,7-7 - MT002-TDIC-GA10-L620000-0005 | 2024-03-07 | 2024-02-09 | Closed
837 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 8-8,9-9 - MT002-TDIC-GA10-L620000-0006 | 2024-03-07 | 2024-02-09 | Closed
838 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN 16.000,17.100,24.500,27.100,30.300,32.800 - MT002-TDIC-GA10-L620000-0007 | 2024-03-07 | 2024-02-09 | Closed
839 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN 2.500,7.200(I),7.200(II),20.200,26.300, 34.400,35.500,40.800,42.000,52.000,62.500 - MT002-TDIC-GA10-L620000-0008 | 2024-03-07 | 2024-02-09 | Closed
840 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 10-10,11-11,12-12,VIEW A - MT002-TDIC-GA10-L620000-0009 | 2024-03-07 | 2024-02-09 | Closed
841 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN 3.300,4.300,6.000,6.800,8.300,13.850,20.000,38.000,39.000 - MT002-TDIC-GA10-L620000-0010 | 2024-03-07 | 2024-02-09 | Closed
842 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | SECTION 13-13 - MT002-TDIC-GA10-L620000-0011 | 2024-03-07 | 2024-02-09 | Closed
843 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN FOUNDATION ±0.000,41.500,DETAIL D14 - MT002-TDIC-GA11-L620000-0001 | 2024-05-29 | 2024-02-09 | Closed
844 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN FOUNDATION 6.000,7.200(I),7.200(II),16.000,17.100,26.300,42.600 - MT002-TDIC-GA11-L620000-0002 | 2024-05-29 | 2024-02-09 | Closed
845 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN FOUNDATION ±0.000-9.600,12.900,20.200,27.100,30.300,32.800,35.500 - MT002-TDIC-GA11-L620000-0003 | 2024-05-29 | 2024-02-09 | Closed
846 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PLAN FOUNDATION 2.500,3.000,3.300,4.500,13.850,23.500,24.500 - MT002-TDIC-GA11-L620000-0004 | 2024-05-29 | 2024-02-09 | Closed
847 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FLOW SHEET - MT002-TDIC-ME01-L620000-0001 | 2024-03-07 | 2024-02-09 | Closed
848 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-L620000-0001 | 2024-03-07 | 2024-02-09 | Closed
849 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FLOW SHEET - MT002-TDIC-ME01-L920000-0001 | 2024-03-07 | 2024-02-09 | Closed
850 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-L920000-0001 | 2024-03-07 | 2024-02-09 | Closed
851 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FLOW SHEET - MT002-TDIC-ME01-4520000-0001 | 2024-03-07 | 2024-02-09 | Closed
852 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4520000-0001 | 2024-03-07 | 2024-02-09 | Closed
853 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FLOW SHEET - MT002-TDIC-ME01-4820000-0001 | 2024-03-07 | 2024-02-09 | Closed
854 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-4820000-0001 | 2024-03-07 | 2024-02-09 | Closed
855 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | 3D MODELING - MT002-TDIC-GA10-L620000-0000 | 2024-03-07 | 2024-03-26 | Closed
856 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | HEAT BALANCE - MT002-TDIC-ME03-L62RM01-0001 | 2024-03-07 | 2024-05-28 | Closed
857 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PROCESS PIPING DRAWING - MT002-TDIC-ME50-L620000-0001 | 2024-10-11 |  | Open
858 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | LIST OF PROCESS PIPING MATERIAL - MT002-TDIC-ME51-L620000-0001 | 2024-10-11 |  | Open
859 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-L62RM01-0001 | 2024-03-07 | 2024-03-11 | Closed
860 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | TRMC42.4 Outline Drawing of Roller Mill - MT002-TDIC-ME12-L62RM01-0001 | 2024-03-07 | 2024-03-11 | Closed
861 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | TRMC42.4 Foundation Drawing - MT002-TDIC-ME12-L62RM01-0002 | 2024-03-07 | 2024-03-11 | Closed
862 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FAN L62FA01 - MT002-TDIC-ME12-L62FA01-0001 | 2024-05-07 |  | Open
863 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | TDM(M)-126/2×12 COAL MILL BAG FILTER - MT002-TDIC-ME12-L62BF01-0001 | 2024-05-07 | 2024-04-27 | Closed
864 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | TECHNICAL INFORMATION - MT002-TDIC-ME12-L62BF01-0002 | 2024-05-07 | 2024-04-27 | Closed
865 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | STEEL SUPPORT LAYOUT AND LOADS - MT002-TDIC-ME12-L62BF01-0003 | 2024-05-07 | 2024-04-27 | Closed
866 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | GAS FLOW - MT002-TDIC-ME12-L62BF01-0004 | 2024-05-07 | 2024-04-27 | Closed
867 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | EQUIPMENT DRAWING - MT002-TDIC-ME12-L62FN01-0001 | 2024-05-07 | 2024-05-24 | Closed
868 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Bag Filter L62BF02 - MT002-TDIC-ME12-L62BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
869 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Bag Filter L62BF03 - MT002-TDIC-ME12-L62BF03-0001 | 2024-10-11 | 2024-08-28 | Closed
870 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Bag Filter L92BF01 - MT002-TDIC-ME12-L92BF01-0001 | 2024-10-11 | 2024-08-28 | Closed
871 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Bag Filter L92BF02 - MT002-TDIC-ME12-L92BF02-0001 | 2024-10-11 | 2024-08-28 | Closed
872 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FAN L62FA02 - MT002-TDIC-ME12-L62FN02-0001 | 2024-10-11 | 2024-09-30 | Closed
873 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FAN L62FA03 - MT002-TDIC-ME12-L62FN03-0001 | 2024-10-11 | 2024-09-30 | Closed
874 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FAN L92FN01 - MT002-TDIC-ME12-L92FN01-0001 | 2024-10-11 | 2024-09-30 | Closed
875 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | FAN L92FN02 - MT002-TDIC-ME12-L92FN02-0001 | 2024-10-11 | 2024-09-30 | Closed
876 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Load Cell L62LC01~03 - MT002-TDIC-ME12-L62LC01-0001 | 2024-10-11 | 2024-08-09 | Closed
877 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Load Cell L62LC04~06 - MT002-TDIC-ME12-L62LC04-0001 | 2024-10-11 | 2024-08-09 | Closed
878 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MT500×38395mm CHAIN CONVEYOR - MT002-TDIC-ME12-L62CV01-0001 | 2024-10-11 | 2024-04-17 | Closed
879 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-L62CV01-0001 | 2024-10-11 | 2024-04-17 | Closed
880 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | BELT WEIGHT FEEDER L62WF01 - MT002-TDIC-ME12-L62WF01-0001 | 2024-05-11 | 2024-08-27 | Closed
881 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | BELT WEIGHT FEEDER L62WF02 - MT002-TDIC-ME12-L62WF02-0001 | 2024-05-11 | 2024-08-27 | Closed
882 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD800×9500mm SCREW CONVEYOR - MT002-TDIC-ME12-L92SC01-0001 | 2024-05-11 | 2024-04-17 | Closed
883 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD800×9500mm SCREW CONVEYOR - MT002-TDIC-ME12-L92SC02-0001 | 2024-05-11 | 2024-04-17 | Closed
884 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD1250×9000mm SCREW CONVEYOR - MT002-TDIC-ME12-L92SC05-0001 | 2024-05-11 | 2024-04-17 | Closed
885 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD1250×9900mm SCREW CONVEYOR - MT002-TDIC-ME12-L92SC06-0001 | 2024-05-11 | 2024-04-17 | Closed
886 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD800×9500mm SCREW CONVEYOR - MT002-TDIC-ME10-L92SC01-0001 | 2024-05-11 | 2024-04-17 | Closed
887 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD800×9500mm SCREW CONVEYOR - MT002-TDIC-ME10-L92SC02-0001 | 2024-05-11 | 2024-04-17 | Closed
888 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD1250×9000mm SCREW CONVEYOR - MT002-TDIC-ME10-L92SC05-0001 | 2024-05-11 | 2024-04-17 | Closed
889 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | MTD1250×9900mm SCREW CONVEYOR - MT002-TDIC-ME10-L92SC06-0001 | 2024-05-11 | 2024-04-17 | Closed
890 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Belt Conveyor L62BC01 - MT002-TDIC-ME12-L62BC01-0001 | 2024-08-11 | 2024-08-15 | Closed
891 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | BUTTERFLY DAMPER L62BV01 - MT002-TDIC-ME12-L62BV01-0001 | 2024-10-11 | 2024-08-18 | Closed
892 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | BUTTERFLY DAMPER L62BV02 - MT002-TDIC-ME12-L62BV02-0001 | 2024-10-11 | 2024-08-18 | Closed
893 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Explosion Gate L62EX01 - MT002-TDIC-ME12-L62EX01-0001 | 2024-10-11 | 2024-08-18 | Closed
894 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Explosion Gate L62EX02 - MT002-TDIC-ME12-L62EX02-0001 | 2024-10-11 | 2024-08-18 | Closed
895 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Louver Damper L62LD01 - MT002-TDIC-ME12-L62LD01-0001 | 2024-10-11 | 2024-08-18 | Closed
896 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Louver Damper L62LD02 - MT002-TDIC-ME12-L62LD02-0001 | 2024-10-11 | 2024-08-18 | Closed
897 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Louver Damper L62LD03 - MT002-TDIC-ME12-L62LD03-0001 | 2024-10-11 | 2024-08-18 | Closed
898 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Needle Gate L62NG01 - MT002-TDIC-ME12-L62NG01-0001 | 2024-10-11 | 2024-08-18 | Closed
899 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Needle Gate L62NG02 - MT002-TDIC-ME12-L62NG02-0001 | 2024-10-11 | 2024-08-18 | Closed
900 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Shut-off Damper L62SD01 - MT002-TDIC-ME12-L62SD01-0001 | 2024-10-11 | 2024-08-18 | Closed
901 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Shut-off Damper L62SD02 - MT002-TDIC-ME12-L62SD02-0001 | 2024-10-11 | 2024-08-18 | Closed
902 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Moterized Shut-off Damper L62SD03 - MT002-TDIC-ME12-L62SD03-0001 | 2024-10-11 | 2024-08-18 | Closed
903 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Moterized Shut-off Damper L62SD04 - MT002-TDIC-ME12-L62SD04-0001 | 2024-10-11 | 2024-08-18 | Closed
904 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Moterized Shut-off Damper L62SD05 - MT002-TDIC-ME12-L62SD05-0001 | 2024-10-11 | 2024-08-18 | Closed
905 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Shut-off Damper L62SG16 - MT002-TDIC-ME12-L62SG16-0001 | 2024-10-11 | 2024-08-18 | Closed
906 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pneumatic Shut-off Damper L62SG17 - MT002-TDIC-ME12-L62SG17-0001 | 2024-10-11 | 2024-08-18 | Closed
907 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Shut-off Damper L62SG18 - MT002-TDIC-ME12-L62SG18-0001 | 2024-10-11 | 2024-08-18 | Closed
908 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pneumatic Shut-off Damper L62SG19 - MT002-TDIC-ME12-L62SG19-0001 | 2024-10-11 | 2024-08-18 | Closed
909 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Explosion Gate L92EX01 - MT002-TDIC-ME12-L92EX01-0001 | 2024-10-11 | 2024-08-18 | Closed
910 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Explosion Gate L92EX02 - MT002-TDIC-ME12-L92EX02-0001 | 2024-10-11 | 2024-08-18 | Closed
911 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Rotary Airlock L92RF01 - MT002-TDIC-ME12-L92RF01-0001 | 2024-10-11 | 2024-08-18 | Closed
912 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Rotary Airlock L92RF02 - MT002-TDIC-ME12-L92RF02-0001 | 2024-10-11 | 2024-08-18 | Closed
913 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pneumatic Shut-off Damper L92SG01~02 - MT002-TDIC-ME12-L92SG01~02-0001 | 2024-10-11 | 2024-08-18 | Closed
914 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pneumatic Shut-off Damper L92SG03~04 - MT002-TDIC-ME12-L92SG03~04-0001 | 2024-10-11 | 2024-08-18 | Closed
915 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Mannual Screw Gate L92SG05~06 - MT002-TDIC-ME12-L92SG05~06-0001 | 2024-10-11 | 2024-08-18 | Closed
916 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pnuematic Shut-off Damper 452SG01 - MT002-TDIC-ME12-452SG01-0001 | 2024-10-11 | 2024-08-18 | Closed
917 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pnuematic Shut-off Damper 452SG03 - MT002-TDIC-ME12-452SG03-0001 | 2024-10-11 | 2024-08-18 | Closed
918 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pnuematic Cut-off Valve 452VA01 - MT002-TDIC-ME12-452VA01-0001 | 2024-10-11 |  | Open
919 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pnuematic Cut-off Valve 452VA02 - MT002-TDIC-ME12-452VA02-0001 | 2024-10-11 |  | Open
920 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PULVERIZED COAL WEIGH FEEDER - MT002-TDIC-ME12-452PF01-0001 | 2024-10-11 | 2024-04-19 | Closed
921 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-452PF01-0001 | 2024-10-11 | 2024-04-19 | Closed
922 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-452PF02-0001 | 2024-10-11 | 2024-04-19 | Closed
923 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Pnuematic Shut-off Damper 482SG01 - MT002-TDIC-ME12-482SG01-0001 | 2024-10-11 | 2024-08-18 | Closed
924 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Sampler L92SM01 - MT002-TDIC-ME12-L92SM01-0001 | 2024-10-11 | 2024-05-15 | Closed
925 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-452BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
926 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-452BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
927 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Roots Blower 452BL01 - MT002-TDIC-ME12-452BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
928 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Roots Blower 452BL02 - MT002-TDIC-ME12-452BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
929 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-482BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
930 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-482BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
931 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Roots Blower 482BL01 - MT002-TDIC-ME12-482BL01-0001 | 2024-05-11 | 2024-05-27 | Closed
932 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Roots Blower 482BL02 - MT002-TDIC-ME12-482BL02-0001 | 2024-05-11 | 2024-05-27 | Closed
933 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | PULVERIZED COAL WEIGH FEEDER - MT002-TDIC-ME12-482PF01-0001 | 2024-04-11 | 2024-04-19 | Closed
934 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | DATA SHEET - MT002-TDIC-ME10-482PF01-0001 | 2024-04-11 | 2024-04-19 | Closed
935 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0001 | 2024-04-11 |  | Open
936 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0002 | 2024-04-11 | 2024-06-28 | Closed
937 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0003 | 2024-04-11 | 2024-08-12 | Closed
938 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0004 | 2024-04-11 | 2024-08-12 | Closed
939 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0005 | 2024-04-11 | 2024-08-12 | Closed
940 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0006 | 2024-04-11 | 2024-08-12 | Closed
941 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0007 | 2024-04-11 | 2024-08-12 | Closed
942 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0008 | 2024-04-11 | 2024-08-12 | Closed
943 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0009 | 2024-04-11 | 2024-08-12 | Closed
944 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Nitrogen generation L62IP01 - MT002-TDIC-ME12-L62IP01-0001 | 2024-04-11 |  | Open
945 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Electric Hoist L62EH01 - MT002-TDIC-ME12-L62EH01-0001 | 2024-10-11 |  | Open
946 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Electric Hoist 452EH01 - MT002-TDIC-ME12-452EH01-0001 | 2024-10-11 |  | Open
947 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | Electric Hoist 482EH02 - MT002-TDIC-ME12-482EH01-0001 | 2024-10-11 |  | Open
948 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ02-0001 | 2024-10-11 | 2024-06-08 | Closed
949 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ03-0001 | 2024-10-11 | 2024-06-08 | Closed
950 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ04-0001 | 2024-10-11 | 2024-06-08 | Closed
951 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ06-0001 | 2024-10-11 | 2024-06-08 | Closed
952 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ08-0001 | 2024-10-11 | 2024-06-08 | Closed
953 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ10-0001 | 2024-10-11 | 2024-06-08 | Closed
954 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ11-0001 | 2024-10-11 | 2024-06-08 | Closed
955 | Mechanical | Mechanical & Process | L62 - FUEL GRINDING | METAL EXPANSION JOINT - MT002-TDIC-ME12-L62EJ13-0001 | 2024-10-11 | 2024-06-08 | Closed
956 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | PLAN LAYOUT - MT002-TDIC-GA10-K920000-0001 | 2024-05-11 |  | Open
957 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | SECTION 1-1 - MT002-TDIC-GA10-K920000-0002 | 2024-05-11 |  | Open
958 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | SECTION 2-2 - MT002-TDIC-GA10-K920000-0003 | 2024-05-11 |  | Open
959 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | FLOW SHEET - MT002-TDIC-ME01-K920000-0001 | 2024-05-11 | 2024-07-24 | Closed
960 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | Process Equipment List - MT002-TDIC-ME04-K920000-0001 | 2024-05-11 | 2024-07-24 | Closed
961 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | 3D modeling - MT002-TDIC-GA10-K920000-0000 | 2024-05-11 |  | Open
962 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-K920000-0001 | 2024-11-13 |  | Open
963 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | Piping- Bill of quantities - MT002-TDIC-ME51-K920000-0001 | 2024-11-13 |  | Open
964 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | STOCK PILE LAYOUT FOR ADDITIVE SYSTEM - MT002-TDIC-ME12-K920000-0001 | 2024-06-13 |  | Open
965 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER ( K92RE01) - MT002-TDIC-ME12-K92RE01-0001 | 2024-06-13 | 2024-06-23 | Closed
966 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR SIDE SCRAPER RECLAIMER ( K92RE01) - MT002-TDIC-ME12-K92RE01-0002 | 2024-06-13 | 2024-06-23 | Closed
967 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | WHEEL LOAD DATA FOR SIDE SCRAPER RECLAIMER (K92RE01) - MT002-TDIC-ME12-K92RE01-0003 | 2024-06-13 | 2024-06-23 | Closed
968 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | METAL SEPARATOR DATA SHEET - MT002-TDIC-ME10-K92MS01-0001 | 2024-06-13 | 2024-06-23 | Closed
969 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | METAL SEPARATOR EQUIPMENT DRAWING - MT002-TDIC-ME12-K92MS01-0001 | 2024-06-13 | 2024-06-23 | Closed
970 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | GA DRAWING FOR LUFFING STACKER - MT002-TDIC-ME12-K92ST01-0001 | 2024-06-13 |  | Open
971 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR LUFFING STACKER ADDITIVE HANDLING SYSTEM (K92ST01) - MT002-TDIC-ME12-K92ST01-0002 | 2024-06-13 |  | Open
972 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR LUFFING STACKER ADDITIVE HANDLING SYSTEM (K92ST01) - MT002-TDIC-ME12-K92ST01-0003 | 2024-06-13 |  | Open
973 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | WHEEL LOAD DATA FOR LUFFING STACKER ADDITIVE HANDLING SYSTEM (K92ST01) - MT002-TDIC-ME12-K92ST01-0004 | 2024-06-13 |  | Open
974 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | RAIL FIXING & FOUNDATION ARRANGEMENT FOR LUFFING STACKER (K92ST01) (ADDITIVE HANDLING) - MT002-TDIC-ME12-K92ST01-0005 | 2024-06-13 |  | Open
975 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | RAIL FIXING & FOUNDATION ARRANGEMENT FOR LUFFING STACKER (K92ST01) (ADDITIVE HANDLING) - MT002-TDIC-ME12-K92ST01-0006 | 2024-06-13 |  | Open
976 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | RAIL FIXING & FOUNDATION ARRANGEMENT FOR LUFFING STACKER (K92ST01) (ADDITIVE HANDLING) - MT002-TDIC-ME12-K92ST01-0007 | 2024-06-13 |  | Open
977 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | RAIL FIXING & FOUNDATION ARRANGEMENT FOR LUFFING STACKER (K92ST01) BUFFER TG-514 (ADDITIVE HANDLING) - MT002-TDIC-ME12-K92ST01-0008 | 2024-06-13 |  | Open
978 | Mechanical | Mechanical & Process | K92-ADDITIVES RECLAIMING AND TRANSPORT | DATASHEET of K92ST01 - MT002-TDIC-ME10-K92ST01-0001 | 2024-06-13 |  | Open
979 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | PLAN LAYOUT - MT002-TDIC-GA10-X120000-0001 | 2024-05-11 | 2024-08-19 | Closed
980 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | SECTION 1-1 - MT002-TDIC-GA10-X120000-0002 | 2024-05-11 | 2024-08-19 | Closed
981 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | SECTION 2-2,3-3 - MT002-TDIC-GA10-X120000-0003 | 2024-05-11 | 2024-08-19 | Closed
982 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | SECTION 4-4 - MT002-TDIC-GA10-X120000-0004 | 2024-05-11 | 2024-08-19 | Closed
983 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | PLAN FOUNDATION -4.700- -3.700,±0.000,13.500 - MT002-TDIC-GA11-X120000-0001 | 2024-06-28 | 2024-08-19 | Closed
984 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | PLAN FOUNDATION -6.500 - 9.500,5.900,6.300 - MT002-TDIC-GA11-X120000-0002 | 2024-06-28 | 2024-08-19 | Closed
985 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | FLOW SHEET - MT002-TDIC-ME01-X120000-0001 | 2024-05-11 | 2024-07-24 | Closed
986 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-X120000-0001 | 2024-05-11 | 2024-07-24 | Closed
987 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | 3D modeling - MT002-TDIC-GA10-X120000-0000 | 2024-05-11 | 2024-09-28 | Closed
988 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-X120000-0001 | 2024-12-15 |  | Open
989 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Piping- Bill of quantities - MT002-TDIC-ME51-X120000-0001 | 2024-12-15 |  | Open
990 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Surface Feeder X12SF01 - MT002-TDIC-ME12-X12SF01-0001 | 2024-05-11 | 2024-08-12 | Closed
991 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | DATASHEET of Surface Feeder X12SF01 - MT002-TDIC-ME10-X12SF01-0001 | 2024-05-11 |  | Open
992 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | SIZER - MT002-TDIC-ME12-X12RC01-0001 | 2024-05-21 | 2024-07-28 | Closed
993 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | DATASHEET of SIZER - MT002-TDIC-ME10-X12RC01-0001 | 2024-05-21 | 2024-07-31 | Closed
994 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Bag Filter X12BF01 - MT002-TDIC-ME12-X12BF01-0001 | 2024-08-11 | 2024-09-02 | Closed
995 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Bag Filter X12BF02 - MT002-TDIC-ME12-X12BF02-0001 | 2024-08-11 | 2024-09-02 | Closed
996 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Bag Filter X12BF03 - MT002-TDIC-ME12-X12BF03-0001 | 2024-08-11 | 2024-09-02 | Closed
997 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | FAN X12FN01 - MT002-TDIC-ME12-X12FN01-0001 | 2024-08-11 | 2024-09-30 | CLosed
998 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | FAN X12FN02 - MT002-TDIC-ME12-X12FN02-0001 | 2024-08-11 | 2024-09-30 | Closed
999 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | FAN X12FN03 - MT002-TDIC-ME12-X12FN03-0001 | 2024-08-11 | 2024-09-30 | Closed
1000 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Belt Conveyor X12BC01 - MT002-TDIC-ME12-X12BC01-0001 | 2024-08-11 | 2024-08-15 | Closed
1001 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Belt Conveyor X12BC02 - MT002-TDIC-ME12-X12BC02-0001 | 2024-08-11 | 2024-08-15 | Closed
1002 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Belt Scale X12BW01 - MT002-TDIC-ME12-X12BW01-0001 | 2024-08-11 | 2024-08-06 | Closed
1003 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | Magnetic Separator X12MS01 - MT002-TDIC-ME12-X12MS01-0001 | 2024-08-11 | 2024-06-23 | Closed
1004 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | TRUCK TIPPLER SPRAY DUST SUPPRESSION SYSTEM 1 - MT002-TDIC-ME12-X12IJ01-0001 | 2024-08-11 | 2024-06-08 | Closed
1005 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | TRUCK TIPPLER SPRAY DUST SUPPRESSION SYSTEM 2 - MT002-TDIC-ME12-X12IJ01-0002 | 2024-08-11 | 2024-06-08 | Closed
1006 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR LUFFING STACKER (X12ST01) - MT002-TDIC-ME12-X12ST01- 0001 | 2024-08-11 | 2024-06-23 | Closed
1007 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | GENERAL ARRANGEMENT DRAWING FOR LUFFING STACKER (X12ST01) - MT002-TDIC-ME12-X12ST01- 0002 | 2024-08-11 | 2024-06-23 | Closed
1008 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | STOCKPILE LAYOUT FOR ADDITIVE & CORRECTIVE SYSTEM(X12ST01, K92RE01 & X92RE01) - MT002-TDIC-ME12-X12ST01- 0003 | 2024-08-11 | 2024-06-23 | Closed
1009 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | STOCKPILE LAYOUT FOR ADDITIVE & CORRECTIVE SYSTEM(X12ST01, K92RE01 & X92RE01) - MT002-TDIC-ME12-X12ST01- 0004 | 2024-08-11 | 2024-06-23 | Closed
1010 | Mechanical | Mechanical & Process | X12 - CORRECTIVES UNLOADING AND TRANSPORT | WHEEL LOAD DATA FOR LUFFING STACKER ( X12ST01) - MT002-TDIC-ME12-X12ST01- 0005 | 2024-08-11 | 2024-06-23 | Closed
1011 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN LAYOUT - MT002-TDIC-GA10-X920000-0001 | 2024-05-11 | 2024-07-24 | Closed
1012 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | SECTION 1-1, SECTION 2-2 - MT002-TDIC-GA10-X920000-0002 | 2024-05-11 | 2024-07-24 | Closed
1013 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | SECTION 3-3 - MT002-TDIC-GA10-X920000-0003 | 2024-05-11 | 2024-07-24 | Closed
1014 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | SECTION 4-4 - MT002-TDIC-GA10-X920000-0004 | 2024-05-11 | 2024-07-24 | Closed
1015 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | SECTION 5-5 - MT002-TDIC-GA10-X920000-0005 | 2024-05-11 | 2024-07-24 | Closed
1016 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | SECTION 6-6 - MT002-TDIC-GA10-X920000-0006 | 2024-05-11 | 2024-07-24 | Closed
1017 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN ±0.000-10.000 - MT002-TDIC-GA10-X920000-0007 | 2024-05-11 | 2024-07-24 | Closed
1018 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN 7.000-9.500 - MT002-TDIC-GA10-X920000-0008 | 2024-05-11 |  | Open
1019 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN 6.300,9.500,12.500 - MT002-TDIC-GA10-X920000-0009 | 2024-05-11 |  | Open
1020 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN FOUNDATION ±0.000,3.800 - MT002-TDIC-GA11-X920000-0001 | 2024-06-13 | 2024-07-24 | Closed
1021 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN FOUNDATION ±0.000-10.000,3.500,6.200,13.200 - MT002-TDIC-GA11-X920000-0002 | 2024-06-13 |  | Open
1022 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN FOUNDATION 7.000-9.500 - MT002-TDIC-GA11-X920000-0003 | 2024-06-13 |  | Open
1023 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | PLAN FOUNDATION 3.700,6.300,9.500,12.500 - MT002-TDIC-GA11-X920000-0004 | 2024-06-13 |  | Open
1024 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | FLOW SHEET - MT002-TDIC-ME01-X920000-0001 | 2024-05-11 | 2024-07-24 | Closed
1025 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | 3D modeling - MT002-TDIC-GA10-X920000-0000 | 2024-05-11 | 2024-07-24 | Closed
1026 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-X920000-0001 | 2024-11-12 |  | Open
1027 | Mechanical | Mechanical & Process | X92 - CORRECTIVES RECLAIMING AND TRANSPORT | Stacker X13ST01 - MT002-TDIC-ME12-X13ST01-0001 | 2024-05-11 |  | Open
1028 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | PLAN LAYOUT - MT002-TDIC-GA10-X920000-0101 | 2024-05-11 |  | Open
1029 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | SECTION 1-1 - MT002-TDIC-GA10-X920000-0102 | 2024-05-11 |  | Open
1030 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | SECTION 2-2 - MT002-TDIC-GA10-X920000-0103 | 2024-05-11 |  | Open
1031 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | PLAN ±0.000-10.000 - MT002-TDIC-GA10-X920000-0104 | 2024-05-11 |  | Open
1032 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | PLAN 7.000-9.500 - MT002-TDIC-GA10-X920000-0105 | 2024-05-11 |  | Open
1033 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | PLAN FOUNDATION ±0.000-10.000 - MT002-TDIC-GA11-X920000-0101 | 2024-06-13 |  | Open
1034 | Mechanical | Mechanical & Process | X92-2- CORRECTIVES TRANSPORT TO EXISTING LINE | PLAN FOUNDATION 7.000-9.500 - MT002-TDIC-GA11-X920000-0102 | 2024-06-13 |  | Open
1035 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | PLAN ±0.000；SECTION 1-1,2-2,3-3,4-4 - MT002-TDIC-GA10-D320000-0001 | 2024-06-26 | 2024-08-27 | Closed
1036 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | PLAN FOUNDATION ±0.000,7.200；AXIS 3 WALL HOLE DETAIL - MT002-TDIC-GA11-D320000-0001 | 2024-06-26 | 2024-08-27 | Closed
1037 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | FLOW SHEET - MT002-TDIC-ME01-D320000-0001 | 2024-06-26 | 2024-08-27 | Closed
1038 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | FLOW SHEET - MT002-TDIC-ME01-D320000-0002 | 2024-06-26 | 2024-08-27 | Closed
1039 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | PROCESS EQUIPMENT LIST - MT002-TDIC-ME04-D320000-0001 | 2024-06-26 | 2024-08-27 | Closed
1040 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | 3D modeling - MT002-TDIC-GA10-D320000-0000 | 2024-06-26 | 2024-08-27 | Closed
1041 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Piping General Arrangement- Isometric drawings - MT002-TDIC-ME50-D320000-0001 | 2024-11-27 | 2024-08-27 | Closed
1042 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Piping- Bill of quantities - MT002-TDIC-ME51-D320000-0001 | 2024-11-27 | 2024-08-27 | Closed
1043 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Compressor D32CX01~03 - MT002-TDIC-ME12-D32CX01-0001 | 2024-06-26 | 2024-07-25 | Closed
1044 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | DATASHEET of Compressor D32CX01~03 - MT002-TDIC-ME10-D32CX01-0001 | 2024-06-26 | 2024-08-16 | Closed
1045 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Compressor D32CX05~06 - MT002-TDIC-ME12-D32CX05-0001 | 2024-06-26 | 2024-07-25 | Closed
1046 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | DATASHEET of Compressor D32CX05~06 - MT002-TDIC-ME10-D32CX05-0001 | 2024-06-26 | 2024-08-16 | Closed
1047 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Air Dryer D32AY01~03 - MT002-TDIC-ME12-D32AY01-0001 | 2024-06-26 | 2024-07-25 | Closed
1048 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Air Dryer D32AY05~06 - MT002-TDIC-ME12-D32AY05-0001 | 2024-06-26 | 2024-07-25 | Closed
1049 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Filter D32WS01~03 - MT002-TDIC-ME12-D32WS01-0001 | 2024-06-26 | 2024-07-25 | Closed
1050 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Filter D32WS05~07 - MT002-TDIC-ME12-D32WS05-0001 | 2024-06-26 | 2024-07-25 | Closed
1051 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Filter D32WS08~09 - MT002-TDIC-ME12-D32WS08-0001 | 2024-06-26 | 2024-07-25 | Closed
1052 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | Filter D32WS10~11 - MT002-TDIC-ME12-D32WS10-0001 | 2024-06-26 | 2024-07-25 | Closed
1053 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV01 - MT002-TDIC-ME12-D32PV01-0001 | 2024-06-26 | 2024-06-28 | Closed
1054 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV02 - MT002-TDIC-ME12-D32PV02-0001 | 2024-06-26 |  | Open
1055 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV03 - MT002-TDIC-ME12-D32PV03-0001 | 2024-06-26 |  | Open
1056 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV05 - MT002-TDIC-ME12-D32PV05-0001 | 2024-06-26 |  | Open
1057 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV06 - MT002-TDIC-ME12-D32PV06-0001 | 2024-06-26 |  | Open
1058 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV07 - MT002-TDIC-ME12-D32PV07-0001 | 2024-06-26 | 2024-06-28 | Closed
1059 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV08 - MT002-TDIC-ME12-D32PV08-0001 | 2024-06-26 |  | Open
1060 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV09 - MT002-TDIC-ME12-D32PV09-0001 | 2024-06-26 |  | Open
1061 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV10 - MT002-TDIC-ME12-D32PV10-0001 | 2024-06-26 | 2024-06-28 | Closed
1062 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV11 - MT002-TDIC-ME12-D32PV11-0001 | 2024-06-26 |  | Open
1063 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV12 - MT002-TDIC-ME12-D32PV12-0001 | 2024-06-26 |  | Open
1064 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV13 - MT002-TDIC-ME12-D32PV13-0001 | 2024-06-26 | 2024-06-28 | Closed
1065 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV14 - MT002-TDIC-ME12-D32PV14-0001 | 2024-06-26 |  | Open
1066 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV15 - MT002-TDIC-ME12-D32PV15-0001 | 2024-06-26 |  | Open
1067 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV16 - MT002-TDIC-ME12-D32PV16-0001 | 2024-06-26 |  | Open
1068 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV17 - MT002-TDIC-ME12-D32PV17-0001 | 2024-06-26 |  | Open
1069 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV18 - MT002-TDIC-ME12-D32PV18-0001 | 2024-06-26 |  | Open
1070 | Mechanical | Mechanical & Process | D32 - COMPRESSED AIR STATION | AIR TANK D32PV18 - MT002-TDIC-ME12-D32PV18-0001 | 2024-06-26 |  | Open
1071 | E&I | E&I Engg. | COMMON DOCUMENTS | Maximum demand calculation & Power Transformer Sizing - | 2024-07-30 |  | Open
1072 | E&I | E&I Engg. | COMMON DOCUMENTS | LV & MV Switchboard Feeder list - | 2024-07-30 |  | Open
1073 | E&I | E&I Engg. | COMMON DOCUMENTS | Typical IMCC wiring scheme - | 2024-08-01 |  | Open
1074 | E&I | E&I Engg. | COMMON DOCUMENTS | Over all plant Earthing calculation - | 2024-09-02 |  | Open
1075 | E&I | E&I Engg. | COMMON DOCUMENTS | MV / LV Power cable sizing Concept - | 2024-07-03 |  | Open
1076 | E&I | E&I Engg. | COMMON DOCUMENTS | MV Key Single line diagram - | 2024-07-30 |  | Open
1077 | E&I | E&I Engg. | COMMON DOCUMENTS | Emergency Power Distribution Scheme - | 2024-07-30 |  | Open
1078 | E&I | E&I Engg. | COMMON DOCUMENTS | Over all Cable tray routing along with cross section details of Gantry/trench/Tunnel - | 2024-09-02 |  | Open
1079 | E&I | E&I Engg. | COMMON DOCUMENTS | Over all Plant Earthing along with details & notes - | 2024-09-02 |  | Open
1080 | E&I | E&I Engg. | COMMON DOCUMENTS | Street lighting and pipe crossing location for roads - | 2024-09-02 |  | Open
1081 | E&I | E&I Engg. | COMMON DOCUMENTS | Over all plant Lightning protection with details & notes include risk assesment and LPL level calculation as per IEC. - | 2024-09-02 |  | Open
1082 | E&I | E&I Engg. | COMMON DOCUMENTS | Process and Instrumentation Diagram with Asset code - | 2024-08-01 |  | Open
1083 | E&I | E&I Engg. | COMMON DOCUMENTS | Instrumentation and Sensor list - | 2024-08-01 |  | Open
1084 | E&I | E&I Engg. | COMMON DOCUMENTS | Subcontrol system list - | 2024-08-01 |  | Open
1085 | E&I | E&I Engg. | COMMON DOCUMENTS | Instrument Hookup drawings - | 2024-07-30 |  | Open
1086 | E&I | E&I Engg. | COMMON DOCUMENTS | Block interlock diagrams Section wise - | 2024-09-02 |  | Open
1087 | E&I | E&I Engg. | COMMON DOCUMENTS | Process control System Architecture (PCS) - | 2024-08-01 |  | Open
1088 | E&I | E&I Engg. | COMMON DOCUMENTS | Load flow analysis with Motor Acceleration for Main Motors - | 2024-09-02 |  | Open
1089 | E&I | E&I Engg. | COMMON DOCUMENTS | Short Circuit Calculation - | 2024-09-02 |  | Open
1090 | E&I | E&I Engg. | COMMON DOCUMENTS | Relay setting & Relay co-ordination chart - | 2024-09-02 |  | Open
1091 | E&I | E&I Engg. | COMMON DOCUMENTS | Arc Flash Study with Feeder Tags - | 2024-08-01 |  | Open
1092 | E&I | E&I Engg. | COMMON DOCUMENTS | Harmonics analysis after Commissioning - | 2024-09-02 |  | Open
1093 | E&I | E&I Engg. | COMMON DOCUMENTS | Erection bill of quantity - | 2024-08-01 |  | Open
1094 | E&I | E&I Engg. | COMMON DOCUMENTS | MV cable drum cutting Schedule - | 2024-07-30 |  | Open
1095 | E&I | E&I Engg. | COMMON DOCUMENTS | LV Consumer List with Motor Frame size make NDE and DE Bearing type - | 2024-08-01 |  | Open
1096 | E&I | E&I Engg. | COMMON DOCUMENTS | MV Consumer List with Motor Frame size make NDE and DE Bearing type - | 2024-08-01 |  | Open
1097 | E&I | E&I Engg. | COMMON DOCUMENTS | LV VFD Rating and Model Nos - | 2024-07-30 |  | Open
1098 | E&I | E&I Engg. | COMMON DOCUMENTS | MV VFD Rating and Model Nos - | 2024-07-30 |  | Open
1099 | E&I | E&I Engg. | COMMON DOCUMENTS | List of Power and Distribution and Converter duty Transformer - | 2024-07-30 |  | Open
1100 | E&I | E&I Engg. | COMMON DOCUMENTS | Battery & Battery charger sizing calculation - | 2024-07-30 |  | Open
1101 | E&I | E&I Engg. | COMMON DOCUMENTS | Airconditiong System Consolidated list - | 2024-07-03 |  | Open
1102 | E&I | E&I Engg. | COMMON DOCUMENTS | MV Cable Vendor Datasheet as per Adani format' - | 2024-06-28 |  | Open
1103 | E&I | E&I Engg. | COMMON DOCUMENTS | LV Cable Vendor Datasheet as per Adani format' - | 2024-06-28 |  | Open
1104 | E&I | E&I Engg. | COMMON DOCUMENTS | Control Cable Vendor Datasheet as per Adani format' - | 2024-06-27 |  | Open
1105 | E&I | E&I Engg. | COMMON DOCUMENTS | Signal Cable Vendor Datasheet as per Adani format' - | 2024-06-27 |  | Open
1106 | E&I | E&I Engg. | COMMON DOCUMENTS | Cable Tray Vendor Datasheet & Drawing - | 2024-06-27 |  | Open
1107 | E&I | E&I Engg. | COMMON DOCUMENTS | Earthing Material Vendor Datasheet & Drawing - | 2024-06-22 |  | Open
1108 | E&I | E&I Engg. | COMMON DOCUMENTS | High Mast and Lighting Vendor Datasheet & Drawings - | 2024-08-01 |  | Open
1109 | E&I | E&I Engg. | COMMON DOCUMENTS | Network Layout of PCS Vendor Drawing - | 2024-08-01 |  | Open
1110 | E&I | E&I Engg. | COMMON DOCUMENTS | PCS BOQ - | 2024-07-03 |  | Open
1111 | E&I | E&I Engg. | COMMON DOCUMENTS | IO Assignment Drawing Controller wise - | 2024-07-03 |  | Open
1112 | E&I | E&I Engg. | COMMON DOCUMENTS | Network Backbone Architecture, GA and wiring Vendor drawing - | 2024-08-01 |  | Open
1113 | E&I | E&I Engg. | COMMON DOCUMENTS | Control room layout (in existing CCR & LCR) - | 2024-07-30 |  | Open
1114 | E&I | E&I Engg. | COMMON DOCUMENTS | VCS GA and Rating - | 2024-08-01 |  | Open
1115 | E&I | E&I Engg. | COMMON DOCUMENTS | LPBS GA, IGA and wiring drawing - | 2024-08-01 |  | Open
1116 | E&I | E&I Engg. | COMMON DOCUMENTS | Junction box GA drawing - | 2024-08-01 |  | Open
1117 | E&I | E&I Engg. | COMMON DOCUMENTS | Misc. Distribution Box Vendor Drawing - | 2024-08-01 |  | Open
1118 | E&I | E&I Engg. | COMMON DOCUMENTS | EMS Architecture Vendor Drawing - | 2024-08-01 |  | Open
1119 | E&I | E&I Engg. | COMMON DOCUMENTS | List of all software and licenses. - | 2024-08-01 |  | Open
1120 | E&I | E&I Engg. | COMMON DOCUMENTS | Energy management system including system configuration, Networking scheme & integration with PCS, - | 2024-08-01 |  | Open
1121 | E&I | E&I Engg. | COMMON DOCUMENTS | Ambient Air Quality monitoring system: Technical specifications, BOM, GA/ IGA Vendor Drawings - | 2024-09-02 |  | Open
1122 | E&I | E&I Engg. | COMMON DOCUMENTS | O&M Manual list - | 2024-09-02 |  | Open
1123 | E&I | E&I Engg. | COMMON DOCUMENTS | As Built Drawings - | 2024-09-02 |  | Open
1124 | E&I | E&I Engg. | COMMON DOCUMENTS | Alarm and Trip schedule - | 2024-08-01 |  | Open
1125 | E&I | E&I Engg. | COMMON DOCUMENTS | Welding Sockets, 3ph/1ph Industrial Sockets and 1 ph Commercial Socket Vendor drawings - | 2024-08-01 | 2024-08-05 | Closed
1126 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-212IM01-0001 | 2024-08-01 | 2024-06-12 | Closed
1127 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-212IM01-0002 | 2024-08-01 | 2024-06-12 | Closed
1128 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-362FN03-0001 | 2024-08-01 | 2024-06-12 | Closed
1129 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-362GB0A-0001 | 2024-08-01 | 2024-06-12 | Closed
1130 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-362GB0B-0001 | 2024-08-01 | 2024-06-12 | Closed
1131 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-363FN03-0001 | 2024-08-01 | 2024-06-12 | Closed
1132 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-363GB0A-0001 | 2024-08-01 | 2024-06-12 | Closed
1133 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-363GB0B-0001 | 2024-08-01 | 2024-06-12 | Closed
1134 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-422FN01-0001 | 2024-08-01 | 2024-06-12 | Closed
1135 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-442FN01-0001 | 2024-08-01 | 2024-06-12 | Closed
1136 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-462KL01-0001 | 2024-08-01 | 2024-06-12 | Closed
1137 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-472FN03-0001 | 2024-08-01 | 2024-06-12 | Closed
1138 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-L62FN01-0001 | 2024-08-01 | 2024-06-12 | Closed
1139 | E&I | E&I Engg. | COMMON DOCUMENTS | MV MOTOR data sheet - MT002-TDIC-E810-L62RM01-0001 | 2024-08-01 | 2024-06-12 | Closed
1140 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-362BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1141 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-362BE02-0M01 | 2024-08-01 | 2024-06-23 | Closed
1142 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-363BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1143 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-363BE02-0M01 | 2024-08-01 | 2024-06-23 | Closed
1144 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-362BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1145 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-362BE02-0M01 | 2024-08-01 | 2024-06-23 | Closed
1146 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-363BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1147 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-363BE02-0M01 | 2024-08-01 | 2024-06-23 | Closed
1148 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-392BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1149 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E801-432BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1150 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-392BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1151 | E&I | E&I Engg. | COMMON DOCUMENTS | MOTOR DATA SHEET - MT002-TDIC-E810-432BE01-0M01 | 2024-08-01 | 2024-06-23 | Closed
1152 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Equipment Layout Drawing - | 2024-06-22 |  | Open
1153 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Load centre Earthing & Lightning Drawing with Calculation - | 2024-06-22 |  | Open
1154 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Lighting calculation & arrangement drawing for Load centre - | 2024-08-01 |  | Open
1155 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | MV Single line diagram - | 2024-06-20 |  | Open
1156 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Battery & Battery charger sizing calculation - | 2024-08-02 |  | Open
1157 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | LV Single line diagram - | 2024-07-15 |  | Open
1158 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | MV switchboard Vendor Drawings - | 2024-07-05 |  | Open
1159 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) - | 2024-08-01 |  | Open
1160 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Power transformer Vendor Drawing - | 2024-07-30 |  | Open
1161 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | NIFPS System Vendor Drawing - | 2024-07-03 |  | Open
1162 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | LRS Vendor Drawing - | 2024-07-29 |  | Open
1163 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | NGR Vendor drawing - | 2024-07-30 |  | Open
1164 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Busduct Vendor Drawing - | 2024-07-03 |  | Open
1165 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | MV motor GA Drawing with Datasheet - | 2024-08-08 |  | Open
1166 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | MV Capacitor Vendor Drawings - | 2024-08-18 |  | Open
1167 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | DG Set Vendor Drawing with AMF panel - | 2024-08-22 |  | Open
1168 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | LV Power Cable schedule - | 2024-08-03 |  | Open
1169 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Electrical Control Cable schedule - | 2024-07-11 |  | Open
1170 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Pre charging Commissioning Test Report - | 2024-09-02 |  | Open
1171 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing - | 2024-08-08 |  | Open
1172 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Control Cable schedule - | 2024-07-24 |  | Open
1173 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Signal Cable schedule - | 2024-08-01 |  | Open
1174 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings - | 2024-08-16 |  | Open
1175 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | IO Assignment - | 2024-07-12 |  | Open
1176 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Fibre and Network test - | 2024-07-26 |  | Open
1177 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | All Subcontrol system Vendor Drawings - | 2024-09-02 |  | Open
1178 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Termination Schedule - | 2024-07-28 |  | Open
1179 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Network Communication Cable Schedule - | 2024-09-06 |  | Open
1180 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing - | 2024-07-28 |  | Open
1181 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | IP addressing Document ( iMCC, PCS, EMS) - | 2024-09-07 |  | Open
1182 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Equipment location drawing (Instrument & JBs/LPB etc.) of LS Crusher building - | 2024-07-03 |  | Open
1183 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Equipment location drawing for 294BC02 - | 2024-07-05 |  | Open
1184 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Cable tray routing with Cross section details for LS Crusher building - | 2024-07-03 |  | Open
1185 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Cable tray routing with Cross section details for 294BC02 - | 2024-07-07 |  | Open
1186 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Earthing arrangement of LS Crusher building - | 2024-06-24 |  | Open
1187 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Lighting arrangement drawing for LS crusher building - | 2024-07-12 |  | Open
1188 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Lightning protection arrangement drawing for LS crusher building - | 2024-07-03 |  | Open
1189 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Communication Cable Schedule - | 2024-08-02 |  | Open
1190 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Earthing arrangement along 293BC01 - | 2024-06-27 |  | Open
1191 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Lighting arrangement along 293BC01 - | 2024-07-13 |  | Open
1192 | E&I | E&I Engg. | Limestone Crusher (201-3E1 LC#21) - 214 | Cable tray routing with Cross section detais for 293BC01 - | 2024-07-09 |  | Open
1193 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Equipment Layout Drawing | 2024-06-26 |  | Open
1194 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Load centre Earthing Drawing with Calculation | 2024-06-26 |  | Open
1195 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Lighting calculation & arrangement drawing for Load centre | 2024-08-05 |  | Open
1196 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | MV Single line diagram | 2024-06-24 |  | Open
1197 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Battery & Battery charger sizing calculation | 2024-08-06 |  | Open
1198 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | LV Single line diagram | 2024-07-19 |  | Open
1199 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | MV switchboard Vendor Drawings | 2024-07-07 |  | Open
1200 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-05 |  | Open
1201 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Busduct Vendor Drawing | 2024-07-07 |  | Open
1202 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | MV motor GA Drawing with Datasheet | 2024-08-13 |  | Open
1203 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | MV Capacitor Vendor Drawings | 2024-08-25 |  | Open
1204 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | LV Power Cable schedule | 2024-08-07 |  | Open
1205 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Electrical Control Cable schedule | 2024-07-15 |  | Open
1206 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Pre charging Commissioning Test Report | 2024-09-07 |  | Open
1207 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-11 |  | Open
1208 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-07-30 |  | Open
1209 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Control Cable schedule | 2024-07-28 |  | Open
1210 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Signal Cable schedule | 2024-08-05 |  | Open
1211 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-19 |  | Open
1212 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | IO Assignment | 2024-07-17 |  | Open
1213 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | All Subcontrol system Vendor Drawings | 2024-09-06 |  | Open
1214 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Termination Schedule | 2024-08-02 |  | Open
1215 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Network Communication Cable Schedule | 2024-09-11 |  | Open
1216 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-09 |  | Open
1217 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Communication Cable Schedule | 2024-08-05 |  | Open
1218 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Cable tray routing with Cross section detais for LS Stockpile | 2024-07-11 |  | Open
1219 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Earthing arrangement of LS Stockpile | 2024-06-30 |  | Open
1220 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Lighting arrangement of LS Stockpile | 2024-07-16 |  | Open
1221 | E&I | E&I Engg. | Raw Material Handling (201-3E3 LC#23) | Lightning protection arrangement for LS Stockpile | 2024-07-05 |  | Open
1222 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment Layout Drawing | 2024-06-28 |  | Open
1223 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Load centre Earthing Drawing with Calculation | 2024-06-28 |  | Open
1224 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting calculation & arrangement drawing for Load centre | 2024-08-08 |  | Open
1225 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | MV Single line diagram | 2024-06-26 |  | Open
1226 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | LV Single line diagram | 2024-07-21 |  | Open
1227 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | MV switchboard Vendor Drawings | 2024-07-08 |  | Open
1228 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-07 |  | Open
1229 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | LRS Vendor Drawing | 2024-08-02 |  | Open
1230 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Busduct Vendor Drawing | 2024-07-09 |  | Open
1231 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | MV motor GA Drawing with Datasheet | 2024-08-15 |  | Open
1232 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | LV Power Cable schedule | 2024-08-09 |  | Open
1233 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Electrical Control Cable schedule | 2024-07-17 |  | Open
1234 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Pre charging Commissioning Test Report | 2024-09-09 |  | Open
1235 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-13 |  | Open
1236 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-03 |  | Open
1237 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Control Cable schedule | 2024-07-30 |  | Open
1238 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Signal Cable schedule | 2024-08-06 |  | Open
1239 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-22 |  | Open
1240 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Opacity Monitor GA, Datasheet Vendor drawings (LC applicable) | 2024-08-04 |  | Open
1241 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | CEMS Vendor drawing (Pyro) | 2024-07-30 |  | Open
1242 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Gas Analyser Vendor drawing ( Pyro lc)) | 2024-08-01 |  | Open
1243 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Kiln Shell Scanner (Pyro lc) vendor Drawing | 2024-08-01 |  | Open
1244 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | IO Assignment | 2024-07-18 |  | Open
1245 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | All Subcontrol system Vendor Drawings | 2024-09-08 |  | Open
1246 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Termination Schedule | 2024-08-04 |  | Open
1247 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Network Communication Cable Schedule | 2024-09-12 |  | Open
1248 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-11 |  | Open
1249 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | TERMINAL DIAGRAM | 2024-05-07 | 2024-05-08 | Closed
1250 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | SCHEMATIC DIAGRAM | 2024-05-07 | 2024-05-08 | Closed
1251 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Communication Cable Schedule | 2024-08-07 |  | Open
1252 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for 333BC01 | 2024-07-09 |  | Open
1253 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Raw material storage bin building | 2024-07-11 |  | Open
1254 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing for Raw material storage bin building | 2024-07-12 |  | Open
1255 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing for Raw material storage bin building | 2024-07-02 |  | Open
1256 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing for Raw material storage bin building | 2024-07-18 |  | Open
1257 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement drawing for Raw material storage bin building | 2024-07-07 |  | Open
1258 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Raw mill building-1 | 2024-07-13 |  | Open
1259 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing for Raw mill building-1 | 2024-07-14 |  | Open
1260 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing for Raw mill building-1 | 2024-07-03 |  | Open
1261 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing for Raw mill building-1 | 2024-07-21 |  | Open
1262 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement drawing for Raw mill building-1 | 2024-07-09 |  | Open
1263 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Raw mill building-2 | 2024-07-15 |  | Open
1264 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing for Raw mill building-2 | 2024-07-15 |  | Open
1265 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing for Raw mill building-2 | 2024-07-07 |  | Open
1266 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing for Raw mill building-2 | 2024-07-23 |  | Open
1267 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement drawing for Raw mill building-2 | 2024-07-11 |  | Open
1268 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Preheater building | 2024-07-17 |  | Open
1269 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing for Preheater building | 2024-07-16 |  | Open
1270 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing for Preheater building | 2024-07-11 |  | Open
1271 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing for Preheater building | 2024-07-24 |  | Open
1272 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement drawing for Preheater building | 2024-07-13 |  | Open
1273 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Raw meal silo | 2024-07-18 |  | Open
1274 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing for Raw meal silo | 2024-07-17 |  | Open
1275 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing for Raw meal silo | 2024-07-27 |  | Open
1276 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing for Raw meal silo | 2024-07-13 |  | Open
1277 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement drawing for Raw meal silo | 2024-07-15 |  | Open
1278 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing at Kiln platform | 2024-07-20 |  | Open
1279 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing at Kiln platform | 2024-07-29 |  | Open
1280 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing at Kiln platform | 2024-07-19 |  | Open
1281 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing at Kiln platform | 2024-07-15 |  | Open
1282 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing at Kiln dedusting area | 2024-07-22 |  | Open
1283 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing drawing at Kiln dedusting | 2024-07-22 |  | Open
1284 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement drawing at Kiln dedusting | 2024-07-16 |  | Open
1285 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement drawing at Kiln dedusting | 2024-07-31 |  | Open
1286 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | RM BH opacity monitor drawing | 2024-08-06 |  | Open
1287 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Communication Cable Schedule | 2024-08-10 |  | Open
1288 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for 313BC02 | 2024-07-23 |  | Open
1289 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing for 313BC02 | 2024-07-26 |  | Open
1290 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement for 313BC02 | 2024-07-18 |  | Open
1291 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement for 313BC02 | 2024-08-02 |  | Open
1292 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Equipment location drawing for Raw mill feed hopper building | 2024-07-27 |  | Open
1293 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Cable tray routing for Raw mill feed hopper building | 2024-07-29 |  | Open
1294 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Earthing arrangement for Raw mill feed hopper building | 2024-07-19 |  | Open
1295 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lighting arrangement for Raw mill feed hopper building | 2024-08-04 |  | Open
1296 | E&I | E&I Engg. | Raw Mill & Preheater (401-3E1 LC#24) | Lightning protection arrangement for Raw mill feed hopper building | 2024-07-17 |  | Open
1297 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Equipment Layout Drawing | 2024-07-02 |  | Open
1298 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Load centre Earthing Drawing with Calculation | 2024-07-02 |  | Open
1299 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Lighting calculation & arrangement drawing for Load centre | 2024-08-12 |  | Open
1300 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | MV Single line diagram | 2024-07-01 |  | Open
1301 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | LV Single line diagram | 2024-07-25 |  | Open
1302 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | MV switchboard Vendor Drawings | 2024-07-10 |  | Open
1303 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-11 |  | Open
1304 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Busduct Vendor Drawing | 2024-07-13 |  | Open
1305 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | MV motor GA Drawing with Datasheet | 2024-08-18 |  | Open
1306 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | DG Set Vendor Drawing with AMF panel | 2024-08-25 |  | Open
1307 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | LV Power Cable schedule | 2024-08-13 |  | Open
1308 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Electrical Control Cable schedule | 2024-07-21 |  | Open
1309 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Pre charging Commissioning Test Report | 2024-09-13 |  | Open
1310 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-17 |  | Open
1311 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-07 |  | Open
1312 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Control Cable schedule | 2024-08-03 |  | Open
1313 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Signal Cable schedule | 2024-08-09 |  | Open
1314 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-26 |  | Open
1315 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Opacity Monitor GA, Datasheet Vendor drawings (LC applicable) | 2024-08-08 |  | Open
1316 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | IO Assignment | 2024-07-23 |  | Open
1317 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Fibre and Network test | 2024-07-30 |  | Open
1318 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | All Subcontrol system Vendor Drawings | 2024-09-13 |  | Open
1319 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Termination Schedule | 2024-08-07 |  | Open
1320 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Network Communication Cable Schedule | 2024-09-16 |  | Open
1321 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-14 |  | Open
1322 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Communication Cable Schedule | 2024-08-13 |  | Open
1323 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Equipment location drawing for Cooler building | 2024-07-30 |  | Open
1324 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Cable tray routing drawing for Cooler building | 2024-07-31 |  | Open
1325 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Earthing arrangement drawing for Cooler building | 2024-07-21 |  | Open
1326 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Lighting arrangement drawing for Cooler building | 2024-08-07 |  | Open
1327 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Lightning protection arrangement drawing for Cooler building | 2024-07-19 |  | Open
1328 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Equipment location drawing for Coal mill building | 2024-08-02 |  | Open
1329 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Cable tray routing drawing for Coal mill building | 2024-08-03 |  | Open
1330 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Earthing arrangement drawing for Coal mill building | 2024-07-23 |  | Open
1331 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Lighting arrangement drawing for Coal mill building | 2024-08-08 |  | Open
1332 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Lightning protection arrangement drawing for Coal mill building | 2024-07-21 |  | Open
1333 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Coal dust feeder vendor drawing | 2024-07-25 | 2024-07-15 | Closed
1334 | E&I | E&I Engg. | Clinker Cooler & Coal Mill (401-3E2 LC#25) | Coal dust feeder vendor datasheet | 2024-07-31 | 2024-07-15 | Closed
1335 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Equipment Layout Drawing | 2024-07-04 |  | Open
1336 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Load centre Earthing Drawing with Calculation | 2024-07-04 |  | Open
1337 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Lighting calculation & arrangement drawing for Load centre | 2024-08-14 |  | Open
1338 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | MV Single line diagram | 2024-07-03 |  | Open
1339 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | LV Single line diagram | 2024-07-27 |  | Open
1340 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | MV switchboard Vendor Drawings | 2024-07-11 |  | Open
1341 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-13 |  | Open
1342 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Busduct Vendor Drawing | 2024-07-15 |  | Open
1343 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | LV Power Cable schedule | 2024-08-15 |  | Open
1344 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Electrical Control Cable schedule | 2024-07-23 |  | Open
1345 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Pre charging Commissioning Test Report | 2024-09-15 |  | Open
1346 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-19 |  | Open
1347 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-09 |  | Open
1348 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Control Cable schedule | 2024-08-05 |  | Open
1349 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Signal Cable schedule | 2024-08-10 |  | Open
1350 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-27 |  | Open
1351 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | IO Assignment | 2024-07-27 |  | Open
1352 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Fibre and Network test | 2024-07-31 |  | Open
1353 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | All Subcontrol system Vendor Drawings | 2024-09-14 |  | Open
1354 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Termination Schedule | 2024-08-09 |  | Open
1355 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Network Communication Cable Schedule | 2024-09-17 |  | Open
1356 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-17 |  | Open
1357 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Communication Cable Schedule | 2024-08-16 |  | Open
1358 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Equipment location drawing for Coal wagon tippler | 2024-08-05 |  | Open
1359 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Cable tray routing drawing for Coal wagon tippler | 2024-08-07 |  | Open
1360 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Earthing arrangement drawing for Coal wagon tippler | 2024-07-25 |  | Open
1361 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Lighting arrangement drawing for Coal wagon tippler | 2024-08-11 |  | Open
1362 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Lightning protection arrangement drawing for Coal wagon tippler | 2024-07-23 |  | Open
1363 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Equipment location drawing for Additive storage shead | 2024-08-09 |  | Open
1364 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Cable tray routing drawing for Additive storage shead | 2024-08-09 |  | Open
1365 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Earthing arrangement drawing for Additive storage shead | 2024-07-27 |  | Open
1366 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Lighting arrangement drawing for Additive storage shead | 2024-08-13 |  | Open
1367 | E&I | E&I Engg. | Wagon tippler & Coal handling (L01-3E1 LC#26) | Lightning protection arrangement drawing for Additive storage shead | 2024-07-25 |  | Open
1368 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Equipment Layout Drawing | 2024-07-06 |  | Open
1369 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Load centre Earthing Drawing with Calculation | 2024-07-06 |  | Open
1370 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Lighting calculation & arrangement drawing for Load centre | 2024-08-16 |  | Open
1371 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | MV Single line diagram | 2024-07-05 |  | Open
1372 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | LV Single line diagram | 2024-07-29 |  | Open
1373 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | MV switchboard Vendor Drawings | 2024-07-12 |  | Open
1374 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-15 |  | Open
1375 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Busduct Vendor Drawing | 2024-07-17 |  | Open
1376 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | LV Power Cable schedule | 2024-08-17 |  | Open
1377 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Electrical Control Cable schedule | 2024-07-25 |  | Open
1378 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Pre charging Commissioning Test Report | 2024-09-17 |  | Open
1379 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-21 |  | Open
1380 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-11 |  | Open
1381 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Control Cable schedule | 2024-08-09 |  | Open
1382 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Signal Cable schedule | 2024-08-11 |  | Open
1383 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-29 |  | Open
1384 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | IO Assignment | 2024-07-29 |  | Open
1385 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Fibre and Network test | 2024-08-02 |  | Open
1386 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | All Subcontrol system Vendor Drawings | 2024-09-15 |  | Open
1387 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Termination Schedule | 2024-08-11 |  | Open
1388 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Network Communication Cable Schedule | 2024-09-19 |  | Open
1389 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-19 |  | Open
1390 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Communication Cable Schedule | 2024-08-19 |  | Open
1391 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Equipment location drawing for Corrective storage shead | 2024-08-11 |  | Open
1392 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Cable tray routing drawing for Corrective storage shead | 2024-08-11 |  | Open
1393 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Earthing arrangement drawing for Corrective storage shead | 2024-07-29 |  | Open
1394 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Lighting arrangement drawing for Corrective storage shead | 2024-08-15 |  | Open
1395 | E&I | E&I Engg. | Corrective handling (201-3E4 LC#27) | Lightning protection arrangement drawing for Corrective storage shead | 2024-07-27 |  | Open
1396 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Equipment Layout Drawing | 2024-07-08 |  | Open
1397 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Load centre Earthing Drawing with Calculation | 2024-07-08 |  | Open
1398 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Lighting calculation & arrangement drawing for Load centre | 2024-08-18 |  | Open
1399 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | MV Single line diagram | 2024-07-07 |  | Open
1400 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | LV Single line diagram | 2024-07-31 |  | Open
1401 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | MV switchboard Vendor Drawings | 2024-07-13 |  | Open
1402 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-17 |  | Open
1403 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Busduct Vendor Drawing | 2024-07-19 |  | Open
1404 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | LV Power Cable schedule | 2024-08-19 |  | Open
1405 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Electrical Control Cable schedule | 2024-07-27 |  | Open
1406 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Pre charging Commissioning Test Report | 2024-09-19 |  | Open
1407 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-23 |  | Open
1408 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-15 |  | Open
1409 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Control Cable schedule | 2024-08-13 |  | Open
1410 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Signal Cable schedule | 2024-08-12 |  | Open
1411 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-30 |  | Open
1412 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | IO Assignment | 2024-08-01 |  | Open
1413 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Fibre and Network test | 2024-08-07 |  | Open
1414 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | All Subcontrol system Vendor Drawings | 2024-09-17 |  | Open
1415 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Termination Schedule | 2024-08-14 |  | Open
1416 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Network Communication Cable Schedule | 2024-09-23 |  | Open
1417 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-21 |  | Open
1418 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Communication Cable Schedule | 2024-08-22 |  | Open
1419 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Equipment location drawing for Fire water pump house | 2024-08-14 |  | Open
1420 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Cable tray routing drawing for Fire water pump house | 2024-08-13 |  | Open
1421 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Earthing arrangement drawing for Fire water pump house | 2024-08-05 |  | Open
1422 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Lighting arrangement drawing for Fire water pump house | 2024-08-17 |  | Open
1423 | E&I | E&I Engg. | Water Treatment & Fire Hydrant (M33-3E1 LC#28) | Lightning protection arrangement drawing for Fire water pump house | 2024-07-29 |  | Open
1424 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Equipment Layout Drawing | 2024-07-10 |  | Open
1425 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Load centre Earthing Drawing with Calculation | 2024-07-10 |  | Open
1426 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Lighting calculation & arrangement drawing for Load centre | 2024-08-20 |  | Open
1427 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | MV Single line diagram | 2024-07-09 |  | Open
1428 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | LV Single line diagram | 2024-08-03 |  | Open
1429 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | MV switchboard Vendor Drawings | 2024-07-14 |  | Open
1430 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Busduct Vendor Drawing | 2024-07-21 |  | Open
1431 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | LV Power Cable schedule | 2024-08-21 |  | Open
1432 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Electrical Control Cable schedule | 2024-07-29 |  | Open
1433 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Pre charging Commissioning Test Report | 2024-09-23 |  | Open
1434 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-25 |  | Open
1435 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-18 |  | Open
1436 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Control Cable schedule | 2024-08-15 |  | Open
1437 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Signal Cable schedule | 2024-08-17 |  | Open
1438 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-08-31 |  | Open
1439 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | IO Assignment | 2024-08-03 |  | Open
1440 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Fibre and Network test | 2024-08-09 |  | Open
1441 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | All Subcontrol system Vendor Drawings | 2024-09-19 |  | Open
1442 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Termination Schedule | 2024-08-17 |  | Open
1443 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Network Communication Cable Schedule | 2024-09-25 |  | Open
1444 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-23 |  | Open
1445 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Communication Cable Schedule | 2024-08-25 |  | Open
1446 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Equipment location drawing for Clinker silo | 2024-08-16 |  | Open
1447 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Cable tray routing drawing for Clinker silo | 2024-08-16 |  | Open
1448 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Earthing arrangement drawing for Clinker silo | 2024-08-09 |  | Open
1449 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Lighting arrangement drawing for Clinker silo | 2024-08-19 |  | Open
1450 | E&I | E&I Engg. | Clinker Silo (401-3E5 LC#29) | Lightning protection arrangement drawing for Clinker silo | 2024-07-31 |  | Open
1451 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Equipment Layout Drawing | 2024-07-12 |  | Open
1452 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Load centre Earthing Drawing with Calculation | 2024-07-12 |  | Open
1453 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Lighting calculation & arrangement drawing for Load centre | 2024-08-23 |  | Open
1454 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | MV Single line diagram | 2024-07-11 |  | Open
1455 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Battery & Battery charger sizing calculation | 2024-08-08 |  | Open
1456 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | LV Single line diagram | 2024-08-05 |  | Open
1457 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | MV switchboard Vendor Drawings | 2024-07-16 |  | Open
1458 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | PCC & IMCC Vendor Drawings (GA,Scheme,BOM) | 2024-08-19 |  | Open
1459 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Busduct Vendor Drawing | 2024-07-23 |  | Open
1460 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | LV Power Cable schedule | 2024-08-23 |  | Open
1461 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Electrical Control Cable schedule | 2024-07-31 |  | Open
1462 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Pre charging Commissioning Test Report | 2024-09-25 |  | Open
1463 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Controller, I/O Panel (GA/IGA), Wiring, Networking Panel , server panel Vendor Drawing | 2024-08-27 |  | Open
1464 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | I/O Panel (GA/IGA), Wiring, Networking Panel Vendor Drawing | 2024-08-20 |  | Open
1465 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Control Cable schedule | 2024-08-18 |  | Open
1466 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Signal Cable schedule | 2024-08-19 |  | Open
1467 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Fire alarm system document GA/ IGA, Detailed System architectural drawing, BOM, Detector / sensor layout & looping Vendor drawings | 2024-09-02 |  | Open
1468 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | IO Assignment | 2024-08-06 |  | Open
1469 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Fibre and Network test | 2024-08-13 |  | Open
1470 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | All Subcontrol system Vendor Drawings | 2024-09-23 |  | Open
1471 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Termination Schedule | 2024-08-19 |  | Open
1472 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Network Communication Cable Schedule | 2024-09-27 |  | Open
1473 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | IP addressing Document ( iMCC, PCS, EMS) | 2024-09-28 |  | Open
1474 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Communication Cable Schedule | 2024-08-28 |  | Open
1475 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Equipment location drawing for Clinker unloading silo-1&2 | 2024-08-18 |  | Open
1476 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Cable tray routing drawing for Clinker unloading silo-1&2 | 2024-08-18 |  | Open
1477 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Earthing arrangement drawing for Clinker unloading silo-1&2 | 2024-08-13 |  | Open
1478 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Lighting arrangement drawing for Clinker unloading silo-1&2 | 2024-08-23 | 2024-08-04 | Closed
1479 | E&I | E&I Engg. | Clinker Loading (Rail) (401-3E6 LC#29A) | Lightning protection arrangement drawing for Clinker unloading silo-1&2 | 2024-08-03 | 2024-08-04 | Closed

## Commissioning 1
S No | Section | Description | Sub Phase 1 | Particular | No. of. Drives | Required For Commissioing | Drive Placement | Drive alignment & Welding | LCS/JB Fixng | Power & Control Cable laying | Cable Termination Panel | Cable Termination Motor | Motor Trial | Individual Trial | Load trial
1 | C | Commissioning | No Load Trials | LS Crusher to Stacker
2 | C | Commissioning | No Load Trials | LS Reclaimer To RMH
3 | C | Commissioning | No Load Trials | Additive Reclaimer to RMH
4 | C | Commissioning | No Load Trials | RMH To Blending Silo Top
5 | C | Commissioning | No Load Trials | Blending Silo Extraction To Clinker Silo Top
6 | C | Commissioning | No Load Trials | Coal Reclaimer to Fine Coal
7 | C | Commissioning | No Load Trials | Compressor, Pump House and Auxiliaries
8 | C | Commissioning | No Load Trials | Wagon Tippler (Unloading and Transport)
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Commissioning 2
S No | Section | Description | Sub Phase 1 | Particular | Total No. of Groups | Total No of Drives | No of Drives Req for commissioning | No. of Drive Trials Completed | Total No of Drive Trials Pending for commissioning | No. of Group Trials Completed | % Trials Completed
1 | C | Commissioning | Group Trials | LS Crusher to RMH | [6 empty] | 0%
2 | C | Commissioning | Group Trials | Raw Grinding | [6 empty] | 0%
3 | C | Commissioning | Group Trials | Corrective Unloading and Transport | [6 empty] | 0%
4 | C | Commissioning | Group Trials | Blending Silo Extraction To Clinker Bulk Loading | [6 empty] | 0%
5 | C | Commissioning | Group Trials | Fuel Stockpile, Transport & Grinding | [6 empty] | 0%
6 | C | Commissioning | Group Trials | Wagon Tippler (Unloading and Transport) | [6 empty] | 0%
7 | C | Commissioning | Group Trials | Compressor, Pump House and Auxiliaries | [6 empty] | 0%
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0%

## Sorting Manpower
Department | Rank
Civil | 1
Mechanical | 2
E&I | 3
Process | 4

## Ref and E&I
Refractory
S No | Sections | Scope | Duration | BL Start | BL Finish | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30
1 | PreHeater | 7080 | 212 | 2025-04-11 | 2025-11-08 |  |  |  |  | 495.6 | 920.4 | 1274.4 | 1557.6 | 1132.8 | 849.6 | 708 | 141.6
2 | Kiln | 1180 | 20 | 2025-09-25 | 2025-10-14 | 2025-09-30: 649; 2025-10-31: 531
3 | Clinker Cooler | 675 | 55 | 2025-08-12 | 2025-10-05 | 2025-08-31: 229.5; 2025-09-30: 243; 2025-10-31: 202.5
|  | 8935 | [7 empty] | 495.6 | 920.4 | 1274.4 | 1557.6 | 1362.3 | 1741.6 | 1441.5 | 141.6
[10 empty] | 495 | 920 | 1274 | 1557 | 1362 | 1741 | 1441 | 145
|  | 0 | [7 empty] | 495 | 920 | 1274 | 1557 | 1362 | 1741 | 1441 | 145
[6 empty] | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30
| Cable Laying - KM | 652 |  | 2025-05-12 | 2025-11-09 | 2025-05-31: 32.6; 2025-06-30: 97.8; 2025-07-31: 130.4; 2025-08-31: 163; 2025-09-30: 117.36; 2025-10-31: 84.76; 2025-11-30: 26.08
| Panels/Transformer Erection - Nos | 500 |  | 2025-05-13 | 2025-09-13 | 2025-05-31: 75; 2025-06-30: 95; 2025-07-31: 125; 2025-08-31: 115; 2025-09-30: 90
| E&I Work - Buildings | 50% |  | 2025-05-24 | 2025-11-15 | 2025-05-31: 2.5%; 2025-06-30: 5%; 2025-07-31: 7.5%; 2025-08-31: 7.5%; 2025-09-30: 12.5%; 2025-10-31: 10%; 2025-11-30: 5%
| Transmission Line Work | 10% |  | 2025-02-10 | 2025-10-08 |  |  | 1.111% | 1.111% | 1.111% | 1.111% | 1.111% | 1.111% | 1.111% | 1.111% | 1.111%
| E&I Work - Sub stations | 40% |  | 2025-03-14 | 2025-11-04 |  |  |  | 0.8% | 2% | 3.2% | 4.8% | 8% | 8% | 6% | 4.8% | 2.4%
|  | 100% | [5 empty] | 1.111% | 1.911% | 3.111% | 6.811% | 10.91% | 16.61% | 16.61% | 19.61% | 15.91% | 7.4%
| Mechanical & Process Drawing |  |  | 2024-01-31 | 2024-02-28 | 2024-03-27 | 2024-04-24 | 2024-05-22 | 2024-06-19 | 2024-07-17 | 2024-08-14 | 2024-09-11 | 2024-10-09 | 2024-11-06 | 2024-12-04 | 2025-01-01
| Target | 1070 |  |  | 23 | 205 | 76 | 211 | 107 | 6 | 31 | 2 | 303 | 90 | 16
0
| Actual | 445 |  | 2024-01-31: 66; 2024-02-28: 60; 2024-03-27: 71; 2024-04-24: 87; 2024-05-22: 58; 2024-06-19: 103
| E&I Drawing |  |  | 2024-01-31 | 2024-02-28 | 2024-03-27 | 2024-04-24 | 2024-05-22 | 2024-06-19 | 2024-07-17 | 2024-08-14 | 2024-09-11 | 2024-10-09 | 2024-11-06 | 2024-12-04 | 2025-01-01 | 2025-02-01
| Target | 409 | [5 empty] | 2 | 18 | 35 | 35 | 65 | 65 | 65 | 60 | 44 | 20
0
| Actual | 28 |  | 2024-05-22: 2; 2024-06-19: 26

## Sheet2 (hidden)
Saturday | 2024-02-08 |  | 1
Sunday | 2024-02-09 |  | 2
Monday | 2024-02-10 |  | 3
Tuesday | 2024-02-11 |  | 4
Wednesday | 2024-02-12 |  | 5
Thursday | 2024-02-13 |  | 6
Friday | 2024-02-14 |  | 7
Saturday | 2024-02-15 |  | 8
Sunday | 2024-02-16 |  | 9
Monday | 2024-02-17 | 1 | 10
Tuesday | 2024-02-18 | 2 | 11
Wednesday | 2024-02-19 | 3 | 12
Thursday | 2024-02-20 | 4 | 13
Friday | 2024-02-21 | 5 | 14
Saturday | 2024-02-22 | 6 | 15
Sunday | 2024-02-23 |  | 16
Monday | 2024-02-24 | 8 | 17
Tuesday | 2024-02-25 | 9 | 18
Wednesday | 2024-02-26 | 10 | 19
Thursday | 2024-02-27 | 11 | 20
Friday | 2024-02-28 | 12 | 21
Saturday | 2024-02-29 | 13 | 22
Sunday | 2024-03-01 |  | 22